## Sheet1
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
A project manager is facilitating a first brainstorming session to identify individual risks as well as sources of overall project risk. The meeting attendees are struggling with the task, and the meeting is becoming unproductive. What action might the pr | Multiple Choice | Call in the project sponsor | Adjourn the meeting | Use the RBS as a prompt list | Consult the risk register |  |  | C |  | 1
The building of an industrial plant has been stopped for four months due to region-specific prohibitions. What should the project manager have done to avoid this issue? | Multiple Choice | Documented all assumptions | Made a prioritized list of the project constraints | Crashed the project schedule | Identified this as a risk in the risk register |  |  | D |  | 1
After contract sign-off, a project manager learns that the vendor has a reputation of not delivering according to the contract. To ensure the vendor's compliance, what should the project manager do? | Multiple Choice | Conduct a make-or-buy analysis to verify vendor reliability | Insist on a firm fixed price contract (FFP) with the vendor | Perform periodic inspection of the vendor's work and progress. | Cancel the current contract and select another vendor |  |  | C |  | 1
If the outsourced deliverables don't meet the agreed-upon acceptance criteria. What should the project manager reference to verify this with the contractor? | Multiple Choice | Statement of work (SOW). | Quality log | Request for proposal (RFP). | Procurement management plan |  |  | A |  | 1
To compare different suppliers and rate their proposals, as a project manager, what should you use? | Multiple Choice | A contract. | Evaluation criteria | Bid documents | Bidder conferences |  |  | B |  | 1
You are a project manager and having a dispute with your seller over certain changes. You have met him to discuss the dispute, but you didn't reach an agreement by negotiation. What should be the best way to resolve this? | Multiple Choice | Litigation | Renegotiate if possible | Alternative dispute resolution (ADR) | Involve your sponsor to settle this claim |  |  | C |  | 1
A project management team has identified a large number of sellers who seem capable to be taken as contractors into the project supply network and allocated to work items. What should be the next step for the team? | Multiple Choice | Conduct a technical evaluation of proposals. | Invite the sellers to contract negotiations. | Sign contracts with the sellers. | Develop a short list of qualified sellers. |  |  | D |  | 1
The company is being bought out and the project that was Just started has been terminated. What should the next step be by the project manager? | Multiple Choice | Review the project management plan for closing the project. | Review the project charter as the details for the buyout are contained there. | Begin filing all of the documents as part of lessons learned. | Complete closed procurements as part of the process Control Procurements. |  |  | D |  | 1
As a project is about to close, you arrange a meeting with one of the vendors who delivered low-quality parts. You express your dissatisfaction with the vendor's performance and try to find a solution to the issue. However, the meeting does not result in | Multiple Choice | Pay the vendor to avoid a conflict | Ignore the vendor until they agree to your demands | Appoint a lawyer and go to court | Seek alternative dispute resolution |  |  | D |  | 1
You have Just been assigned as the project manager for an ongoing project in your organization. You have discovered there is no Project Charter that describes the responsibilities and authorities of the project manager. When you talked to your project spo | Multiple Choice | Conduct the project kick-off meeting and inform everyone that the project has started | Create a draft project charter and submit to your supervisor | Create the project charter and inform project team members to ensure common understanding of the key deliverables and their roles and responsibilities | Discuss the need to have a project charter with the sponsor |  |  | D |  | 1
You are a project manager in an IT project. You and key stakeholders start conducting a project benefit analysis. Because of the solutions that have not been identified, an engineer from another department has informed you that there are affected systems. | Multiple Choice | Review the project benefit analysis to consider the additional impact | Update the risk register | Document the issue in the issue log | Identify all stakeholders |  |  | C |  | 1
One of the key stakeholders requested additional features to be added to the product without changing the scope, budget, or schedule. The project manager believes that these features will add great value to the end product. However, these additions will | Multiple Choice | Schedule and cost management | Change management | Collect requirement | Scope and cost management |  |  | B |  | 1
You are managing a construction project, your cost performance is not as planned and your Project is over budget. Therefore, you again estimate the cost of the project and find that you wilt require more money to complete the project. This will require | Multiple Choice | Issue the change request. | Update Change Log. | Update the cost baseline | Terminate the Project. |  |  | A |  | 1
You are the project manager of the GHY Software Project for your company. You've recently completed the project and need to distribute the project closure report. Who should get a copy of the project closure report? | Multiple Choice | Project sponsor | Follow the guidelines established in the project's communications management plan | All stakeholders | No one. It is created for future historical information |  |  | B |  | 1
Your organization has decided to cancel some of the projects. Unfortunately, your project has been selected to be canceled, and the sponsor Informed you about the decision. The team came to know about It, and their morale Is very low. They reached out to | Multiple Choice | Award the deserving team members with rewards | Request the team members to continue the work until an official letter is received | Request the team members to update the lessons learned and organizational process assets | Talk to sponsor to revoke his decision |  |  | C |  | 1
In the final meeting to approve these deliverables that are completed in a project, some stakeholders state that the product doesn't meet their needs. What should the project manager do? | Multiple Choice | Demonstrate that the objectives in the project charter have been achieved. | Review the list of stakeholders and determine whether the appropriate individuals attended the meeting. | Validate that the deliverables are as requested and close the project | Demonstrate that the deliverables have been verified and negotiate their approval. |  |  | A |  | 1
During a project's third Iteration, the project manager informed the team that there is a new competitor in the market, and it's necessary to move faster to ensure market share is not missed. As a project manager, what should you do? | Multiple Choice | Ask the team to increase the velocity to launch the product as soon as possible | Help the team to find a new approach to launch the product as soon as possible | Ask the sponsor to add more people to the team | Add the competitor's functionalities to the product backlog to improve the product. |  |  | B |  | 1
You are a project manager in the execution phase of a residential housing construction project. The project is behind schedule and is missing some materials. The contractor submits an offer to supply the missing materials and reimburse the cost since the | Multiple Choice | Update the procurement management plan and negotiate with the contractor. | Request the contractor to review the offer and reduce the costs. | Updates the procurement strategy and negotiate with the contractor | Meet with the project sponsor and ask to allocate more budget to cover the cost. |  |  | A |  | 1
You are a project manager of a company and your project is currently in the execution phase. You have informed that most of the project team members will work from a home base on the new company policy. Which of the following will be updated to reflect t | Multiple Choice | Update the communication styles for enrolled team members in the communication management plan. | Update the stakeholder engagement plan to reflect the contact information for the team members | Update the team members' roles and responsibilities in the RACI chart. | Update the resource calendar |  |  | A |  | 1
You are the project manager of a large project for your organization. You have recently reported that the project’s SPI is 0.85 and the CPI is 1.17. You want to focus that the project is under control in the next project status review. How should the pro | Multiple Choice | Prepare a detailed presentation for stakeholders on earned value, including how it's calculated. | Report that the project is not tracking as expected, but is still under control. | Report that the project is behind schedule but that an additional experienced resource can be added to stay within schedule and maintain the budget. | Use Pareto chart and why- why diagram to demonstrate that the project is under control. |  |  | C |  | 1
The change control board (CCB) is evaluating a recently submitted change request. The project sponsor wants to deny the request. Another stakeholder is in favor of deferring the request until a later date. The project manager and other stakeholders feel | Multiple Choice | Consult the project management plan | Approve the request as the project sponsor has the final say | Defer the request until all of the stakeholders are in agreement | Approve the request as the project manager has authority to decide for the group |  |  | A |  | 1
The customer requests a supply of additional equipment to the current contract. The project manager asks the team to evaluate this request and submits a change proposal, including a cost increment of $120,000 and an extension of 4 weeks on the delivery fo | Multiple Choice | Request a further meeting with the customer to discuss the 4 week delivery extension | Sign off and accept the variation order and update the risk register. | Ask the human resources manager to hire additional resources to fast track the project. | Report to the divisional manager that the project margin has been improved due to this extra supply. |  |  | A |  | 1
During the Sprint Planning Meeting, the amount of work necessary for fulfilling the items requested by the Product Owner seems greater than the Development Team's capacity. Which action makes more sense? | Multiple Choice | The Product Owner demands that the Development Team work overtime just for this Sprint, provided this doesn't happen again. | Increasing the number of Sprints. | The Development Team and Product Owner collaborate, with a view to removing or modifying items | Cancel the Sprint. |  |  | C |  | 1
A project manager is conducting agile release planning with their recently acquired team. They are committed to working together to deliver excellent results. The client asks for a product with limited requirements because of a lack of technical knowledge | Multiple Choice | Engage the client in every iteration | Add more features to the final product | Set the requirements in a signed contract | Have the client provide their own technical engineer |  |  | A |  | 1
An agile team is tasked with the development of a robot. The project manager wants to ensure that before the actual robot is built, the team receives early feedback on requirements and adapts the design accordingly. Which of the following should the proje | Multiple Choice | Design review | Business case | Checklists | Prototyping |  |  | D |  | 1
A vendor has been contracted by a buyer to develop a new device. The vendor insisted that the contract thoroughly captures the device specifications. The buyer does not have clear requirements upfront and, therefore, requested that the vendor develop the | Multiple Choice | Pair programming over continuous integration | Individuals and interactions over processes and tools | Customer collaboration over contract negotiations | Business people and developers must work together |  |  | C |  | 1
A project team that is experienced in the waterfall project management approach has been assigned to their first agile project. To make the transition easier, it has been decided to keep some elements of the waterfall approach in place. During the iterat | Multiple Choice | Fallback to a waterfall project management framework going forward | Submit a change request to update the communications management plan | Bring up the topic during the upcoming iteration retrospective | Do nothing since the team members are transitioning from waterfall to agile |  |  | C |  | 1
You have been hired as an agile expert for an organization that is in the transition phase from predictive to the agile approach in project management. The organization has recently embarked upon the Agile Journey. Which of the following is not a chan | Multiple Choice | Existence of departmental silos | Talent management maturity and capabilities. | Executive management's commitment | Focus on short-term budgeting and metrics versus long-term goals. |  |  | A |  | 1
You are managing a complex web development project. Reviewing the project's statistics you determined that the team completes 50 story points on average per Iteration. Reviewing the backlog, you determine that there are about another 500 points remain | Multiple Choice | Agile teams cannot predict project completion | In about 20 weeks from now. | In about 10 weeks from now. | In about 75 weeks from now. |  |  | B |  | 1
A project team has recently completed the initial sprint for developing an automated payroll system for a company. The project manager has scheduled a sprint planning meeting with the product owner and team members to discuss which features should be | Multiple Response | Product backlog | Sprint goal | Sprint charter | Company mission and vision | Burn down chart |  | AB |  | 1
Your project is very complex and due to a scope change, you need a few additional experts, which you did not think of earlier. You request that your company provide you with some experts for consultancy work. Although your company has provided you with t | Multiple Choice | None of the above | Recruit new members with same skills | Create a virtual team | Ask management to bring them to you |  |  | C |  | 1
You are a project manager in Critical Project for your organization. Your project is behind schedule and over budget. Therefore, the Project Sponsor asks you if the team members may work on weekends. As a Project manager, what should you do to pers | Multiple Choice | Ignore the Sponsor | Ask the Management what should you do | Update Issue Log | Recognition and rewards |  |  | D |  | 1
While you are in one of the first meetings for your new project that you have been assigned to early, two team members were discussing new ideas that each one thinks is correct and their opinion is the best for the project. You didn’t interact or cut the | Multiple Choice | Supporting | Performing | Norming | Storming |  |  | D |  | 1
A project manager wants to recruit another team member to replace an architect who resigned. What document should capture this change? | Multiple Choice | Project management plan. | Organizational process Assets. | Ground rules | Responsibility assignments matrix (RAM) |  |  | D |  | 1
You are managing a large diversified project team. In the initial days of the project, the team members behaved like Independent Individuals and seemed reserved, learning about their roles and responsibilities. Then, as the team began to work on the pro | Multiple Choice | Adjourning | Forming | Performing | Norming |  |  | D |  | 1
Within your project team, you notice that emotions are at a high due to competition among the team members. People are quick to react rather than understanding each other's needs and responding appropriately. Due to this, team members you are strugglin | Multiple Choice | Goal setting and results management | Active listening | Team building | Emotional Intelligence |  |  | D |  | 1
A scrum master has been hired to lead a project for an organization that has no prior experience with agile methodologies. Which of the following training activities will be critical for the success of the project? | Multiple Choice | Conducting an agile workshop on the agile mindset and principles with the entire project team | Ensuring that the product owner has a clear understanding of how to groom the backlog | Training the product owner on best practices for facilitating the daily scrum meetings | Instructing the project team on how to ensure the implementation of a rigid change control process | Helping the development team to Remove any obstacles & resolving impedimentsConducting an agile workshop on the agile mindset and principles with the entire 1. |  | B |  | 1
A team is working on implementing a communications system when the client says that they are considering closing the project. The project manager schedules an urgent meeting with the client to understand why the project is risk. Which two tools or techn | Multiple Response | Alternatives analysis | Voting | Autocratic decision making | Cost benefit analysis | Multicriteria decision making |  | DE |  | 1
After completion of a project with specific users in various countries, the project manager's supervisor asks if the project users are satisfied with the way the project was run. What two actions should the project manager take? (Choose two) | Multiple Response | Prepare the lessons learned from the project phase. | Refer to the communications management plan | Obtain official approval on the new process from the various countries | Send a questionnaire to the project participants and seek their feedback. | Deliver the project materials to the users and see if they have any comments |  | BD |  | 1
A project manager has been assigned to lead a project to deploy a new system. The stakeholders disagree on the project objectives and approach. What should the project manager do? | Multiple Choice | Create a roles and responsibilities matrix based on the project charter and ask the sponsor to share it with all stakeholders to provide credible authority | Conduct a general meeting with all stakeholders and review and address a list of activities for each of them | Conduct scoping workshops with the project team to create a work breakdown structure (WBS), assign tasks to various entities share this with all stakeholders, and ask the team to complete their tasks as scheduled | Break down the situation to identify the root causes for the disagreement and then work with each stakeholder and participating entity on their exact roles and responsibilities. |  |  | D |  | 1
A project manager analyzes the cumulative flow chart and identifies a bottleneck in the testing activities from a self-organizing team. After discussing it with the team, a gap related to testing skills is identified. What should the project manager do to | Multiple Choice | Provide training to the entire team so they all will be able to perform tests. | Onboard a new project team member who has testing skills. | Support the team to identify an approach to resolve the problem. | Ask the development team to slow down so the testers can catch up. |  |  | C |  | 1
A project manager finished reviewing the project deliverables for the current iteration with the customer. A new key stakeholder who just joined the customer's team, complains that the results do not provide the capabilities the business anticipated. W | Multiple Choice | Update the project management plan and lessons learned | Create a change request and update the scope management plan | Conduct stakeholder identification and a project objectives review session | Update the stakeholder list and fix the deliverables |  |  | C |  | 1
During the design phase, a project manager realizes that the project will benefit from using adaptive tools. The effectiveness of this approach has been proven in past projects inside the organization. What should the project manager do first? | Multiple Choice | Confirm team capabilities before introducing adaptive tools and artifacts to the project | Update project documents to include adaptive tools and artifacts and plan the first iterative session | Freeze the design stage and look for an external resource to run iterative design at extra cost | Contact the project sponsor and request new team members who are familiar with adaptive projects |  |  | A |  | 1
The project team suggests to the project manager that there is no reason to perform quality control since the project tasks are very simple, The project manager understands that removing the quality management plan from the project will also help to s | Multiple Choice | Develop the quality management plan, as quality is as equally important as cost and schedule management | Ask the customer to order an external quality audit after accepting the project deliverable, and decrease the budget of the project | Register starting the project without a quality management plan as a risk, and allocate the budget savings to the management reserve | Get confirmation from management that the team member has enough experience to build software without quality control |  |  | A |  | 1
A company has a lot of experience with predictive projects The project management office (PMO) has been trying to implement iterative tools within the project management framework, and the project manager has been asked to use these tools in their cu | Multiple Choice | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project | Determine the data to be monitored during the project as well as the expected performance and targets | Prepare and submit a status report to the steering committee to update performance monitoring | Update the communications management plan to consider performance review meetings with the project stakeholders |  |  | A |  | 1
During project execution, a conflict occurs between the project manager and one of the team members at every project team meeting. The ongoing conflict is preventing tasks and deliverables from being completed. The project manager contemplates changi | Multiple Choice | Review the set of responsibilities with the team member | Escalate the situation to the project sponsor | Review the personnel skill documents | Avoid the team member to prevent further conflicts |  |  | B |  | 1
You are a project manager managing a complex project with a high level of uncertainty. A request is made to implement a method to measure the quality of the deliverables. Using a hybrid approach, what techniques can be used to achieve this goal? | Multiple Choice | Scrum master reviews and the quality Kanban method | Time-boxed iterations and review meetings | Daily Scrum and product owner quality assessments | Paired work and the customer role method |  |  | B |  | 1
A Key stakeholder wants to understand when the risk may potentially become an issue. What artifact should the project manager share with the stakeholder? | Multiple Choice | Project management plan | Issue log | Risk register | Risk management plan |  |  | C |  | 1
During the project execution, the project manager reviews the project's progress and find a few tasks that are behind schedule. After investigating, the project manager discovers that a few team members were pulled to work on other assignments, which imp | Multiple Response | Alert the business stakeholders immediately of the schedule delay | Work with the team to identify options to accelerate project delivery | Discuss the risk of project delay and work priorities with the respective functional managers | Establish daily standups to review project progress and track the completion of deliverables | Allow the team members to catch up at their own pace |  | BC |  | 1
You are a project manager of a company. The sponsor is supportive in leveraging agile approaches. The project manager is contemplating how to roll out the agile approach and gam buy-in from both project team members and stakeholders. What should the p | Multiple Choice | Select a current predictive project, define the approach, and provide agile training to execute the remainder of the project | Start with a pilot project of appropriate complexity and provide agile training to those who are impacted | Determine which agile software tools will be required to support agile delivery within the organization | Determine how to transform the organization using agile techniques, including organizational training and communications |  |  | B |  | 1
Some of the more experienced members of a project team have complained about the project manager The senior project team members feel that the project manager is micromanaging them and preventing them from completing their work. What should the project ma | Multiple Choice | Adjust the project manager's management style to better fit senior team members. | Meet daily with each senior team member to monitor project status | Set up a team-building event to bring synergy back to the project team. | Ask for advice on how to be a better mentor to these team members. |  |  | C |  | 1
Since the beginning of a project, the product owner keeps asking during ceremonies about the budget spent for each product iteration The product owner seems much more interested in the cost rather than the product itself. What should the project manager | Multiple Choice | Worked with the product owner to clarify their role in an agile project and the scope of the agile ceremonies | Worked on a fixed-price contract to switch the product owner's attention to value instead of money | Worked on a communications management plan with reports of budget spent in each iteration versus planned to avoid these discussions during ceremonies | Worked on different approaches of estimating to give confidence of the cost spent in each product increment. |  |  | A |  | 1
During the implementation phase of a construction project, a key supplier went bankrupt and cannot supply the contracted material. This issue could affect the project schedule. What should the project manager do first? | Multiple Choice | Update the schedule to include the delay | Escalate to the management team for delay approval | Add the risk and the delay to the risk register | Update the issue log and act to minimize the impact |  |  | D |  | 1
A project manager has been moved to a new division and is in charge of an existing project in an unfamiliar domain. When attempting to gain an understanding of the risks for this agile project what is the primary tool the project manager should employ? | Multiple Choice | Workshops for risk avoidance | Probability assessments | Interview with the project champion | Collaborative discussions |  |  | D |  | 1
A new project manager has been assigned to a project that is in danger of falling The stakeholders do not know the project status nor do they know what benefits will be delivered by the project. How can the project manager convey these benefits to the s | Multiple Choice | Perform a project cost-benefit analysis for the stakeholders | Rebase line the project schedule to show the current status of the project. | Create a benefits management plan mapped to the organization's strategic objectives | Update the deliverables map against the agreed-upon project requirements |  |  | A |  | 1
Internal restructuring by the customer has resulted In the replacement of some key stakeholders. What should the project manager do first? | Multiple Choice | Review and execute the communication management plan. | Review and update the stakeholder engagement plan. | Hold another kick-off meeting with the new stakeholders to re-establish the project baseline. | Distribute a summary of the project's current status to the new stakeholders. |  |  | B |  | 1
Stakeholders are persons or organizations who are actively involved in the project or whose interests may be positively or negatively affected by the performance or completion of the project. What is the best reason for stakeholder analysis In the Stake | Multiple Choice | Stakeholders help create the Project Management Plan | Stakeholders help build the WBS and Scope Statement | Stakeholders help conduct procurements | Stakeholder satisfaction is a key success criteria in a project |  |  | D |  | 1
After collecting major requirements from the stakeholders, you Identify more stakeholders that should have been part of your project. What should you do next? | Multiple Choice | Do not add them to Stakeholder Register but collect requirements from them | Do not add them to Stakeholder Register | Add them to Stakeholder Register and collect requirements from them | Create a separate Stakeholder List |  |  | C |  | 1
During a project that affects the entire organization, some groups of stakeholders appear to have low product expectations. As a result, they are not performing as expected. This may put project objectives at risk . What should the project manager do? | Multiple Choice | Speak with the problematic stakeholders to increase their performance. | Submit a change request. | Ask the project sponsor to intervene and motivate the underperforming stakeholders. | Follow the stakeholder engagement plan. |  |  | D |  | 1
A company has always utilized a predictive approach to project management, but now the project management office wants to Incorporate some agile best practices to generate earlier revenue realization. The project manager Is about to begin planning for the | Multiple Choice | Request the training from the project management office (PMO) | Empower the team to self-organize and study agile best practices | Check the lessons learned repository for agile best practices | Add the risk of the team's inadequate agile skills to the risk register |  |  | A |  | 1
A project manager is conducting a meeting with the newly hired project team. The primary purpose of the meeting is to assign roles and responsibilities to the team members. Since the team members are meeting for the first time, you have each of them intro | Multiple Choice | Forming | Norming | Storming | Performing |  |  | A |  | 1
An agile team is developing a product for a customer. in the last few iterations, the team members spent extra hours creating product documentation and reviewing the contracts with the customer. How would the team's time been better spent? | Multiple Choice | Developing functionality as requested by the project sponsor | Building features according to the initial project management plan | Creating the product increment and working with the product owner | Reporting the extra hours in the company's time and attendance tools |  |  | C |  | 1
A few days before the end of the last Iteration, the team Informs the project manager that they will be unable to finish two work packages, A and B, because the WBS Is insufficiently refined. The team thinks they might be able to complete package A on ti | Multiple Choice | Consult with the product owner and make a decision accordingly | Instruct the team to complete package A since it can be done on time | Extend the iteration length in order to finish both packages A and B | Instruct the team to complete package B since it has a higher priority |  |  | A |  | 1
You are a project manager In a construction project. What should you do to ensure the successful delivery of the project? | Multiple Choice | Establish a management reserve to handle the unknown risks when occurs | Meet with stakeholders to communicate the schedule budget, and cost impact in the event of a project delay. | Conduct a team-building activity | Identify the project's risks and necessary success criteria. |  |  | D |  | 1
A multiphase project that has been executed withinternal resources has reached a phase gate. The keyproject stakeholders want to determine if the phase hasmet its success criteria, and whether or not the projectshould progress to the next phase. In addit | Multiple Choice | Lessons learned register and lessons learned repository | Risk register and risk report | Business documents and project charter | Agreements including procurement contracts |  |  | C |  | 1
A project manager is asked to contribute to a document to describe what is Intended to be achieved with a project once it is successfully finished, and how this will be measured. What could be the name of that document? | Multiple Choice | Statement of work | Change management plan | Project management plan | Benefits management plan |  |  | D |  | 1
Which of the following techniques can ensure that the stakeholders are engaged at appropriate project phases and to obtain or confirm their continued commitment to the success of the project? | Multiple Choice | Setting ground rules | Managing project team | Performance audits | Stage gate meetings |  |  | D |  | 1
Some of your project management peers are of the opinion that leadership and project management software usage skills are some of the important skills a project manager should have. As per PMI Talent Triangle. which of the below reflects all the competen | Multiple Choice | Technical project management, leadership, strategic and business management | Project management, people management, Business and strategy | Management experience, process expertise, domain experience | Knowledge, performance, personality |  |  | A |  | 1
A customer is frequently asking for scope changes though a product vision and roadmap have been established at the start of the project. What type of development lifecycle is this likely to be? | Multiple Choice | Waterfall | Predictive | Hybrid | Adaptive |  |  | D |  | 1
A project has a senior stakeholder whose input is important, and who needs to be kept informed about the project's status. Rather than receive updates from the project manager, this stakeholder prefers to contact a team member directly. The stakeholder ha | Multiple Choice | Keep the team member properly informed about project status so that the stakeholder receives the same information from both sources. | Ask the stakeholder how the additional information that they feel is missing from current communications may be provided. | Leave the connection in place, since the information coming via the team member is unofficial and will not create problems. | Tell the team member not to accept calls from the stakeholder, because these calls have an adverse effect on the team member's members productivity. |  |  | B |  | 1
By the project management Information system (PMIS), a project management team is updating a dashboard monthly with information on the project's performance. Which of the following communication methods describes this? | Multiple Choice | Pull Communication | Interactive Communication | Manual communication | Informal communication |  |  | A |  | 1
A project manager is in charge of managing a large construction project of 4 billion USO. Various teams from different countries are involved in this project and the teams need to work cohesively and seamlessly for the success of the project. The task o | Multiple Choice | Communications management plan | Detailed definition of the work packages | Change management | Adherence to professional code of conduct |  |  | A |  | 1
The project team learns from key stakeholders that some deliverables have been forwarded for approval without their knowledge. What should the project manager have done to prevent this situation? | Multiple Choice | Scheduled a meeting with the customer and the project team | Verified the communication management plan. | Consulted the most recent meeting minutes related to deliverable | Notified the project team. |  |  | B |  | 1
Which of the following should the project managerreview to determine the cost of conformance? (Choose Three) | Multiple Response | Expenses related to the testing of individual parts of the machine prior to assembly | The economic value of lost business due to product failures | Costs associated with training of the project team | The cost of warranty claims due to defective parts or workmanship | Losses incurred as the result of destructive testing |  | ACE |  | 1
As part of a Joint venture, a project manager working with another company needs to share some confidential information related to intellectual property rights. She wants to know the person responsible for authorizing the release of this confidential inf | Multiple Choice | Project Communication Management Plan | Organizational Breakdown Structure | Stakeholder Management Plan | Project Charter |  |  | A |  | 1
Midway through project execution, several stakeholders raised concerns about team performance and delivery. The project manager believes the project is progressing as per the approved scope, budget, and schedule. What should the project manager do next? | Multiple Choice | Ask the project sponsor to interview. | Ask stakeholders to escalate their concerns to the CEO | Consult the communications management plan to manage stakeholders' expectations. | Email the stakeholders to assure them of action |  |  | C |  | 1
Melissa is managing a project. A new project sponsor frequently visits functional managers to discuss the project's status because of missing a weekly status meeting. However, the minutes are regularly sent but appear to remain unread. What should Melissa | Multiple Choice | Send the communication management plan to the sponsor. | Meet with the sponsor individually | Resend the weekly meeting minutes to the sponsor. | Direct the functional managers to stop discussing project status. |  |  | B |  | 1
You have been assigned as a project manager of a new project. You want to understand what communication technology and methods are being used in the project and would like to ensure that the project continues without disruption from the change in project | Multiple Choice | Refer to the project management plan | Refer to work performance reports | Examine the stakeholder engagement assessment matrix | Refer to the stakeholder engagement plan |  |  | A |  | 1
During the implementation phase, you want to compare the baseline to the actual results and determine if the variance is within the threshold amount or if corrective or preventive action is appropriate. Which of the following techniques can help you? | Multiple Choice | Trend analysis | Control chart | Decomposition | Variance Analysis |  |  | D |  | 1
You are busy with an important milestone, and after that, you have to deliver a deliverable to the client. Since the client is known for his difficult behavior, management is worried whether the client will accept the deliverable. Therefore, they tell you | Multiple Choice | Control Chart | Project scope statement | WBS dictionary | WBS |  |  | B |  | 1
You are the Project Manager of a large and complex project. Your project team has finished creating a Work Breakdown Structure for the project. However, some of the team members are still not sure of the kind of work included in each of their work packa | Multiple Choice | Project scope statement | Work Break Structure (WBS) Dictionary | Project Management Plan | The Product Scope document |  |  | B |  | 1
The customer has signed a contract with your organization to develop a product upgrade for them as their current product is not helping their operations due to changes in the business environment. You schedule a meeting and realize that they are not ab | Multiple Choice | Interviews | Context diagram | "Facilitation" workshop | Observation or job shadowing |  |  | D |  | 1
You have Just been assigned as project manager for a large manufacturing project. You want to understand the Process for preparing a project scope statement and how format acceptance of the completed project deliverables will be obtained. Which of the fo | Multiple Choice | The stakeholder management plan | The scope management plan | The quality management plan | The requirements management plan |  |  | B |  | 1
During the development of the scope management plan, a stakeholder requests the addition of pilot technology into the project scope to assist with product marketing. What should the project manager do? | Multiple Choice | Review the scope baseline with the stakeholder | Include the stakeholder in the scope planning meetings. | Increase the project budget with the cost of the pilot technology. | Use the project reserve for the pilot technology. |  |  | B |  | 1
A project manager finds that a specific work package was not delivered on time and will be delayed by an additional three weeks. The project manager worries that this might impact project completion. What should the project manager do first? | Multiple Choice | Determine if the work package is on the critical path | Calculate the amount of free float for the work package. | Adjust the Gantt chart for the work package. | Use schedule compression to get the project back on track. |  |  | A |  | 1
You are managing a project which will provide e-learning solutions to your customer. The requirements of this project are not clearly defined in the beginning and there will be modifications based on customer feedback as the project evolves. You plan as | Multiple Choice | Rolling wave planning | WBS | Scope management | Templates |  |  | A |  | 1
During Initial project scheduling, an internal key stakeholder announces that they already agreed on some delivery dates with a vendor. What technique should the project manager use to ensure that all prerequisites are fulfilled for those deliverables t | Multiple Choice | Internal dependencies | Discretionary dependencies | Finish-to-finish dependencies | Mandatory dependencies. |  |  | D |  | 1
You are managing a few projects and the sponsor asks you to submit CPI and TCPI numbers for them. You provided CPI = 1 for project A, CPI = 1.2 for project B, TCPI = 0.9 for project C and TCPI = 1.2 for project D. Which project do you think the sponsor mi | Multiple Choice | Project C | Project B | Project D | Project A |  |  | C |  | 1
During the team review, the project manager learns that the schedule performance Index (SPI) is 0.8 and the cost performance Index (CPI) is 0.7. The project manager asks the team members to work overtime. How will this affect the (CPI)? | Multiple Choice | It will increase. | It will decrease. | It will return to 1.0 | It will remain the same. |  |  | B |  | 1
As part of earned value management (EVM), The budget at completion (BAC) for the project is $100,000 and the estimate at completion (EAC) is $120,000. If the schedule performance Index (SPI) is equal to 1.0. What is the cost performance Index (CPI)? | Multiple Choice | Equal to 1.0 | Equal to 1.2 | Less than 1.0 | Greater than 1.0 |  |  | C |  | 1
You are a project manager who Is In charge of an Important project for your company. When the SPl=0.95 andCPl=l.05. How Is the project performing? | Multiple Choice | The project is ahead of schedule and under budget | The project is behind schedule and within budget | The project is behind schedule and over budget | The project is on schedule and under budget |  |  | B |  | 1
You have submitted the cost baseline to the sponsor. After a review, the sponsor tells you that the amount you have estimated for a certain month is more than the funds the sponsor can disburse you for that month. What do you think the sponsor will advis | Multiple Choice | To remove some of the work scope for that month | To motivate the project team do the work of that month without being fully paid for it | To reschedule the work of that month | To reduce the cost estimates of the activities for that month |  |  | C |  | 1
Mark has been managing an engineering design project for a contracting firm. He uses Three-Point Estimates to calculate costs for each activity. What should he do next if he is planning on developing a budget for the whole project? | Multiple Choice | Develop the Cost Baseline | Perform Earned Value Management | Perform Quality Assurance | Perform Qualitative Risk Analysis |  |  | A |  | 1
A project status report shows that: The earned value (EV) is 30 The schedule performance Index (SPI) is .93. The cost performance Index (CPI) is 1.05. In what area should the project manager implement corrective actions? | Multiple Choice | Project schedule. | Project cost. | Resource management | Communication management. |  |  | A |  | 1
You find some difference or variance between the funds available and the planned expenditures over the duration of the project, with the latter being higher than the former for certain time periods. What must be done first to address this issue? | Multiple Choice | Use a portion of the risk budget to provide this extra funding as there is a risk of not completing the activities for that time period due to lack of funds | Use a portion of the change budget to provide this extra funding as there is a difference between the plan and funds available | Reschedule certain activities if possible so that the rate of expenditures can be levelled to the available funding | Transfer funds from other time periods to the periods where the planned expenditures are higher |  |  | C |  | 1
As part of earned value management (EVM), The budget at completion (BAC) for the project is $10,000, the estimate at completion (EAC) is $ 12,000, and SPI = 1.05. How is the project performing? | Multiple Choice | The project is ahead schedule and over budget | The project is behind schedule and under budget | The project is ahead of schedule and under budget | The project is behind schedule and over budget |  |  | A |  | 1
The project manager is trying to get sign off for a series of marketing materials. The work is rejected by the stakeholders responsible for sign off because of incorrect use of marketing standards. What should the project manager do before sending materi | Multiple Choice | Validate the scope before performing quality control | Create a work breakdown structure before validating the scope | Perform quality control checks before validating the scope | Validate scope before communicating the project status |  |  | C |  | 1
Carlos is the project manager for a mobile application development project. An issue has occurred and one of the team members identifies a workaround, but falls to inform the project manager. After a few weeks, a similar issue appeared again that impa | Multiple Choice | Revising the responsibility assignments matrix (RAM). | Performing a root cause analysis | Escalate the problem to the sponsor | Updating the risk register |  |  | B |  | 1
A project team is staffed with experienced subject matter experts. The project is going well and there are no known quality issues. Team members believe that the quality control process is unnecessary for this project. What should the project manager do? | Multiple Choice | Create a cause and effect diagram to quantify impact | Remove the process from the quality management plan | Review the risk management plan to update risks. | Create a team culture that is committed to quality |  |  | D |  | 1
Your project scheduler has Just started working with your project and has produced defective reports for the past two accounting cycles. You are now checking your company policies before moving to the next step with the corrective actions. What is the | Multiple Choice | Control Scope | Validate Scope | Manage Quality plan | Perform Quality Audit |  |  | D |  | 1
You are a project manager in a software development project. The developers and the quality control team have a poor relationship, so the developers are resisting the tests. The product cannot be delivered until It has been tested and passed by quality | Multiple Choice | Update the quality management plan | Immediately meet with the developers and quality control team to ensure that the quality standards are met. | Outsourcing the quality management activities | Evaluate the impact and inform the customer |  |  | B |  | 1
As a project manager, many of your project team members are new to the project, and while they are working well as a team, you are concerned as to whether they are following the procedures correctly. What tool or technique is likely to help you determ | Multiple Choice | Ishikawa diagrams | Inspection | Quality audit | Histogram |  |  | C |  | 1
You are assigned as a Project Manager to a project in the execution stage. The current schedule and performance indices for the project, SPI and CPI are 1.12 and 1.15, and project performance is well within the baseline. The defects found during internal | Multiple Choice | Improve project schedule and cost control measure so that SPI and CPI reaches above 1.5 | Conduct a meeting with the customer to understand his concern over project progress | Meet with the project team to understand open issues in the project | Start managing project as you gain more insight into day to day responsibilities |  |  | B |  | 1
You are the project manager of a project to solve customer service problems in your company's call center. During the execution phase, several quality defects have been discovered, causing customer concern. You would like to create a chart showing th | Multiple Choice | Ishikawa Diagram | Pareto Chart | Matrix diagrams | Flowchart |  |  | B |  | 1
A customer has already signed off on a given deliverable. During later inspections, the project manager is Informed that the deliverable does not conform to the local government's regulations and that it was built this way due to an informal request fr | Multiple Choice | Project status reports. | Fishbone diagram | Control chart | Matrix diagram |  |  | B |  | 1
During project execution, a high-performing team member leaves. Following this loss, a planned quality audit is conducted that indicates the work product's quality standards are unmet. What should the project manager do next? | Multiple Choice | Create a cause and effect diagram. | Perform a reserve analysis of the work performance. | Consult the resource management plan. | Crash the schedule. |  |  | A |  | 1
A project manager is managing a project with a major deliverable that failed its final acceptance test. The project is now behind schedule and over budget because a replacement must be created. What process should the project manager use to determine | Multiple Choice | Root cause analysis. | Critical path method. | Alternative analysis. | Decomposition |  |  | A |  | 1
Rekha is a project manager on a large construction project. Rekha had originally planned to use both of the company's tower crane simultaneously for a project but has Just learned that one of them will be unavailable. Rekha adjusts the schedule so that | Multiple Choice | Resource leveling | Fast tracking | Reserve analysis | Critical path method |  |  | A |  | 1
You are running one week behind on a project due to late delivery by a vendor. You are forced to compress your project schedule due to a government-mandated end date that constrains your project. After meeting with your team, you found a method to compr | Multiple Choice | Resource leveling. | Crashing | Risk mitigation | Fast Tracking |  |  | D |  | 1
While adjusting the critical path you find that extending the project end date is inevitable due to the short supply of a few people. What else can you do to prevent or reduce this project delay? | Multiple Choice | Crash the critical path | Negotiate revised project end date with the customer | Fast-tracking the project | Add floats to few of the critical path tasks |  |  | C |  | 1
A quality defect on project deliverables. In Which Category are these risks included? | Multiple Choice | External Risk | Management Risk | Technical Risk | Commercial Risk |  |  | C |  | 1
You are the project manager of a large IT project. During the implementation phase, you sign a contract to rent an additional server from a local company because of the possibility that the main server may fall due to constant, local-area electrical outa | Multiple Choice | Avoid | Mitigate | Transfer | Escalate |  |  | B |  | 1
The risk breakdown structure (RBS) helps the project team consider the full range of sources from which individual project risks that may arise. The second Level of RBS includes Regulatory and Legislation. In Which Category are these risks included? | Multiple Choice | Technical Risk | External Risk | Management Risk | Commercial Risk |  |  | B |  | 1
A project manager has received reports from a supplier that he is over capacity, which may delay his delivery. What should the project manager update next? | Multiple Choice | Schedule Baseline | Risk register. | Stakeholder engagement plan. | Issue log. |  |  | B |  | 1
As a project manager, you know the importance of risk management. You always try to include risk management as an agenda item in your status meetings. Some of your project team members complain that discussing risk management issues in status meetings is | Multiple Choice | Escalate to your senior management that some of your team members do not agree with your risk management practices | Call a meeting with your project sponsor and project management team to discuss potential training requirements for your project team members | Agree with your team members and let them know that no more time will be spent on discussing risks in the project status meetings unless required in the future | Talk to your team members about the importance of risk management |  |  | D |  | 1
A project manager notifies the project sponsor that the mitigation strategy for a major risk did not work. The sponsor states that the same risk response was implemented a few months ago on a similar project with the same result. How might this situation | Multiple Choice | The project manager could not have avoided this situation since it is impossible to determine in advance the effectiveness of a risk response | The project manager should have researched the lessons learned register for knowledge gained throughout similar past projects | The project manager should have applied the avoidance risk response strategy because the risk had been seen before in past projects | The project manager should have researched the lessons learned repository for knowledge gained throughout similar past projects |  |  | D |  | 1
An organization has historically executed most projects using a predictive approach. The organization now wants to change over to an agile approach. Due to this change, the project manager is worried about the scope definition process for upcoming proje | Multiple Choice | Ask the general manager to review every requirement to ensure that all projects will deliver the required products. | Meet with the general manager and convince them to return to use the predictive approach to avoid any risk. | Help sponsors and stakeholders craft the product vision and bring the team and product owner together to clarify the expectations. | Ask the sponsor to increase a budget to check if every business needs are included in the requirements. |  |  | C |  | 1
Adam has Just taken over a construction project. Adam planning an information security project for a company that resides in different countries. What is the first step that should Adam take to gather customer requirements? | Multiple Choice | Co-locate with stakeholders to Conduct project planning meetings and enhance communications. | Conduct a stakeholder analysis to identify how regional policies may influence needs. | Perform scope review workshop with the relevant stakeholders | Request relevant stakeholders to conduct an analysis and reach consensus independently. |  |  | B |  | 1
During daily meetings, a team member continues to express issues in completing his task. As a project manager, what should you do? | Multiple Choice | Start a discussion with all team members to help resolve the issue. | Move the team member to another task that is more skill appropriate. | Have a confidential discussion with the team member to identify the root cause. | Wait for the team to identify and solve the problem independently. |  |  | C |  | 1
The main stakeholders asked the project manager to finish the project two months earlier than the scheduled date.As a project manager, what should you do? | Multiple Choice | Update the cost management plan to allocate more resources to the project to finish the scope earlier. | Adding resources and crashing the schedule without changing the project scope. | Hold a stakeholder meeting to align timelines and scope expectations. | Removing activities to shortening the timeline. |  |  | C |  | 1
You are the project manager of a large IT project. Your Agile team wants to develop quality standards for a project.How should you coach the team? | Multiple Choice | Inform the team that user acceptance testing is required to ensure that the product owner accepts the solution. | Insist that test-driven development is implemented along with automated testing. | Determine the tool and techniques suitable for the project and ensure that testing is done early and continuously. | Ensure that the definition of done DOD is provided when the product owner agrees that all acceptance criteria have been met for the user story. |  |  | D |  | 1
An agile project is in its sixth iteration out of 10. Two of the existing team members were replaced. As the project entered the next iteration, the team velocity dropped and the performance started to slip. What should the project manager do? | Multiple Choice | Guide the team to revert back to the forming and storming stages. | Escalate the issue to the human resources. | Escalate the issue to the project sponsor. | Convene a team building event to address key performance indicators KPls |  |  | A |  | 1
During a project's third iteration, a planned activity becomes more complex. The work should be delivered in the shortest time possible. What approach should be used in this situation? | Multiple Choice | The team member brings SMEs to help them. | The team should request support from external team members. | The cross-functional team members work together to complete the activity. | The product owner should remove the complex activities from the product backlog. |  |  | C |  | 1
You are a project manager for a project. One of the subject matter expert (SME) that working in your project Identifies an occurrence and ask you to include it in the lessons learned register. As a project manager, what should you do? | Multiple Choice | Request the SME to wait until the project closure phase | Take ownership of documenting this information | Assign the documenting task to project team members. | Ask the SME to document and capture the occurrence. |  |  | C |  | 1
The programming activities of a project were planned to last 30 days per module, but the programming of the first module has taken 40 days. As a project manager, what should you do? | Multiple Choice | Issue a change request to CCB to change the schedule. | Identify ways to compress the schedule without impacting the baseline. | Check the scope to verify if there is scope creep and get the project on schedule. | Ask the team to work overtime to complete the project on time. |  |  | C |  | 1
The marketing team is transferring to using hybrid approaches for their projects. The marketing director is not knowledgeable about hybrid methodologies. And the project manager needs the director's support as the marketing director is a key stakeholder. | Multiple Choice | mentor the marketing director on hybrid approaches. | Ask the marketing team members to coach the director. | Train the marketing team and keep the director informed. | Ask the marketing director to participate in daily meetings. |  |  | A |  | 1
you are a project manager working on a critical project. Some stakeholders have complaints about some of the team member's performance. You want to understand the situation and provide feedback to the team as soon as possible. What three actions should y | Multiple Response | Conduct an annual review. | Define team ground rules. | Perform a retrospective session. | Request a manager performance review. | Perform a daily team meeting. |  | BCE |  | 1
An organization wants to transfer from a predictive to an agile approach. What strategy will help the organization with this change? | Multiple Choice | Create a task force of executives who will monitor agile projects on a daily basis. | Improve organizational readiness by addressing impediments and agile in the organization. | Take a big bang approach of moving the whole organization to agile at once. | Assign multiple managers who will be accountable for the agile approach. |  |  | B |  | 1
An opportunity is outside the scope of the project is discovered by the project team. The project manager decided to update the risk register and escalate the opportunity to a higher level. What should the project manager do next with this opportunity? | Multiple Choice | Share this opportunity with another project. | Establish a contingency reserve to handel this opportunity. | No more action is required. | Further monitoring the opportunity |  |  | C |  | 1
During the execution of a project, big changes in enterprise environmental factors EEFs will severely reduce the Implementation cost and reduce the project schedule. As a project manager, what should you do? | Multiple Choice | Follow the communications management plan and project escalation policy. | Give the team extra time to finish activities within the planned schedule. | Decide how the remaining budget will be spent. | Keep the extra budget as management reserve until project close out. |  |  | A |  | 1
An agile project is running activities to define the minimum viable product MVP. During the session, the project manager identifies some mandatory regulations, but there is no consensus to include these regulations in the MVP because if may extend the du | Multiple Choice | Ask the project sponsor to add more time to the project. | Share with the participants the need to focus only on product functionality. | Get commitment from the team to include all of the required regulations. | Train the team on the new regulations as requested by management. |  |  | C |  | 1
A permanent highly skilled staff hired for the project to avoid potential budget overruns. However, there is a risk of staff turnover during the course of the project, which may have an impact on the delivery. Which two actions should the project manager | Multiple Response | Dividing the project into smaller projects. | Introduce a recognition program to motivate and reward resource performance. | Ask the sponsor to hire third-party staff. | Enhance the competencies of the project team through training, mentoring, and coaching. | Increase the trained staff to create back up for resources. |  | BE |  | 1
During project scope management, the project manager noticed that some requirements seem to be different from the ones specified within the project charter. What should the project manager do? | Multiple Choice | Modify the baseline of the project for minor impact changes to the project scope | Send the change to the change control board for approval. | Use a focus group and brainstorming sessions to gather more details about the project scope. | Explain to the customer that these requests could Impact the schedule and cost of the project. |  |  | C |  | 1
A project manager suggests implementing a new system using a mix of scrum and Kanban methodologies. The product owner is confused as to how to start delivering the functionalities required. How should the project manager assist the product owner? | Multiple Choice | Coach the product owner on how to create a product backlog. | Explain the deliverables to the product owner. | Discuss the product owner's responsibilities within the project team. | Coach the team to decompose the project task. |  |  | A |  | 1
A project manager is managing a project with a newly formed project team. An experienced team member is complaining about the complexity of the tasks and is not happy with the project team. What should the project manager do? | Multiple Choice | Actively listen to the team member and identify ways to support their needs in completing the task. | Update the risk register with potential schedule delays. | Ask the team member to find a solution to overcome the challenges as the tasks are unavoidable. | Set up team building activities with the project team members to reduce tension. |  |  | A |  | 1
Which of the following are part of an effective team charter? (Choose two) | Multiple Response | Project objectives | Shared values | Resource assignments | Conflict resolution |  |  | BD |  | 1
What are some objectives of running a Retrospective? (Choose two) | Multiple Response | Plan ways to increase quality and effectiveness. | Lessons learned and opportunities for improvement | Provide the stakeholders access to the team. | Get feedback on the product. |  |  | AB |  | 1
You and the project team draft a project scope statement. Which of the following is commonly part of the project scope statement? (Choose two) | Multiple Response | Scope description | Scope creep | Acceptance criteria | Budget | Schedule |  | AC |  | 1
As the project team decomposes the work in the WBS, they begin to populate the product backlog. When must the team have the product backlog finished? | Multiple Choice | By the first iteration. | By the first phase of the project. | The product backlog is a living artifact that is finished at the end of the product. | By the time the business signs off on the project scope statement. |  |  | C |  | 1
You are working on a project that is part of a program. All the projects within this program are being managed in an agile way. What is a good technique to get the project teams aligned? | Multiple Choice | Assign one customer point of contact for all projects. | Develop one project management plan. | Conduct a Scrum of Scrums. | Hold one daily standup meeting for all the projects. |  |  | C |  | 1
A project manager is approached by the sponsor who requests to provide an estimate as to how long will it take for the agile development team to complete the project. How should the project manager respond? | Multiple Choice | The project duration will be determined by adding the total number of story points completed by the development team members in each iteration. | The velocity of the project team will be calculated prior to the start of the first iteration and then multiplied by the number of iterations in the project. | Project duration will be determined using bottom-up estimating by adding up the duration of the tasks comprising the user stories in the product backlog. | Once the velocity is established, the total amount of story points divided by the velocity of the project team will determine the project duration. |  |  | D |  | 1
If an Agile project's Earned Value is $100,000 and the CPI is 0.8, how much the team has spent so far on the project? | Multiple Choice | 130000$ | 100000$ | 125000$ | 70000$ |  |  | C |  | 1
You have Just been assigned as the project manager for a project in your company to deploy a new system. The stakeholders disagree on the project objectives and approach. As a project manager, what should you do? | Multiple Choice | Conduct a general meeting with all stakeholders and review and address a list of activities for each of them. | Create a roles and responsibilities matrix based on the project charter and ask the sponsor to share it with all stakeholders to provide credible authority. | Conduct scoping workshops with the project team to create a work breakdown structure WBS, assign tasks to various entities, share this with all stakeholders and ask the team to complete their tasks as scheduled. | Breakdown the situation to identify the root causes for the disagreement and then work with each stakeholder and participating entity in their exact roles and responsibilities |  |  | D |  | 1
The project sponsor on an agile project informed the project lead that an executive would like an update on the project's progress. What should the project lead do? | Multiple Choice | Reach out to the project management office PMO for status report templates and provide project updates in that format. | Ask the project sponsor or product owner to provide an update since the project lead should be trying to keep the team free from impediments. | Invite the executive to the project's meeting space to determine if the project information radiators meet their needs. | Provide a link to the project's shared drive for the executive to search through for any artifacts that are of interest. |  |  | C |  | 1
You are working on a project as a project manager. You wantto estimate the cost of a new project that is similar to a projectthat was implemented last year. You meet with a group of expertsfrom the previous project. The group uses a three-pointestimating | Multiple Choice | Use soft skills to convince the project sponsor to approve the new budget estimate. | Review the historical information and lessons learned from last year's project to justify the new budget estimate. | Review the organizational process Assessment to determine if a contingency reserve was considered in the budget estimate. | Change the budgeting technique to a more accurate bottom-up cost estimation. |  |  | B |  | 1
You are a project manager of a company and your project is currently in the execution phase. You notice that the work performance reports have deteriorated drastically in less than two weeks. The project team in country A is complaining about delays resul | Multiple Choice | Implement fast-tracking to compress the schedule and improve SPI. | Implement crashing to compress the schedule and improve the schedule performance index SPI. | Perform conflict management using the project's resource management plan. | Review the risk management plan to evaluate the probability and impact of these delays. |  |  | C |  | 1
A project manager who is managing a critical project in a multinational company is conducting a progress meeting with all team members. During the meeting, one of the team members states that they are facing a critical problem that will prevent the team f | Multiple Choice | Ask the team member to follow the approval communications management plan to communicate their issue | Ask the team member to raise a change request to assess the issue in detail. | Schedule a meeting with the concerned team member to review and update the issue log. | Review the risk register with the team member to find the proper response action for this issue. |  |  | C |  | 1
The project manager Just started leading a project team from which the previous project manager resigned. After a quick evaluation of this project, it is apparent that team morale is low due to continuous disagreement about how to complete tasks. Tasks ar | Multiple Choice | Issue a change request to extend the project schedule based on identified delays. | Inform the stakeholders that the project will be delayed due to previous team management. | Crash the project timeline to ensure the project is back on schedule. | Conduct a meeting with the project team to discuss end address the sources of disagreement. |  |  | D |  | 1
A project manager is assigned to a project in a company that is transitioning to agile. Not all stakeholders believe in the project, and some stakeholders would like the entire project defined and planned out early in the project. However, the project spo | Multiple Choice | A hybrid project as this will mitigate stakeholders' concerns. | A predictive approach as this would please the senior stakeholder. | An agile approach as this would provide working functionality earlier. | A predictive approach as this will show benefits for all stakeholders. |  |  | A |  | 1
Due to delays on some activities one of the project teammembers has increased the scope without any approval.What should the project manager do next? | Multiple Choice | Update project documentation with the new scope | Evaluate the impacts of the changes that were made to the project | Add team members to the project to avoid more schedule delays | Remove the changes to match the original requirements. |  |  | B |  | 1
A project manager is assigned to a new project todeliver a product at the end of the year. The project managerwas informed by the vendor that a core component could notbe shipped on time, which will impact the schedule. Whatshould project manager to do ne | Multiple Choice | Add an item to the next status review to make stakeholders aware of the vendor issue | Review and update the issue log and determine If any alternative components can be offered | Replace the vendor with a new vendor who can offer the component on time | Schedule a meeting with all stakeholders to extend the project deadline |  |  | B |  | 1
A new team member has Joined an agile project, replacing a team member who recently left, The project team needs the new team member to speed up their ability to contribute affectively to the project, What should the project manager do to help in this | Multiple Choice | Schedule knowledge transfer sessions and assign less complex tasks to the new team member | Have the new team member complete all of the company's mandatory training | Send technical documentation to the new team member and schedule training for the next iteration | Assign the new team member the same tasks that were assigned to the previous team member who they replaced |  |  | A |  | 1
An agile team is brainstorming and prioritizing all of the risks according to severity. What should the team do about the identified risks? | Multiple Choice | Agree that any issue can be handled when it becomes a problem | Mitigate the risks that are applicable to the current and following iterations | Acknowledge that the risks will be handled in the corresponding iteration | Focus on the project deliverables rather than the documented risks |  |  | B |  | 1
A customer is concerned with the quality of the product delivery, as the production deployment is approaching. What should the project manager do next to ensure acceptance of the deliverables? | Multiple Choice | Verify the production budget before advancing the product | Review the approved exit criteria for the product | Evaluate the quality checklist for product compliance. | Test product integration in accordance with the requirements |  |  | C |  | 1
In the middle of an iteration, an agile team working on the development of a new product was notified that an important team member will leave the project for a few weeks due to some urgent personal issues. What should the project manager do regarding th | Multiple Choice | Allow senior management to decide how to proceed with the project | Convince the team member not to leave until the project is completed. | Reach out to the procurement team to hire a substitute for the team member | Reach an agreement with the team on how to handle the situation. |  |  | D |  | 1
A new project manager was assigned to a project during implementation. The project manager realized that new tax policies are creating a risk for a cost overrun by 25%. The project manager updated the risk register and kept the project running as norma | Multiple Choice | Ensured the risk tolerance of the company was properly updated. | Implemented the stakeholder engagement plan correctly | Implemented the communications management plan properly. | Provided a proper risk response. |  |  | C |  | 1
Some members of a project team are frustrated by a new team member who previously worked in a scrum setting. This new team member approaches members of the project team on a dally basis in what appears to be an attempt to engage in individual stand-up mee | Multiple Choice | Schedule a meeting for the project team to review the communications management plan. | Send an email to the project team outlining the communication strategy. | Direct the new team member on the methodology the project team is using. | Direct the project team to continue the discussion with the new team member. |  |  | A |  | 1
A company routinely outsources resources for specific core activities. Due to a sudden, unforeseen risk, all of the team members are needed to work remotely, including the outsourced ones. How can the project manager address this challenge to assure | Multiple Choice | Develop a new strategy for communication and management of resources. | Review the coordination and communication costs with the supplier. | Review the risk management plan for the mitigation activities. | Submit a change request to increase the contingency budget. |  |  | C |  | 1
A mandatory compliance requirement that will impact the project software is introduced during the execution phase of an iterative project. The team is aware of the compliance requirement. What should the project manager do next? | Multiple Choice | Update the product backlog item with this new requirement. | Update the stakeholder register to include the requirement owner. | Escalate the issue of project impact to the project sponsor | Escalate the issue of project impact to the product owner. |  |  | D |  | 1
A project manager is leading a technically complex project. The project is part of a strategic program of work and the first to use an agile approach. One of the board members is interested in attending a meeting to see how the delivery of the project s | Multiple Choice | Invite the board member to the next sprint retrospective. | Invite the board member to the next daily standup. | Invite the board member to a separate demo. | Invite the board member to the next sprint review. |  |  | D |  | 1
An experienced project manager is leading an enthusiastic team but realizes the team lacks the experience to complete the job successfully. What should the project manager do to reduce the risk of project failure? | Multiple Choice | Provide team members with the necessary coaching and mentoring. | Assign a dedicated resource to check the quality of each deliverable. | Ask the sponsor to add experienced professionals to the team. | Approve the appropriate training program for team members. |  |  | A |  | 1
A multicultural team is working on a project. After a few months of observation, the project manager realizes that two team members are not responding to the construction manager properly. The project manager spoke to the team members individually and | Multiple Choice | Provide the construction manager with instructions on how to resolve the situation. | Ask the team members to tolerate the cultural differences as they have a different cultural background. | Discuss the team members' concern with the construction manager and seek solutions. | Ask the construction manager to meet with the two team members to resolve the situation. |  |  | C |  | 1
A customer reviewed the plan for a project with high uncertainty. The customer expressed concerned about the work requiring SO many iterations with a risk of not reaching the mandatory delivery date. Which approach should the project manager use in this | Multiple Choice | Kanban approach | Hybrid approach | Agile approach | Predictive approach |  |  | B |  | 1
A project team member just informed the project manager that the license for the software that the team uses to perform calculations has just expired. As a result, the team cannot continue with their project tasks. What should the project manager do fi | Multiple Choice | Ask the team members to find an alternative way to perform calculations | Ask the team to fast-track the project and perform tasks that do not require calculations | Issue a formal complaint to the project sponsor claiming a lack of proper tools. | Meet with the IT team to evaluate how fast the software license can be renewed. |  |  | D |  | 1
A project manager manages a bridge construction project. The project manager has received a major change request from a regulatory stakeholder to add one branch of the bridge to the engineering design. The project manager prepared a change request, which | Multiple Choice | Evaluate the adjustments to the project management plan. | Include the new branch of the bridge in the design. | Notify the project team about the change request's approval. | Communicate the decision to the stakeholder who requested the change. |  |  | A |  | 1
A team has developed and tested new software to control airplanes during flights. There are several regulatory requirements that must be met. What should the project manager do to meet these requirements? | Multiple Choice | Measure the extent to which the project complies with the regulations. | Ask human resources (HR) to assign a compliance specialist to the team. | Determine potential threats regarding compliance with the regulations. | Validate that the software is compliant with standards and regulations. |  |  | C |  | 1
A global petroleum crisis has affected the distribution of crude oil in the region where the construction project is underway. Materials are not being delivered on time and this phase of construction is already behind for what was initially planned. Wh | Multiple Choice | Propose a pause in this phase to save labor costs and asset depreciation. | Proceed with the project using management reserves to cover any delays or losses. | Establish new partnerships with other suppliers in anticipation of any delays. | Perform a risk assessment and define a risk response action plan. |  |  | D |  | 1
A project manager has noticed that the performance of a new team member has increased dramatically over the past few months. The project manager has been measuring this team member's performance through the cost performance index (CPI) and schedule per | Multiple Choice | Send a communication to management recognizing the team member's contributions | Attach a note to the project management plan about the team member | Record the team member's contribution in the responsibility assignment matrix (RAM) | Hold a project team meeting about the team member's contribution and take minutes |  |  | D |  | 1