## Exam Data
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
A software vendor has recently hired you to manage some of its key projects. During your orientation at the organization, you were told that the organization has recently adopted Agile practices for project management. A chart was then shown to you where Agile and Kanban were shown as a subset of Lean. What is your view on this? | Multiple Choice | Agile and Kanban are subsets of Lean because they are named instances of Lean thinking. | The chart is wrong because Agile is a subset of Lean while Kanban is not. | The chart is wrong because Agile, Kanban and Lean are three different approaches to project management. | The chart is wrong because Kanban is a subset of Lean while Agile is not. |  |  | A |  | 1
The PMO has been following a waterfall-based project management approach consistently across all projects. You a project manager, want to pilot Agile approaches on a couple of new projects and see how these approaches can benefit the organization. However, the team members are not experienced in the use of Agile approaches. What should you do first? | Multiple Choice | Train the team members in effectively using the Kanban approach. | Train the team members in effectively using the Scrum methodology. | Train the team members in the fundamentals of the Agile Mindset and principles. | Train the team members in effectively using the XP approach. |  |  | C |  | 1
You have been assigned a new project. The project Involves disruptive technologies. The project scope Is not clear which has introduced a lot of risk into the project. You have requested to use Agile to manage this project. Why? | Multiple Choice | Agile techniques and approaches effectively manage scope changes. | Agile techniques and approaches effectively manage project risk. | Agile techniques and approaches effectively manage disruptive technologies. | Agile techniques and approaches effectively manage disruptive technologies, scope changes, and project risk. |  |  | D |  | 1
When Introducing Agile methods to an organization that has historically managed all Its project using predictive life cycles, which of the following approaches is more likely to succeed? | Multiple Choice | Trying the new techniques on ongoing projects. | Trying the new techniques on completed projects. | Trying the new techniques on a less risky pilot project. | Trying the new techniques on high-value projects. |  |  | C |  | 1
A project team is currently building a warehouse management system. Due to the complexity of the project and ambiguous requirements, the team decided to adopt an Agile management approach. If a higher rate of management process improvement is required by the project team, which of the following can help achieve this objective? | Multiple Choice | Deferring the development until all requirements have been collected. | Adopting XP for the development phase. | Frequent retrospectives and selecting improvements. | Using a Kanban board to enable visual management. |  |  | C |  | 1
Your organization has been awarded a contract todevelop and implement a new resource managementsystem for a client based in Asia. Your development teamis distributed across Europe. You are also planned torelocate the implementation team to the client location.What would be your biggest challenge in such a setup? | Multiple Choice | Monitoring project progress. | Efficient and effective communication. | Controlling project costs. | Documenting sprint retrospectives |  |  | B |  | 1
You and your team are executing the first Agile project in the organization. This is a special project for the organization as Agile is being piloted for the first time. You are nearing the end of the first iteration on the project and not all of the assigned user stories are complete. Can the team extend the iteration duration by a couple of days in order to complete all assigned stories in the iteration plan? | Multiple Choice | Yes; but requires the approval of the Scrum Master. | Yes; but requires the approval of the product owner. | No; the iterations are time-boxed. | Yes; but the extension cannot be more than 2 days. |  |  | C |  | 1
You are leading a massive knowledge work project. Some team members have complained they have to work overtime in order to complete some of the assigned work. What should you do to resolve this issue? | Multiple Choice | Launch a root cause analysis | Establish a Kanban board and set WIP limits | Call a team for a retrospective meeting | Establish working agreements |  |  | B |  | 1
The product owner has requested some major changes that will have a significant impact on the project and require reprioritizing the remaining backlog items. What should you do? | Multiple Choice | Terminate the current sprint and reprioritize the entire project. | Cancel the current sprint and immediately call a retrospective. | Complete the current iteration, reprioritize the backlog and adapt the new plan for the next iteration. | Complete the started stories but do not bring any more "Ready" stories into "WIP". |  |  | C |  | 1
You are helping a software development team transition from traditional to Agile approaches. You tell the team that the single most important attribute of any product or feature is: | Multiple Choice | The velocity at which the team takes on the development of that product or feature. | The time required to deliver the product or feature. | The value customers associate with that product or feature. | The ideal days estimated to develop the minimum viable product or feature. |  |  | C |  | 1
Project life cycles can be shown on a continuum ranging from predictive cycles on one end, to Agile cycles on the other end, with more iterative or incremental cycles in the middle. Another approach is to visualize the continuum with a two-dimensional chart with the frequency of delivery on the Y-axis and degree of change on the X-axis. What project life cycle should be proposed for the quadrant with a high degree of change and high frequency of delivery? | Multiple Choice | Incremental | Agile | Iterative | Predictive |  |  | B |  | 1
You are currently managing a complex project that requires a lot of knowledge work. You want some sort of visual management system that can help you visualize the flow of work, make impediments easily visible, and allow flow to be managed by adjusting the work-in-process limits. Which of the following tools can help you in this regard? | Multiple Choice | Sprint retrospective | Sprint Review meeting | Product backlog | Kanban board |  |  | D |  | 1
You have been invited by your colleague to attend oneof the project standup meetings. You notice that the team has got a big chart on a wall, divided into sections suchas "Ready", “in Development", "Being Tested", and "Completed". What tool are they using? | Multiple Choice | Burndown chart | Burnup chart | Kanban board | War room |  |  | C |  | 1
A project team has recently adopted Agile approaches to project management. However, the team is still not proficient in these methods as It has only recently adopted these approaches. Which of the following questions should the team address to ensure it has successfully adopted an Agile Mindset? | Multiple Choice | How to handle confidential information during the project? | How can the team deliver quickly and obtain early feedback to benefit the next delivery cycle? | How to ensure all contractual obligations are fulfilled? | How can project management processes be tailored to suit each project? |  |  | B |  | 1
Creating a recognition plan with established times for rewards ensures that recognition takes place and is not forgotten. This is usually part of the: | Multiple Choice | HR Company Management plan | Stakeholder engagement plan | Resource Management Plan | Communications Management Plan |  |  | C |  | 1
You are managing the design and development of an HR system. Your project calls for communication in the form of announcements and messages with an extremely large audience. What communication method would be appropriate under such circumstances? | Multiple Choice | Push communication | Pull communication | Interactive communication | Verbal communication |  |  | B |  | 1
When a project manager assumes the roleof a coach and a facilitator for the project team,in an Agile environment, this role is known as: | Multiple Choice | Project sponsor | Product owner | Servant-leader | Functional manager |  |  | C |  | 1
While developing your project schedule, you have asked everyone to provide a list of planned vacations over the next three months, and you have applied this information to the tasks that each person is responsible for. What also needs updating? | Multiple Choice | Lags | Leads | Gantt chart | Resource Calendars |  |  | D |  | 1
Which of the following are the core values of XP? | Multiple Choice | Collaboration, complexity, communication, faith, and discipline. | Communication, simplicity, feedback, courage, and respect. | Planning, executing, monitoring, and controlling. | Unity, faith, agility, and discipline |  |  | B |  | 1
A client approaches a design team member requesting that a current task be stopped and a new concept be developed. This will significantly change the design, and impact the project budget and schedule. The team member asks the project manager for the next course of action. What should the project manager do? | Multiple Choice | Accept the request and make the changes. | Ask the client to refrain from directly contacting team members. | Refer to the perform integrated change control process. | Hold a team meeting to discuss the request. |  |  | C |  | 1
Some of your team members seem to be not cooperating with each other. There is a lack of mutual support and they are coming to you for decision making on small issues. What can you do to make this better? | Multiple Choice | Check whether there are any issues due to diverse cultures | Initiate team building to increase trust among team members | Involve them in project management work to increase their motivation | Involve them in your decision making activities |  |  | B |  | 1
Some of your organization's department who are collaborating together for a project have found a great way to include a few subject matter experts in their project even though those experts will work from another geography. You are appointed as the project manager while this project is in the executing phase. You notice some conflicts in the project team due to this arrangement of people working from remote locations. What will you do first to improve the situation? | Multiple Choice | Exchange the locations of the other geography resources with the local resources | Hold frequent meetings with the other geography resources | Improve the communications plan for the project | Bring the other geography resources to the local office for a day every month to meet the local members face to face |  |  | C |  | 1
You administer surveys, interviews, assessments and focus groups within your project team and create a team performance assessment with observations on their skills, competencies, turnover rate and cohesiveness. You then evaluate the team's overall performance. How will you use this report now? | Multiple Choice | Estimate the cost of improving the team's performance | Make changes to the team members who are performing poorly | Identify specific training, coaching, mentoring or other changes required to improve the team's performance | Estimate the revised project schedule based on the team's performance |  |  | C |  | 1
The project team members are in conflict are not collaborative and differ in opinion on the architecture. Which of the following phases of Team Development are they in now? | Multiple Choice | Norming | Forming | Performing | Storming |  |  | D |  | 1
During the execution of a project, the project manager discovers that one branch team's tasks are being ineffectively influenced by one team member. What should a project manager use to ensure good working relationships among team members? | Multiple Choice | Interpersonal skills. | Team-building activities. | Recognition and rewards. | Ground rules. |  |  | B |  | 1
You are a project manager of a company, and your project is currently in the execution phase. One of your project teams leave the site early at 3:00 pm Friday and mistreats his colleagues. You would like to establish clear expectations regarding the acceptable behavior of the team member. To avoid such situations, you should create: | Multiple Choice | Management skills | Team-building activities | The team charter | Interpersonal skills |  |  | C |  | 1
A lead business analyst on a large project has consistently been working late to finalize requirements for the next sprint.In the weekly team lead meeting. The project manager learns there are several business analysts on the team who have free cycles. What should the project manager do to ensure an even workload? | Multiple Choice | Facilitate a discussion within the team to redistribute the work within the project team. | Review the list of open requirements and reassign them to team members with free cycles. | Delay the start date of the next sprint to allow more time for gathering requirements. | Direct the business analysts with free cycles to take more ownership of the project. |  |  | A |  | 1
You are managing a software upgrade project for your company. One of the key stakeholders has a great deal of authority regarding project decisions, but resistant to any changes that may occur as a result of the work or outcomes of the project. To complete the project successfully, you need his continuous support. What stakeholder management strategy should you use with the key stakeholder? | Multiple Choice | Keep the key stakeholder satisfied | Manage the key stakeholder closely | Monitor the key stakeholder actions | Keep the key stakeholder informed |  |  | B |  | 1
A project is six months into its nine-month projected duration, and the project manager is reporting that the project is at least three months behind schedule because certain key stakeholders were resistant to any changes that might occur as outcomes of the project. What might have been done differently during project planning to have avoided this situation? | Multiple Choice | Better execution of the Manage Stakeholder Engagement process | Establishment of a more robust communications management plan | Development of a stakeholder engagement assessment matrix | Creation of a comprehensive stakeholder register |  |  | C |  | 1
The government sponsors a project to construct a new highway. The assigned project manager communicates to stakeholders that the project charter was approved. The project manager is working on the project management plan and receives an email from an environmental organization asking for the objectives and start date of the project. What should the project manager do to address the situation? | Multiple Choice | Respond to the email with the requested information. | Conduct a stakeholder analysis and communicate to stakeholders accordingly. | Conduct a brainstorming session with the stakeholders and the team. | Update the communication management plan accordingly. |  |  | B |  | 1
A project manager focuses on systems and structure to accomplish project goals. As a result, the project manager has a strained relationship with the project team. Although the current project is trending to meet project objectives, excessive turnover of the project team threatens the project. For self-Improvement, what type of skills should the project manager spend time developing? | Multiple Choice | Management skills | Leadership skills | Operational and problem-solving skills | Communication skills |  |  | B |  | 1
You are leading a software development project, which requires knowledge of several programming languages. During project execution, one of the developers has been pulled out of the project by her functional manager. The manager provided you with another developer instead. What should you do first? | Multiple Choice | Schedule training for the new developer | Provide the new developer with an ability test | Assign the developer the next user story in the backlog | Introduce the new developer to the project sponsor |  |  | B |  | 1
You have been assigned to lead an agile project. You want to ensure that project information is shared within and across the organization, so that any misalignments, dependencies, or other issues related to the frequently changing requirements are surfaced as quickly as possible. How could this goal be best achieved? | Multiple Choice | By sharing comprehensive documentation | By distributing the project report weekly | By inviting stakeholders to daily standups | By promoting aggressive transparency |  |  | D |  | 1
A scrum master is leading an agile project in which the development team has failed to achieve the sprint goal for the past three iterations. During the sprint retrospective, the team decides to implement several changes to improve velocity. How might the scrum master verify any performance Improvement? | Multiple Choice | Review the burnup chart | Study the Gantt chart | Calculate the project's TCPI | Create Pareto chart |  |  | A |  | 1
The project manager and project team have worked together for many years. There is a deep sense of community and collaboration. Everyone knows their stuff and gets better with every project. Which leadership style of the project manager is most effective in deepening those connections? | Multiple Choice | Charismatic leadership | Communications leadership | Transformational leadership | Servant leadership |  |  | D |  | 1
Your organization's PMO is periodically asking for project artifacts from all projects and checking whether corporate standards of project management are being adhered to or not. They are also supportive in providing templates and guidelines related to project management when asked. Which type of PMO are we referring to here? | Multiple Choice | Supporting PMO | Controlling PMO | Directing PMO | Governing PMO |  |  | B |  | 1
The Project Manager to build a concrete waterfall at a theme park likes to plan everything upfront and follow the waterfall method. However, the customer doesn't want everything fixed from the beginning, as she may change her mind in a number of areas once the project is underway, and needs to be sure that the Project Manager can allow for flow-on effects. What sort of project life cycle should the Project Manager use? | Multiple Choice | Predictive | Adaptive | Explicit | Tacit |  |  | B |  | 1
You have recently Joined an organization as the Marketing Manager. You have been told that a new product has Just been created and you will need to get it into the market within the next month. This means press released, TV, Radio, internet and newspaper adverts, a big launch, with at least one local celebrity. You request a meeting with a project manager for advice on initiating the project, but you are told the organization doesn't have a Project Manager, it Just has a part-time Project Coordinator. What is the organizational structure of the organization? | Multiple Choice | Project-oriented | PMO | Balanced matrix | Strong matrix |  |  | C |  | 1
A project manager has Just taken over a project to develop a product using a hybrid life cycle. With this project, the hardware has fixed requirements while the software requirements are still evolving. How should the project manager apply the hybrid life cycle for this project? | Multiple Choice | Develop the software with a predictive life cycle and use an adaptive life cycle for the hardware | Develop the hardware with a predictive life cycle and use an adaptive life cycle for the software | Both the hardware and software should have their scope defined during initial project planning | Both the hardware and software should have their scope defined iteratively |  |  | B |  | 1
In your project, a supplier delivers equipment that falls to meet customer requirements. after the investigation, you determined that the supplier misunderstood the requirements and make incorrect assumptions without clarifying them with the customer. As a project manager, what type of communication methods should you have used to avoid this? | Multiple Choice | Pull communication | Manual communication | Push communication | Interactive communication |  |  | D |  | 1
Which of the following practices will best support the transfer of knowledge to benefit future projects? (Choose three) (Choose three) | Multiple Response | Ensure that the lessons learned register is listed as a configuration element in the configuration management plan | Conduct regular retrospective meetings with the project team and relevant stakeholders | Document knowledge gained in the lessons learned register throughout the project | Regularly review the knowledge management plan as an element of the project management plan | Ensure that the lessons learned register is finalized and transferred to the lessons learned repository |  | BCE |  | 1
In one of the meetings, the project sponsor shouted at the project manager that why did he send the critical reports to the HR manager. What could have been done to prevent this situation? | Multiple Choice | Review project communications | Review organizational process assets | Review communication management plan | Review stakeholder engagement plan |  |  | C |  | 1
During a new product development project, the project manager identifies that the requirements are conceptual and that it is difficult to obtain a shared understanding by all stakeholders. What can the project manager do to obtain a shared understanding of the project's requirements? | Multiple Choice | Benchmark with the other organizations. | Build a prototype. | Hold brainstorming sessions with the stakeholders. | Conduct a requirements walkthrough. |  |  | B |  | 1
There are a variety of stakeholders on your project representing several different functional areas. While collecting requirements from all of them, you want to define the cross-functional requirements and reconcile stakeholder differences. Which requirement collection techniques is best used to achieve this goal? | Multiple Choice | Focus Groups | Interviews | Facilitation | Brainstorming |  |  | C |  | 1
As a Project Manager, you are estimating the duration of your project activities using a triangular distribution formula. For a particular project activity, your Optimistic estimate is 14 days, the Pessimistic estimate is 49 days, and the Most Likely estimate is 27 days. What should be the expected duration of this activity? | Multiple Choice | 32 | 50 | 30 | 25 |  |  | C |  | 1
A software development project has been awarded to one of the many vendors. Your company and the vendor have agreed to build this project using the Waterfall Methodology. You decide to check with the progress regarding when development will start. The vendor informs you that the actual development can only start after the completion of the design. Which type of relationship best describes the dependency between design and actual development? | Multiple Choice | Finish-to-Finish | Start-to-Start | Start-to-Finish | Finish-to-Start |  |  | D |  | 1
A project's primary focus is staying on schedule. To monitor this, the project manager requests monthly progress reports from the contractor. What should the project manager ask the contractor to include in these reports? | Multiple Choice | Schedule attributes. | Work breakdown structure (WBS) | Gantt chart. | Network chart. |  |  | C |  | 1
Using the following values, calculate the Management reserve: Project Budget = 100,000 EAC = 120,000 AC = 5,500BAC = 70,000 | Multiple Choice | 100,000 | 70,000 | 30,000 | 40,000 |  |  | C |  | 1
Your project is in the planning phase. The project team commences estimating the cost by using a work breakdown structure. What Is the tool the project team uses? | Multiple Choice | Three-point estimating | Parametric estimating | Bottom-up estimating | Analogous estimating |  |  | C |  | 1
You are a project manager for an infrastructure project. Your project team members report monthly on their assigned activities. What should you do to maintain a healthy cash flow? | Multiple Choice | Provide project reports | Team building Activities | Apply earned value (EV) principles. | Perform a qualitative analysis |  |  | C |  | 1
To create a quality product, the project management team invested in training the project team members and purchasing high-end equipment. Such costs are: | Multiple Choice | Appraisal costs | Prevention costs | Costs of Nonconformance | Internal Failure costs |  |  | B |  | 1
Which of the following is an example of an external failure cost? | Multiple Choice | Cost of documentation | Cost of training | Cost of testing | Warranty cost |  |  | D |  | 1
Tim has been running a project. While performing a quality audit he found that the team members have committed a number of minor mistakes while producing the product of the project. He is concerned about whether or not the project processes are under control. Which of the following tools should he use to clear his doubts? | Multiple Choice | Bar Chart | Control Chart | Histogram | Ishikawa Diagram |  |  | B |  | 1
You are a project manager in a manufacturing company. You want to analyze the output of a production line that manufactures piston rings. You want to determine whether the variations in the Jobs are inherent to the process or if the process is in need of adjustment. Which of the following tools would be most useful? | Multiple Choice | Pareto charts | Control charts | Statistical sampling | Trend analysis |  |  | B |  | 1
A quality assurance subject matter expert SME discovered that the formulation team didn't follow compliance procedures while manufacturing a drug. What should the project manager have done to prevent this issue? | Multiple Choice | Reviewed the quality baseline document. | Reviewed the quality management plan. | Reviewed the quality improvement method. | Reviewed the quality metrics document. |  |  | B |  | 1
A project team is analyzing a major, critical defect to determine the root cause. In order to do this, the team considered various factors linked to the defect and grouped them Into categories such as Machine, Method, Material, and Manpower. Which of the following tools of quality is the team using? | Multiple Choice | Cause-and-effect diagram | Flowchart | Control chart | Histogram |  |  | A |  | 1
You are monitoring the status of a project to update the project progress and manage changes to the schedule baseline. You have some resources assigned to more than one activity simultaneously, making them overallocated during those days. You want to reduce this overallocation and keep resource usage at a constant level. What technique should you use to achieve this goal? | Multiple Choice | Resource Leveling | Resource Allocation | Schedule Compression | Resource Compression |  |  | A |  | 1
The project manager works in risk management and creating a risk register. The risk register records details of all the risks Identified at the beginning and during the life of the project. What tool or technique should the project manager use to generate a list of all possible project risks? | Multiple Choice | Brainstorming | Probability and impact matrix | Monte Carlo | Tornado diagram |  |  | A |  | 1
You are managing a construction project. After identifying risks, you start the qualitative risk analysis process and now you are going to prioritize them.Which of the following techniques are you going to use? | Multiple Choice | Tornado diagram. | Sensitive analysis. | Probability and impact matrix. | Scatter diagram. |  |  | C |  | 1
You have just replaced a project manager who was managing a city street tight installation project. The project is in its execution phase. The new project manager has issues with some undiscovered risks on previous projects. What document should the new project manager reference to ensure that all possible risks are involved in risk identification? | Multiple Choice | Stakeholder register | Probability and impact matrix | Project charter | Risk register |  |  | D |  | 1
You know that the success of your project will be determined by how well you manage risks. You know that identifying risks upfront can help you be better prepared with risk response strategies. You discuss and consult with other project managers in the company. One manager suggests the usage of SWOT to identify risks. What would you do next as a part of this technique? | Multiple Choice | Identify the Organization's strengths and weaknesses | Gather anonymous responses from experts and identify risks | Perform root cause analysis to identify problems, their cause, and potential response | Gather team members and experts together and discuss to identify risks |  |  | A |  | 1
You have been assigned as a project manager to a software project. Before creating your product, you decided to create a prototype to ensure that it is acceptable to stakeholders. This is an example of: | Multiple Choice | Risk avoidance | Risk Transference | Risk mitigation | Risk acceptance |  |  | C |  | 1
A project manager working with a risk-averse financial firm has Just started a new project. The project sponsor is extremely concerned that the project may run over budget and is looking to the project manager for confirmation that this won't happen. In order to alleviate the sponsor's concerns, what should the project manager do? | Multiple Choice | Perform a strengths, weaknesses, opportunities, and threats (SWOT) analysis. | Run a Monte Carlo simulation. | Create the probability and impact matrix. | Use historical data analysis. |  |  | A |  | 1
Your program manager has advised that you need to protect the organization from financial risk. In planning a new project, you realize there is a limited scope definition related to the work required to fulfill the contract. What is the best type of contract to choose? | Multiple Choice | Fixed price incentive fee (FPIF). | Time and material (T&M) | Cost plus fixed fee (CPFF) | Cost plus incentive fee (CPIF). |  |  | D |  | 1
A project manager feels the need of updating one of the project supplier contracts to meet the current needs of the project. However, before any change can be requested, the project manager must know the right process to Incorporate a change to this specific contract. What should he do first? | Multiple Choice | Issue the change request and get it approved through Integrated Change Control process | Update the project procurement management plan | Review alternative dispute resolution (ADR) procedures in the contract | Review the change control procedure as documented in the contract |  |  | D |  | 1
One of the sellers has completed their work as specified in the contract and you are proceeding to close out the purchase. Your quality team is not satisfied with the work as the machining tolerances are not as close as they had hoped for. You need to do which of the following with the seller? | Multiple Choice | Terminate the contract. | Close out the procurement and start a new contract for any rework. | Request that they rework the parts to the specified tolerances. | Request from seller to issue a change request. |  |  | B |  | 1
When do bidder conferences normally take place? | Multiple Choice | After the contract has been awarded to keep alternatives open. | Prior to the submission of a bid or proposal by the bidder. | After the contract has been awarded to keep alternatives open. | After technical meetings with bidders to discuss contract requirements. |  |  | B |  | 1
During project closure and transferring of the completed project deliverables to the operations group, the project manager discovers that an audit report from an early project phase is missing. What should the project manager do? | Multiple Choice | Remove the audit report from the required project documents and update the project management plan | Complete project closure and Update the OPA | Ask the operations group to accept the project without the audit report. | Inform the operations group about the missing audit report. |  |  | D |  | 1
A security team notifies a project manager of a change in security procedures. The project manager uses the change control process to update the project management plan. After seeing the change, a stakeholder complains that it was unnecessary because the project is almost complete. What should the project manager do? | Multiple Choice | Add a risk to the risk register to track the impact of stakeholder disagreement. | Ignore the stakeholder's concern and follow the new procedures. | Create a change request to reverse the change until a consensus is reached. | Convince the stakeholder of the benefits resulting from the change. |  |  | D |  | 1
You are a project manager in a software project. A development team completed the project and plans to Initiate the closure phase. However, one key stakeholder refuses to sign-off due to non-compliance with the agreed-upon deliverables. What should the project manager do to facilitate acceptance? | Multiple Choice | Record the noncompliance and initiate project closure. | Conduct a variance analysis to identify any deviation in the deliverables. | Document the noncompliance and start the change management process. | Provide a new statement of work (SOW) for the variation in the deliverables |  |  | B |  | 1
A project manager is in charge of an important project, and the customer requests changes on a continuous basis. The project manager implemented the change requests without documenting the change requests to satisfy the customer. The project manager realized that his project exceeded costs. What could have been done by the project manager to prevent cost overruns? | Multiple Choice | Change management plan | Project management plan | Cost management plan | Schedule management plan |  |  | A |  | 1
The project team is reviewing the requirements documentation that they are responsible for working on. Which project artifact can they reference to see the connection between the requirements and the business and project objectives? | Multiple Choice | Scope management plan | Requirements traceability matrix | Project charter | RACI Chart |  |  | B |  | 1
An architectural firm has spent a great deal of time and effort creating the design and blueprints for the building. They had to purchase materials and hire consultants and have been working on this project for six months. They have submitted all the Invoices for the money they have spent on the work, as well as an Invoice for the fee of $5,000. What type of contract was this? | Multiple Choice | Fixed price with economic price adjustments (FPEPA). | Time and materials | Cost-plus incentive fee (CPIF). | Cost-reimbursable |  |  | D |  | 1
When can the contract closeout occur? | Multiple Choice | Whenever a contract is completed and accepted. | At the end of a project only. | Whenever a seller is selected. | At the end of a project only, unless the project is terminated early. |  |  | A |  | 1
What are the goals of contract closeout? (Choose three) (Choose three) | Multiple Response | To provide a performance evaluation of seller staff. | To arrange for final settlement of seller payments and claims. | To verify work was done and delivered to specification. | To close the project. | To update contract records and documents. |  | BCE |  | 1
As the project team gains better understanding of the value their product might deliver, they are excited to make the product a reality. Due to the volume of features and the work required, the project team decides to delivery incrementally. What are some benefits to this strategy? (Choose three) (Choose three) | Multiple Response | Makes senior leadership promote their work. | Enables the end users to provide feedback. | Allows progress to be realized. | Allows the team to discard or ignore the challenging work. | Creates a sense of urgency to deliver part of a solution. |  | BCE |  | 1
The business is unclear on the direction and when features are to be expected for an agile managed project. What project artifact helps communicate the goals, milestones, and potential deliverables, releases, or other work outputs? | Multiple Choice | Project charter | Requirements documentation | Product roadmap | Configuration management plan |  |  | C |  | 1
The business is anxious to get a portion of the project's creations out into the marketplace to get end user feedback and impressions before the entire product is finished. What must the project team establish for their release to end users? | Multiple Choice | Velocity | The minimal viable product | Transition plan | The sprint cycle |  |  | B |  | 1
Minor impediments may interfere with or slow down day-to-day progress. Which tool or practice can be used to bring attention to those impediments on a regular basis? | Multiple Choice | Kanban boards | Lessons learned | Annual conferences | Daily standups |  |  | D |  | 1
Early in the establishment of the project, the project manager spends time looking for historical data that might be helpful in planning the new project. She is looking for examples of project documents in similar projects that have been completed that she might be able to use as templates for the new project. She is also looking for information about established processes and procedures that will help the project run more smoothly. What is the term used to define these? | Multiple Choice | Progressive elaboration | Organizational process assets (OPAs). | Retrospective | Enterprise environmental factors (EEFs) |  |  | B |  | 1
Every timeboxed iteration in the project has a demo scheduled at the end during the iteration review session. What is the goal of this demo? | Multiple Choice | To establish the features to be included in the product backlog. | To solicit feedback from the product owner and other stakeholders. | To revise the product roadmap. | To groom the iteration backlog |  |  | B |  | 1
At the end of an agile project chartering session, a stakeholder asks the project manager when will be the first opportunity to view the team's progress on the development of the new application. Which scrum event should the project manager suggest to the stakeholder to attend? | Multiple Choice | Sprint review meeting | Sprint retrospective meeting. | Daily scrum meeting | Sprint planning meeting |  |  | A |  | 1
There is disagreement among the project stakeholders makes the project manager having difficulty obtaining approval of the project requirements. As a project manager, what should you do first to facilitate the approval of project requirements? | Multiple Choice | Identify the source of the disagreement. | Team building Activities | Conduct a stakeholder analysis | Review the project charter. |  |  | A |  | 1
A team member is continuously improving. This team member has been a role model and mentor to others in the organization. How should the project manager acknowledge this team member's commitment? | Multiple Choice | Appreciate this team member's performance throughout the project life cycle. | Promote this team member to a coaching role after this project is completed. | The team member should negotiate the scope with the client. | Document it in the team member's end of year performance review. |  |  | A |  | 1
A newly technical project manager has appointed by the client. The technical project manager visits the project site to verify the project deliverables, the technical manager feels that the project manager has not been providing enough Information. As a project manager, what should you do first to resolve this situation? | Multiple Choice | Update the issue log and escalate to the project sponsor. | Schedule frequent one to one meetings with the technical manager | Review and update the stakeholder engagement plan. | Update the risk register. |  |  | C |  | 1
Adam is a project manager who is starting a project using a hybrid approach and notices some team members only have knowledge of predictive approaches. What does Adam need to do first in order to have good project performance? | Multiple Choice | Replace the team with hybrid approach experts | Coach those team members lacking hybrid knowledge. | Assess the required training per team member. | Deliver hybrid training to all team members |  |  | C |  | 1
Six agile teams working together on a product. When all of the teams integrated at the product level, many integration issues were observed. The overall product release progress declined and the content will not be able to be accomplished. What should the project manager have done differently? | Multiple Choice | Formed a quality control team to test all items coming from each team at the end of each iteration. | Performed a scrum of scrum on a regular basis to help the teams remove impediments. | Ensured frequent and continuous integration of work to obtain early feedback and continuous learning. | Conduct an online session on the integration concept to teach the teams. |  |  | B |  | 1
You are a project manager in a construction project. At the end of a project with multiple suppliers, you start reviewing the closing process and finds that an unexpected financial balance is remaining. Which of the following will help you to understand why this has occurred? | Multiple Choice | Project audit. | Organizational process Assets | Procurement audit. | Lessons learned. |  |  | C |  | 1
An issue that had not been registered as a risk appeared. This issue may have a big impact on the project. What should the project manager do? | Multiple Choice | Hold a meeting with the project team and relevant stakeholders to agree on the best way to manage the issues. | Inform the sponsor that the issue is addressed | Avoid managing the issue as it was not registered as a risk for the project | Delay the project until the issue is addressed |  |  | A |  | 1
After the completion of a project with specific users in various countries, the project manager wants to know if the project users are satisfied with the way the project was run. What two actions should the project manager take?Choose two (Choose two) | Multiple Response | Send a questionnaire and seek their feedback. | Prepare the lessons learned from the project phase. | Obtain official approval on the new process form the various countries. | Deliver the project materials to the users and see if they have any comments. | Review the communication management plan |  | AE |  | 1
A project manager is starting a new project and has identified an opportunity to use the iterative tools. One of the senior managers is concerned about this modified framework as it is new to the company. What should the project manager do first? | Multiple Choice | Organize individual sessions with the stakeholders to build awareness and trust in the new framework. | Escalate the senior manager's concern to the project sponsor and distribute the status to the team. | Look for external training on the new framework to eliminate the risk of low engagement from stakeholders. | Send documentation to the senior manager about the advantages of the new framework. |  |  | A |  | 1
A company is initiating a project to enhance one of its existing products. All of its products are developed internally. What should the project manager do? | Multiple Choice | Create a lessons learned document for the initiation phase. | Ensure the stakeholder engagement plan is accurate and properly documented. | Review the lessons learned from the previous project. | Identify the risk of implementing the new solution and evaluate the impact on the project. |  |  | C |  | 1
Several team members seem disinterested in the daily standup meeting and are carrying on a side conversation. What should the agile coach do first? | Multiple Choice | Stop the meeting and dismiss the participants | Inform their functional managers after the meeting | Ignore the issue and let the meeting continue | Let the team uphold its own ground rules |  |  | D |  | 1
A skilled project manager should have the necessary expertise to identify appropriate project management approaches (traditional vs. Agile) and tailor the tools, techniques, and methods for each project. What are these skills called? | Multiple Choice | Leadership skills | Strategic and business management skills | Technical project management | Interpersonal skills |  |  | C |  | 1
Due to the complexity and the number of requirements, you need someone to provide the guiding direction and requirements prioritization. Ideally, this role should work with the project team and provide product feedback, and set direction on the next piece of functionality to be delivered. In Agile, this role is called? | Multiple Choice | Scrum master | Cross-functional team member | Product owner | Servant-leader |  |  | C |  | 1
"The most efficient and effective method of conveying information to and within a development team is face-to-face conversation". Which of the following Agile techniques help achieve this? | Multiple Choice | Backlog preparation | Daily standups | Team composition | Backlog refinement |  |  | B |  | 1
Due to the complexity and size of the project, the project team needs a product roadmap that shows the anticipated sequence of deliverables over time. Who is responsible for producing this roadmap? | Multiple Choice | Agile team | Scrum master | Product owner | Servant-leader |  |  | C |  | 1
Which of the following will most likely require an approved change request before the change can be accommodated? (Choose Three) (Choose Three) | Multiple Response | A senior executive has recommended updating the project life cycle description to include an additional phase. | The revised status of several tasks needs to be reflected in the project schedule. | A suggestion has been made to change from predictive to a hybrid development approach. | A new stakeholder has just been identified and needs to be added to the stakeholder register. | The project is running well over budget, and the cost baseline needs to be revised to reflect reality. |  | ACE |  | 1
Agile teams use which of the following to collaboratively prioritize user stories based on their respective value to the project's customer? | Multiple Choice | Conducting sprint retrospectives | Kanban board | Rolling wave planning | Backlog refinement |  |  | D |  | 1
A project manager receives a request for a proposal (RFP) from a client. The client is very clear about the requirements. A requirements analysis must be done in the first month of the project, and the client wants to see a demo of the work completed every two weeks. What project approach should the project manager use? | Multiple Choice | Predictive for the requirements analysis and agile for delivery of the project | Iterative for the requirements analysis and delivery phases of the project | Predictive for the requirements analysis and delivery phases of the project | Agile for all of the phases of the project, including the requirements analysis and delivery |  |  | A |  | 1
Monica, the project manager of a hardware project, is performing a structured review of the procurement process. She would like to examine each document from the Plan Procurement Management process through the Control Procurements process to Identify failures. What tool should Monica use? | Multiple Choice | Procurement audits in the control procurements process | Procurement audits in the conduct procurements process | Performance reports in the conduct procurements process | Negotiated settlements in the control procurements process |  |  | A |  | 1
Agile approaches promise better user experience of project deliverables in comparison to the traditional waterfall based approaches. This is due to | Multiple Choice | Early development of an exhaustive product backlog. | Relying less on processes and more on documentation. | Early and continual involvement of users. | Relying less on documentation and more on processes. |  |  | C |  | 1
A project team is currently analyzing Its current Iteration progress and reviewing the following chart. What is this chart called? | Multiple Choice | Burndown Chart | Control Chart | Histogram | Burnup Chart |  |  | A |  | 1
System requirements have been collected and the project scope has been defined. If one of the major project's success factors is delivering within the budget, which of the following approaches would you recommend to be used on this project? | Multiple Choice | Incremental | Iterative | Predictive | Agile |  |  | C |  | 1
You have been asked to develop a new website for one of your clients. The website is required to be browser independent and delivered within a month. Although the website has a simple design, the requirement of browser independence has added some complexity to the project. Which of the following approaches would you recommend for this project? | Multiple Choice | Incremental | Predictive | Iterative | Agile |  |  | C |  | 1
You are working on a large project that is divided into the following phases: feasibility, conceptual, design, prototype, and build. You want to use the process groups with these different phases. What is the recommended approach? | Multiple Choice | Eliminate your phase structure and rename each phase with one of the process group names | Assign one process group to each phase | Repeat all the five process groups for each phase | Skip a couple of the process groups since they don't apply to a large project |  |  | C |  | 1
Due to a recent technological development, a significant change in the product design is required. This change would require a so percent increase in the project budget. The project manager prepares a detailed report and emails it to the project sponsor, and the sponsor acknowledges the receipt of the report. What should Ben do next? | Multiple Choice | Update the Project management plan | Update the project schedule | Update the Cost Baseline | Wait for the formal approval of the new budget |  |  | D |  | 1
An Agile team is struggling with coordinating work in progress. This is causing unnecessary conflicts and delays on the project. Which of the following two techniques can help this situation? | Multiple Choice | Story boards and retrospectives. | Gantt chart and backlog grooming | Prototyping and backlog grooming. | Kanban boards and daily stand-ups. |  |  | D |  | 1
Your Agile team is collocated except one of the team members who is based at the client location.How should you conduct your dally standups with this constraint? | Multiple Choice | Conduct the face-to-face daily standups without the remotely located team member. | Do not use daily standups and rely on formal written communications. | Use video conferencing technology to accommodate the remote team member. | Since all of the team members are not collocated, this is not an Agile project. It is recommended reverting back to traditional project management approaches. |  |  | C |  | 1
"Business people and developers must work together daily throughout the project". One of the 12 Agile principles.Which of the following Agile techniques helps achieve this? | Multiple Choice | Kanban boards | Retrospectives | Backlog preparation and refinement | Daily standups |  |  | C |  | 1
An Agile team is currently developing an inventory control system. Two programmers on the team are arguing and recommending different development approaches. One is of the view that the system should be built from scratch, white the other believes that the existing system should be enhanced and patched. How should you resolve this conflict? | Multiple Choice | Develop the product from scratch as that will bring the system closer to requirements. | Ask the entire team to analyze both approaches and select the one that will deliver higher business value. | Select the patch work approach as that will save time for the organization. | Ask the product owner to choose the right approach. |  |  | B |  | 1
"Responding to change over following a plan" is one of the key Agile Manifesto values. Which of the following Agile approaches helps in achieving this value? | Multiple Choice | Self-organizing teams | Servant-leader | Kanban boards | Backlog refinement |  |  | D |  | 1
After several Iterations, some of the stakeholders from your software development project have begun to raise concerns about the product your team has developed so far. The stakeholders claim the product هs not what they had envisioned at the beginning of the project when you interviewed them as part of the Collect Requirements process. What did you likely miss earlier? | Multiple Choice | Creating a detailed WBS during project initiation | Conducting targeted brainstorming sessions | Developing adequate prototypes | Planning a response to the risk of building a wrong product |  |  | C |  | 1
An agile project started 6 months ago. Since the beginning of the project, there have been disagreements among team members regarding daily meetings since some of the team members are not available at the same time. The project manager is convinced an agile team should be self-organizing, and that meeting times should be worked out by the team. What should the project manager do? | Multiple Choice | Establish a project schedule. | Establish a team charter. | Assign a team leader. | Recognize the team's contributions. |  |  | B |  | 1
A project team has examined the degree of variance relative to the scope baseline. The project manager needs to know If the variance has been Improving or deteriorating as the project has progressed. What should the project manager do next? | Multiple Choice | Perform variance analysis | Perform a trend analysis | Conduct product analysis | Complete stakeholder analysis |  |  | B |  | 1
If the deliverables will be produced using an agile framework. What strategies might be appropriate to gain formal acceptance of the product scope? (Choose two) (Choose two) | Multiple Response | Ask the product owner to attend each sprint retrospective to review and approve the completed product increment | Conduct a demonstration whenever enough features have been developed to form a coherent set | Ensure that the product scope is fully decomposed down to the work package level during initial project planning | Perform the Validate Scope process once the entire project scope is complete in accordance with the scope management plan | Have the team demonstrate the completed user stories to the product owner at the end of each iteration |  | BE |  | 1
When grooming the backlog, which of the following is the greatest determinant for priority? | Multiple Choice | Value | Dependencies | Risk Mitigation | Politics |  |  | A |  | 1
While working on the layout of one of the screens on a mobile application, a developer on an agile team came up with a screen improvement idea that will increase the application's usability, and ultimately Increase customer satisfaction. Implementing this Idea represents a new requirement. The developer's first thought is to Implement this improvement to impress their client. What should the developer do next? | Multiple Choice | Collect the supporting information for this requirement and present this information to the product owner | Suggest this requirement to the product owner for possible inclusion in the next iteration | Implement this requirement to show the product owner the improvement in terms of the application's usability | Do nothing since this requirement is out of scope and it should not be added to the product |  |  | B |  | 1
A project manager is leading a virtual team that is geographically dispersed. What should the project manager do to avoid uncertainty in the project due to different cultures? | Multiple Choice | Dissolve the virtual team and build a collocated team. | Build a culturally neutral team that will not be affected by cultural differences. | Start the project and add any uncertainty that arises to the risk register | Gather relevant cultural data and engage members in discussions covering their work ethics. |  |  | D |  | 1
An agile team has Just finished an iteration in which one of the user stories is only partially complete. Which of the following is true regarding incomplete user stories? | Multiple Choice | Partially completed stories are included in velocity estimates | Incomplete user stories are excluded from velocity estimates. | The project team must complete the user story with the next iteration | Partially completed stories represent partial value for the customer |  |  | B |  | 1
After an agile team completes three iterations, the project manager determines that the average velocity of the team for these three iterations was 50 story points. There are 300 more story points to complete the remaining portion of the project. How many additional iterations will it take for the team to complete the project? | Multiple Choice | 6 iterations | 10 iterations | 5 iterations | 7 iterations |  |  | A |  | 1
large construction project for a logistics company will require the expenditure of a large amount of capital. The finance group works with the project manager to project set limits when expenses will be incurred in a given project and to determine whether there are ways to smooth out or level the spending to avoid a single large expenditure in one quarter and none in the next. This is an example of: | Multiple Choice | Crashing | Funding Limit Reconciliation | Resource leveling | Rescheduling |  |  | B |  | 1
A project manager is starting a project using a hybrid approach. The customer decided on a major change for the project design. This change was approved. The software team leader who is supposed to develop the software refuses to commit to delivery dates, claiming that they work using an agile approach and cannot commit to the final delivery date. The hardware team depends on this software to develop their part of the product. As a project manager, what should you do? | Multiple Choice | Impose the delivery dates on the software team leader and notify the functional manager about the situation. | Escalate this to higher management and ask for help to resolve the issue. | Ask the software team leader to use a predictive approach and commit to the delivery date. | Update the risk register with this risk and monitor it according to the risk management plan. |  |  | C |  | 1
Adam has Just taken over a construction project. The project is currently in the planning phase of the project lifecycle., Adam realizes that a stakeholder engagement approach will not suffice. One of the client representatives, who Is not a key decision-maker, is extremely opinionated. This client representative could become a roadblock to progress due to their perceived level of authority during meetings. How should Adam handle this situation? | Multiple Choice | Ask that only key decision makers attend the project meeting. | Update the project schedule to cater to this particular stakeholder. | Allocate time to gain buy in from the stakeholder prior to key decision meetings. | Update the risk register to consider the possible project impacts. |  |  | C |  | 1
During the retrospective ceremony, the agile team is talking about the product owner's expectations not being met. What should the project manager have done at the beginning of the project? | Multiple Choice | Assessed the capabilities of the agile team and planned for the required training. | Communicated project vision and sprint goals clearly to the team. | Defined the team ground rules and shared project vision. | Defined the expected agile team contribution in the creation of the backlog. |  |  | B |  | 1
A Junior staff member was recently assigned to the team. The new team member tells the project manager that he is confused because he is not familiar with what is expected of them on the project. What should the project manager do to assist the new team member? | Multiple Choice | Instruct the new team member to review the responsible, accountable, consult, and inform RACI matrix before asking for help. | Advice the new team member to review the project charter and stakeholder engagement plan. | Review the resource management plan and provide mentoring to the new team member if necessary. | Advice the new team member to enroll in project management training. |  |  | A |  | 1
An integrated project involves the interaction of both hardware and software, and the sponsor has approved the schedule management plan. The project team evaluated the product's feasibility of functionality and accelerated testing What should the project manager do as servant leader? | Multiple Choice | Amend the project budget to include MVP testing. | Submit a change request to the project sponsor for accelerated testing. | Develop the product as per the schedule to perform integration and testing. | Support the team as necessary to find the minimum viable product (MVP) |  |  | D |  | 1
During the implementation phase of a project, a new regulation affects the project, and a critical status meeting discussing the scope changes is required. The project manager discovers that a key stakeholder cannot attend the scheduled meeting What should the project manager do? | Multiple Choice | Update the communications management plan and implement the change | Meet with the stakeholder prior to the meeting to obtain their opinion | Meet with the project sponsor to discuss how to address the situation | Call for a change control board (CCB) meeting, and inform the stakeholder about the outcome |  |  | B |  | 1
A project manager is acting as a scrum master in a hybrid project and is dealing with a conflict between team members. What strategy should be used to handle this conflict? | Multiple Choice | Place conflicts into categories: structural and interpersonal | Place conflicts on a shared conflict list and ensure it is visible | Sort conflicts into two groups: positive and negative | Review conflicts during daily Scrum so they are handled in a timely manner |  |  | C |  | 1
In a multinational project, stakeholders are in different time zones. The project manager has regular project update meetings with the stakeholders. However, a group of stakeholders who have never attended project update meetings is complaining to the project sponsor that they know very little about the project. What should the project manager do? | Multiple Choice | Change the meeting time to the working time zones of the stakeholders who are complaining | Ensure that the stakeholders who are complaining are present for the next project update meetings. | Discuss the issue with all stakeholders and work on a communications management plan to meet all stakeholder requirements. | Record the regular project update meeting and share it with all stakeholders after the meeting is completed. |  |  | C |  | 1
A government agency has recently Introduced new standards that may significantly impact the project. The deliverables must be changed to align with the new quality standards. What should the project manager do? | Multiple Choice | Update the lessons learned register and inform senior management of the new standards | Set up a structured, independent process to determine if project activities followed the standards | Evaluate the impact the new regulations will have on the project and submit a change request | Schedule training for the project team on the new regulations introduced by the government agency |  |  | C |  | 1
The project is approaching the end. Several tasks are now practically complete and ready for handover to the client. How should the project manager proceed? | Multiple Choice | Close out the project tasks that have been completed | Update the communications management plan for the overall project | Ask the client to verify and accept the tasks that have been completed | Update the quality management plan for the overall project |  |  | C |  | 1
An agile project is starting and the assigned team is new to agile. During the first daily meetings, the project manager observes that the team is having problems meeting goals. What should the project manager do? | Multiple Choice | Ask the team to review agile project management approaches | Conduct a meeting to help the team define the team charter | Plan an outdoor activity for the team to get to know each other | Ask the human resources department for an experienced agile team |  |  | A |  | 1
Adam is a project manager who is starting a project using a hybrid approach. Adam has requested a senior team member to perform a quantitative risk analysis the team member responds that they do not have the knowledge to perform such an analysis. What should Adam do? | Multiple Choice | Contact the project management office (PMO) and request them to assign another team member who has the knowledge to perform this task to the team | Perform the quantitative risk analysis for the team member | Escalate the issue to the functional manager | Help the team member to perform the quantitative risk analysis through coaching, mentoring and training |  |  | D |  | 1
The project sponsor recently requested that a vendor begins working toward adopting a hybrid approach. In response, the vendor hired a project manager experienced in agile for the project. What does that project manager need to do to make the team work in a collaborative way? | Multiple Choice | Identify any training gaps | Allocate time to mentor the team | Update the issue log. | Request the project management office (PMO) for a team of mentors. |  |  | B |  | 1
A project is delayed due to multiple problems discovered during the quality review. Every time the team addresses one problem, additional problems are encountered. This is frustrating for both the project team and the project sponsor, who are driven to meet the dates and results expected by the organization. What should the project manager do? | Multiple Choice | Ask the team to commit to a new date to fix all the problems and proceed with a change request to adjust the baseline. | Request that a senior subject matter expert (SME) be hired to analyze and solve the problems. | Request that the team identifies, documents, and registers the issues to locate the source of the problems. | Evaluate the cost and schedule variance in order to determine how much the project is off track. |  |  | C |  | 1
The technology market is very competitive and getting Its product out to market quickly Is one of the critical factors for the success of a technology start-up. An agile team launches the product with minimal features and plans to learn from the early adopters' feedback. What agile tool or technique is the team embracing in this situation? | Multiple Choice | Kano Analysis | WBS | Product Analysis | Minimum Viable Product ( MVP) |  |  | D |  | 1
A project manager has a team of shared resources from other projects who are working on a client project. Three days before the project is due. The team informs the project manager that the project will be delayed because a component was not delivered on time Competing priorities of the shared resources are delaying delivery of the component. What should the project manager have done to prevent this delay from happening? | Multiple Choice | Maintained constant communication with the stakeholders of the other projects | Updated the risk management plan and registered lessons learned for the project | Reorganized the team for the project based on the work breakdown structure (WBS) | Used the resource management plan to identify the impacts of the other projects |  |  | A |  | 1
You are a project manager managing a multimillion-dollar project. The project is considered to be high risk since no similar projects have been undertaken before and there is no historical data. Some external stakeholders are reluctant to provide support. As a project manager, what approach should you take? | Multiple Choice | Examine the plans, processes, policies, and knowledge that are specific to the organization undertaking the project | Convince senior management to close the project since the project lacks sponsorship and is considered to be high risk | Host a project team meeting, then update the risk register and the project management plan | Establish dialogue with stakeholders on the project constraints, assumptions, and critical inputs |  |  | D |  | 1
A team is ready to start working on a project with a customer who was very difficult to work with in the past because the customer was unable to describe exactly what they wanted. What approach should the project manager take to remove this impediment? | Multiple Choice | Reinforce the negotiation and soft skills of the team through training | Follow a predictive approach in order to obtain formal acceptance of each deliverable | Work with the product owner to define the minimum viable product(s) | Develop and monitor a plan with due dates to reduce the time of completing the product |  |  | C |  | 1
A project manager is struggling to figure out the performance of the project teams in an agile environment for the same scope of work, team A has calculated 100 story points and team B has calculated 125 story points. Which team is performing better? | Multiple Choice | Team Bas they have calculated more story points than team A | The team that completes the most stories selected from the sprint backlog | The team with the least amount of defects in their deliverables | Team A as they have calculated fewer story points than team B. |  |  | C |  | 1
You are a project manager managing a bridge construction project. The high-level elements of the project are handled using a predictive approach. The software responsible for retracting the bridge has been developed based on agile principles. During software development, the workflow is often interrupted by various delays or impediments due to a lack of information. As a project manager, how you handle this situation? | Multiple Choice | Apply lean manufacturing to limit the team's work | Make work visible using kanban boards | Increase retrospectives to deliver results fast | Incorporate small batches of work into the project |  |  | B |  | 1
You are a project manager for revamping an existing product. The marketing executive reaches out to the project manager to make sure that necessary measures are in place for a successful launch. As a project manager, you should focus on: | Multiple Choice | Ensuring that the scope management plan is in place to cover all related objectives | Determining and aligning performance indicators that will help in assessing successful delivery | Ensuring that the team is also focused on the overall change management plan | Planning for regular project updates to cover the status of critical deliverables |  |  | B |  | 1
According to the project contract the delivery date is approaching. However, one important material is still not on site. The construction work will have to stop and wait for this special material, delaying the project.What should the project manager do? | Multiple Choice | Ask the client to help solve the problem | Start procuring this material from another supplier. | Engage the project team to look for alternatives to find a solution | Record it in the risk register |  |  | C |  | 1
A project is nearing completion The contingency time has been consumed. To ensure that the final deliverables are achieved on time and within budget, the project manager has asked the team to follow a rigorous process. This is causing some resistance among the team members. What should the project manager do to address the growing resistance? | Multiple Choice | Crash the project schedule and ask project team members to work overtime to meet the new timeline | Describe to the team members how specific tools and techniques can be used to finish on time | Convince team members to use a specific methodology to complete the project on time | Motivate project team members by offering incentives to complete the project on time |  |  | D |  | 1
A self-organizing team was delivering as committed. The team accepted a development task with new technology and the iterations started to have reduced velocity. What management decision is suited for this situation? | Multiple Choice | Add new members to the team and increase the velocity | Re-assign the project to a team that has worked with this technology | Move team members who are not performing from the team. | Provide opportunity for team members to learn and adjust to the technology |  |  | D |  | 1
At the closing phase of the project, the project manager sends the completion reports to the client as a formal written document, Indicating that the contract has been completed The client refuses to approve the document since the defect rate is 0.1%. The project manager insists that it is an acceptable rate as the standard defect rate of the Industry is 0.15%. What should have been done to avoid this situation? | Multiple Choice | The acceptance criteria should have been properly defined in the contract | The Manage Quality process should have been appropriately conducted | The client requirements should have been clearly defined in the contract | The project manager should have reviewed the standard industry defect rate |  |  | A |  | 1
A project manager is assigned to a project in a company that is transitioning to agile. Not all stakeholders believe in the project, and some stakeholders would like the entire project defined and planned out early in the project. However, the project sponsor needs a quick win to ensure the continuation of the project. What approach should the project manager use? | Multiple Choice | A predictive approach as this would please the senior stakeholders. | A hybrid project as this will Mitigate stakeholders' concerns. | An Agile approach as this would provide working functionality earlier. | A predictive approach as this will show benefits for all stakeholders. |  |  | B |  | 1
A hybrid project has just deployed, and the project manager is planning project closure with lessons learned workshops. A key stakeholder informs the project manager that having the Scrum team in the workshops is a waste of time because the project was delivered successfully. What should the project manager do? | Multiple Choice | Ask the scrum master to attend the workshops. | Ask the Scrum team members to share retrospectives. | Invite the Scrum team members as optional participants. | Invite the Scrum team members as mandatory participants. |  |  | B |  | 1
A project manager meets with the development team to estimate the time required to complete a software application. The software developers are new to the company, and they have never developed a similar application. Which estimation technique should the project manager recommend? | Multiple Choice | Analogous estimating | Planning poker | Three-point estimating | Parametric estimating |  |  | B |  | 1
During project execution, the client provided updated requirements, which apparently will only require a minor adjustment to the work breakdown structure (WBS). What should you do first? | Multiple Choice | Deny the request as it represents scope creep | Submit a change request to update the schedule baseline | the WBS as necessary as the change is minor | Submit a change request to update the scope baseline Adjust |  |  | D |  | 1
A customer is concerned about the time required to complete a project and is asking the project team to reduce the number of iterations required to complete the product. Which approach should the project manager take? | Multiple Choice | Prioritize the tasks with high risks to reduce the number of iterations required. | Ask the team to raise blockers or impediments in daily meetings. | Ask the team to challenge the project estimations for faster delivery. | Prioritize deliverables based on business value and define frequent releases |  |  | D |  | 1
A company is launching a new product that has to be ready before the summer season begins. After the discovery process, the team realizes that the requirements are very uncertain. What should the project manager do? | Multiple Choice | Invite stakeholders to discuss project requirements prioritization. | Ask to include some business subject matter experts (SMEs) in the team. | Register a risk and define a contingency plan to finish the project on time. | Assist the team in proposing a minimum viable product (MVP). |  |  | D |  | 1
A project manager notices that a new junior team member's suggestions are constantly rejected by senior team members. The senior team members find the suggestions valid and innovative, but unrealistic. Following several project assignments, the senior members request to have the junior team member removed. What should the project manager do next? | Multiple Choice | Encourage further and deeper discussions among team members. | Accept the demands and remove the junior team member. | Group the new team members together for training purposes. | Remove possible conflicts from future project assignments |  |  | A |  | 1
A stakeholder informs the project manager about a few compliance-related gaps and issues. The stakeholder then presents several suggestions to the project manager to address the issues. What should the project manager do? | Multiple Choice | Use the compliance issues to identify coaching and mentoring opportunities. | Review this with the project sponsor to avoid compliance gaps and issues. | Discuss the suggestions with the staff responsible for the compliance issues. | Log the feedback from the compliance gaps in the lessons learned register. |  |  | C |  | 1
A project manager is performing the serum master role for a project team of developers. At the daily standup, a couple of developers complain about the noise from a neighboring team, the performance of their laptops, and the difficulty in booking meeting rooms. What should the project manager do? | Multiple Choice | Note the impediments and escalate them to the product owner. | Assign actions to all stakeholders and oversee their implementation. | Note the impediments and work on addressing them later. | Acknowledge the impediments and facilitate their resolutions |  |  | D |  | 1
A large matrix organization is adopting a new communications approach. This is necessary because their projects often require the resourcing of expert knowledge in the form of specialists from various departments and divisions. What should the project manager do to set up effective communications? | Multiple Choice | Focus on the recipients' needs and not the information itself. | Ensure that messages sent to the recipients are delivered. | Use the highest possible technical language and avoid using metaphors. | Plan on transmitting the information in an easily understandable manner. |  |  | A |  | 1
Which of the following describes the characteristics of the performing stage? | Multiple Choice | In the performing stage, the team completes the work and disbands as a project team. | In the performing stage, the team starts to work together and adjust their behavior. | In the performing stage, the team function as a well-organized unit and resolve issues effectively. | In the performing stage, the team members are not collaborative. |  |  | B |  | 1
A project team is trying to meet the milestone target dates in order to receive a bonus promised by the project sponsor. Unforeseen challenges and poor communication among the team members resulted in mistakes and delays. Tensions are high, and the sponsor is concerned. What should the project manager do? | Multiple Choice | Organize a team meeting to remind the team of the ground rules. | Discuss with the team how the project objectives can be met. | Request that the sponsor increase the bonus for high performers. | Schedule a team-building activity to boost the team's morale. |  |  | D |  | 1
A project manager is leading a project team composed of members with varying levels of knowledge and experience. Some are experts and some have less than 1 year of experience. The project schedule was approved by the steering committee. What should the project manager do? | Multiple Choice | Ask the resource manager to replace the less-experienced members with more experienced team members. | Ask the more experienced members to review all of the tasks performed by the less-experienced members. | Ask the less-experienced members to perform tasks exactly as they are instructed by the experienced members. | Ask each experienced member to be the mentor to one of the less-experienced members |  |  | B |  | 1