## Exam Data
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
Important projects in the portfolio backlog need to be delivered. Budget estimates are needed to prioritize the project. How should the project budgets be estimated? | Multiple Choice | The project is decomposed into features and based on the feature value and the velocity of the team, the team provides the estimate. | The team facilitator uses historical data and arrives at an estimate based on the nature of the project. | Budget estimates are provided based on the experience of the sponsor, product owner, and team facilitator | The product owner obtains all project details and based on the team's experience and velocity provides budget estimates. |  |  | C |  | 1
A project manager working with the team to develop a software application. Due to failures in similar applications in the past, the rapid feedback from the customer on the suitability of the deliverables is very important. What is the best approach that should be selected? | Multiple Choice | Adaptive | Traditional | Waterfall | Predictive |  |  | A |  | 1
A project manager is assigned to a project in a company that is transitioning to agile. During the sprint retrospective meeting, the meeting becomes slightly contentious with the first signs of conflict between several team members. What is the best course of action for the project manager? | Multiple Choice | Address the situation during the meeting to hold the individuals who are involved in the conflict accountable | Intervene only if the conflict becomes destructive and take a break if needed to address individuals privately | Intervene immediately to avoid further escalation and damaged relationships between the team members | Do not intervene regardless of what happens since agile teams are self-managing and can handle anything |  |  | B |  | 1
An agile team wants to use a quick method using relative size to estimate the user stories. Which metric would you recommend to the team? | Multiple Choice | Story points | Lead time | Velocity | Real-time |  |  | A |  | 1
Based on this chart , what can besaid about this process? | Multiple Choice | Out of control based on the measurement of 4.1 mm, and corrective action should be taken | Out of control based on the rule of seven, and corrective action should be taken | A In control since all of the measurements are between 4 mm and 5 mm | In control because the average thickness is between 4.2 mm and 4.8 mm |  |  | A |  | 1
You are a project manager for the Internal project that will deliver a new tool to the performing organization for use by its employees. A conflict occurred between the project team and the training manager. The team wants to use short development cycles to gain early feedback and manage the high rate of change coming from the employees. The training manager, on the other hand, insists on creating a detailed training plan upfront to train the employees. What is the best way for the project manager to resolve the conflict? | Multiple Choice | Emphasize the commonalities between both approaches | Force an agile framework to satisfy the project team | Avoid the conflict by escalating the issue to the project sponsor | Facilitate a compromise by adopting a hybrid approach |  |  | D |  | 1
Henry is a new project manager has assigned to an existing project. Henry starts reviewing the work assigned to the team that has already been decomposed to its lowest level but he feels some additional, useful information is missing. What should henry review? | Multiple Choice | Requirements documentation | The project charter and scope statement. | The WBS dictionary. | The requirement traceability matrix. |  |  | C |  | 1
You are a project manager in a construction project. Due to some reasons that seem to be outside of the project acceptance criteria, you are having difficulty obtaining the final acceptance of some deliverables from a stakeholder. As a project manager, what should you do? | Multiple Choice | Escalate this issue to the project sponsor and ask for support in obtaining final stakeholders' acceptance. | Create a project acceptance waiver, noting the stakeholder's concerns so they can be addressed later. | Obtain final acceptance from another stakeholder who is also familiar with the project | Persuade this stakeholder using emotional intelligence skills to obtain acceptance. |  |  | A |  | 1
On the branch of a decision tree, you see a decision has a 60% chance of earning a $1000 profit, but also a 40%chance of a $2000 loss. What is the EMV of this branch on the decision tree? | Multiple Choice | None | -$200 (loss) | -$800 (loss) | $600 (profit) |  |  | B |  | 1
A large organization will transform from a predictive environment to agile methodologies. In its current state, the work in the organization is decomposed into departmental silos, and the employees are best described as specialized contributors. What is the best strategy for this agile transformation? | Multiple Choice | Establish a fixed date for all projects to transition from predictive to agile | Tailor projects so that the scope is fixed with time and cost being variable | Use hybrid life cycles as a transition strategy from predictive to agile | Introduce some agile techniques to a large and complex project |  |  | C |  | 1
Based on the following information, what is the project performance? BAC= US$ 1 million EV= US$ 0.7 million AC= US$0.75 million CPI= 0.933 | Multiple Choice | The project will be completed exactly as planned | The project won't be complete as planned | The project will be difficult to complete as planned | The project will be easier to complete than planned |  |  | D |  | 1
A key project stakeholder who was a big supporter and motivator for the project team leaving the organization. The project team is experiencing low morale and poor teamwork. What should the project manager do to improve morale? | Multiple Choice | Identify the wants and aspirations of the team. | Build team connections and emotional bonds. | Forge consensus through team participation. | Set goals and push the team to achieve the goals. |  |  | A |  | 1
During the retrospective of the fifth sprint the project team complains that many obstacles exist with the organization that are creating project delays and rework. What should the project manager do in this situation? | Multiple Choice | Create a dedicated sprint to solve the obstacles with the team. | Promote collaboration to help remove the obstacles for the team. | Perform a root cause analysis during the stand up meetings | Include impediment resolutions during daily stand-up meetings. |  |  | B |  | 1
A project team is experiencing delays in completing a task that turned out to be more complex than initially estimated. This is a critical task that could impact current iteration goals. What two options will help the team initially address this obstacle? Choose two (Choose two) | Multiple Response | Create a risk management plan. | Conduct a root cause analysis. | Escalate the issue to the project sponsor. | Review and update dependencies | Schedule a retrospective. |  | BD |  | 1
One team member is not as active as the rest of the team during a brainstorming session. The project manager has a separate conversation with the team member and learns that the team member is slightly hearing impaired. The team member appreciates the project manager's concern. The project manager then decides to change the time and room for the meeting to ensure everyone can participate. What interpersonal skill did the project manager use? | Multiple Choice | Influencing | Networking | Conflict management | Emotional intelligence |  |  | D |  | 1
As per the burndown graph shown below, the dotted burndown line is the plan. What should the team see at day 3? | Multiple Choice | The iteration on track. | There is a cost overrun. | The iteration is ahead of schedule. | They are at risk for that delivery. |  |  | D |  | 1
There are five stages of development that teams may go through. Which of the following is the correct order in which these stages occur? | Multiple Choice | Forming, Norming, Performing, Storming, Adjourning | Norming, Storming, Forming, Performing, Adjourning | Forming, Performing, Norming, Storming, Adjourning | Forming, Storming, Norming, Performing, Adjourning |  |  | D |  | 1
An error detected in the engineering drawing and results in significant rework, and cost overruns. The project manager performs a root cause analysis and discovers that the drawing was not checked according to procedures. What should the project manager do to ensure that this doesn't happen in future projects? | Multiple Choice | Capture the findings in the lessons learned repository. | Inform all the other project manager. | Identify and control the resource responsible for the mistakes. | Update the quality management plan. |  |  | A |  | 1
A project manager discovers a significant flawin a major project deliverable. Which project management process is being performed? | Multiple Choice | Manage quality. | Statistical sampling. | Control quality. | Plan quality management. |  |  | C |  | 1
Task B is dependent upon task A which is delayed. Resource for task B have limited availability and must begin task B on time.What should the project manager do to replan the schedule so that the deadline is unchanged.? | Multiple Choice | Fast track task A and move task B's start date. | Fast track task B and immediately begin work. | Replan task B's start date so it begins after the completion of task A . | Crash task A and start task B at the planned time. |  |  | D |  | 1
Before disbanding a project team, the project manager facilitates a lessons learned workshop, what should the project manager do next? | Multiple Choice | Organize a party to celebrate the project success. | Review the issue log, update if necessary to minimize the impact on the project. | Send project documents to the stakeholders. | Archive project documents using generally accepted practices. |  |  | D |  | 1
Which of the following are components of a Resource Calendar? (Choose two.) (Choose two) | Multiple Response | Training Strategies | Availability of physical resource | Working days | Recognition Plans |  |  | BC |  | 1
Which of the following describes the most common phase-to-phase relationship in multi-phase projects? | Multiple Choice | Sequential | Finish-to-start | Non-overlapping | Orderly |  |  | A |  | 1
In addition to the departments listed in the scenario, your company also has a manager of project management to oversee all of the ongoing projects. As one of the project managers, you report directly to the project management department but share staff with other departments. What type of organizational structure does this describe? | Multiple Choice | Projectized | Functional | Matrix | Composite |  |  | C |  | 1
Which of the following statements most accurately describes a typical project scenario? | Multiple Choice | Changes in project scope during the initial phases of the project are very expensive. | The next phase of a project should never start until the deliverables for the previous phase are completely reviewed and approved. | The influence of the stakeholders is the same all through the project. | Staffing peaks during the execution phase of a project. |  |  | D |  | 1
When should the risk identification occur? | Multiple Choice | During the Plan Risk Management process | Ongoing throughout the project | During the Perform Quantitative Risk Analysis process | During the Perform Qualitative Risk Analysis process |  |  | B |  | 1
Where should the project manager obtain the initial cost-benefit analysis? | Multiple Choice | The project charter | The benefits management plan | From the customer | The business case |  |  | D |  | 1
The ------ is also called "the voice of the customer"? | Multiple Choice | Development team | Product Owner | Sponsor | Scrum Master |  |  | B |  | 1
On traditional projects, a change control board is usually established to authorize change requests. Who is responsible to authorize changes on an Agile project? | Multiple Choice | Product owner | Agile team | End users | Scrum master |  |  | A |  | 1
Which of the following is one of the major challenges faced by an organization just beginning to use Agile approaches? | Multiple Choice | Avoidance of multi-tasking introduces inefficiency. | Daily standups could be viewed as time-intensive activities. | Agile approaches could be viewed as plan-driven. | Iterative prototypes involve rework that could be viewed negatively. |  |  | D |  | 1
The code being delivered to your software development project by another team is consistently five days late. When you ask the leader of that group about the delay, he states the company's quality control testing processes take five days. What should you do? | Multiple Choice | Advise the leader to stop any quality control processes that are not mandated by your project policies | Crash the project | Develop a communications plan to ensure the project team understands the required delivery schedule | Add resources |  |  | C |  | 1
You are a project manager for a maintenance project. The contract is renewed annually. The project started 5 years ago. After contract renewal this year, the auditor reported that this version of the contract violates a new law that was passed last year. What has happened in this situation? | Multiple Choice | The project manager does not have enough knowledge on this legal matter. | The stakeholder engagement plan has not been correctly implemented. | The contract hasn't been appropriately reviewed by the project team. | The legal department has not disseminated the law correctly to all staff. |  |  | D |  | 1
During the demo of an agile project. the client states that the product does not reflect the product vision and requirements initially discussed. Theclient says that the product needs significant changes before It would be acceptable. What might have prevented this situation? | Multiple Choice | Managing conflicts more efficiently between the client and the team | Following a more rigorous organization's change control process | Allowing higher transparency of the work in front of the stakeholders | Isolating the development team from stakeholders to avoid distraction |  |  | C |  | 1
A project manager is assigned to a project that is in progress. The project is running behind schedule which is attributed to the poor performance of the project team. You want to Improve their performance and avoid repeating past mistakes. What should you do first? | Multiple Choice | Meet with the team and ask for their input | Review the project team assignments | Check out the team charter | Review the lessons learned log |  |  | D |  | 1
Although the team delivered the required features, they encountered several issues and conflicts during the sprint. Team members were upset about this experience and are now showing a lack of motivation due to what has occurred. What can the project manager do to help increase the team's motivation and engagement with the project? | Multiple Choice | Review sprint progress with the project team members | Review sprint planning procedures with the project team members | Perform a sprint retrospective with the project team members | Set up one-on-one meetings with the project team members |  |  | C |  | 1
A project manager is using a hybrid approach for project delivery. The development team was sized but is not yet fully resourced. The project manager is working on defining the project schedule. What should the project manager do to address the issue of developer availability? | Multiple Choice | Use expert judgment to estimate all of the tasks and complete the schedule in the allocated time. | Ask the resource manager when the new contractor is available to start and change the delivery date for the project schedule. | Ask the sponsor to provide the desired completion date for project activities and complete the schedule. | Organize a planning session with the development team and use their estimations to complete the schedule. |  |  | D |  | 1
You are a new project manager assigned to a project in the execution stage. A few key stakeholders inform the new project manager that the project has some serious issues.What should the newly assigned project manager do first to understand the issues? | Multiple Choice | Escalate the issues to the project sponsor. | Check the risk management plan to ensure there is a strategy to address the issues | Review the issues log to ensure the issues are captured | Ask the key stakeholders to discuss the issues with the project team. |  |  | C |  | 1
You are a project manager for a global project. During the planning process, team members from different regions are not agreeing to collaborate with each other. As a project manager, what should you do? | Multiple Choice | Review the organizational culture, structure, and governance | Review lessons learned from previous projects that used the same team | Coordinate a meeting to understand the situation and resolve any conflicts | Coordinate a meeting with regional managers to ask for support |  |  | C |  | 1
A new project manager has been assigned to an environmental project. After reviewing the project plan, the project manager notices that health and safety requirements have not been properly addressed. This is a serious concern, and the project manager wants to fix this issue immediately.Why is this situation problematic? | Multiple Choice | The project manager is obligated to comply with the project location's regulatory requirements. | The project manager must follow their employer's organizational process assets (OPAs). | Injury or loss incidents could delay project deliverables. | It is imperative that established performance metrics are met. |  |  | A |  | 1
You are a project manager for an important project. The schedule performance index (SPI) is 1.8 and the cost performance index (CPI) is 0.1. The project sponsor told the project manager that if this trend continues, they will be forced to prematurely close the project. What should the project manager do? | Multiple Choice | Manage the project sponsor closely and revise the project's resource management plan to improve indicators | Stop crashing the schedule | Monitor the project sponsor but understand that it is normal to spend more money in the design phase of a project. | Use a resource-leveling technique |  |  | B |  | 1
A project manager invites the company CEO, sponsor, team members, and an external client representative to a meeting to review the project management plan. The project manager starts to present the budget but the CEO suddenly asks to end the meeting. What should the project manager have done to avoid this situation? | Multiple Choice | Sent the presentation slides to internal participants first and then to the external client representative prior to the meeting | Reviewed the cost management plan with internal participants and CEO prior to inviting an external client representative to the meeting | Reviewed the communications management plan before inviting an external client representative to the meeting | Performed a root cause analysis with the external client representative and documented the findings in the lessons learned register |  |  | B |  | 1
The performing organization does not have a project management office (PMO) or formal governance policies procedures, and guidelines for this type of project. As a project manager, what should you do first to determine a governance approach for the project? | Multiple Choice | Consult with team members and stakeholders to determine whether the organization has any informal governance policies procedures, and guidelines | Choose either a predictive or agile framework best suited to the nature of the project, and use this framework as the basis for project governance policies, procedures, and guidelines | Consult a subject matter expert (SME) as to the best governance policies, procedures, and guidelines to be used by the project | Coach the self-managing team to produce tailored governance policies, procedures and guidelines for the project |  |  | C |  | 1
A supplier was supposed to mobilize a government-issued, licensed piece of equipment two days ago, but did not. The procurement manager was informed that the supplier failed to check the validity of the license, which expired last week.The supplier had already submitted an application to the authorities, but it generally takes one to three weeks to process the application, which will affect the critical path.Which action should the project manager take? | Multiple Choice | Update the project team on the delay so that resources can be utilized elsewhere. | Update the lessons learned register to serve as an input for future material transactions | Review the terms of the contract in order to determine the next steps | Analyze the schedule and look for fast-tracking and crashing alternatives |  |  | C |  | 1
After gathering all the requirements for a project with dependencies on external stakeholders, the project team Is finishing the second Iteration. At this point, the project manager learns about a possible change In regulations that would prevent the product launch. What should the project manager do to realize benefits? | Multiple Choice | Review target benefits | Implement the changes | Improve the team's velocity | Add an entry in the risk log |  |  | A |  | 1
The project manager was asked to recommend an agile practice to provide business value throughout the project.What should the project manager recommend? | Multiple Choice | Iterative development and collection of frequent feedback from project team members | Frequent retrospectives to ensure that lessons learned and improvement actions are implemented | Incremental delivery and frequent backlog refinement based on user feedback | Time-boxed iterations to allow the testing team to thoroughly test the product increments |  |  | C |  | 1
A project manager is implementing a new software system. Some department staff members are questioning the necessity of the change and feel the new system will impede their current processes.What should the project manager have done at the start of the project to prevent this resistance? | Multiple Choice | Ensured that the company culture encourages changes before accepting the project | Involved stakeholders from all levels of the company so everyone understands the change | Created a communications management plan that outlined the method of communicating to stakeholders | Encouraged leadership to discuss the change with departments that are typically resistant to change |  |  | B |  | 1
The project manager has finished all the tasks of the project and immediately starts on a new project. A few months after beginning the new project, the accounting manager asks for confirmation of previous projects because the budget is still open with no further cash flows.What should the project manager have done? | Multiple Choice | Conveyed task completion information to accounting | Completed the transition process | Performed administrative closure of the project | Closed the procurement process properly |  |  | C |  | 1
A company's (PMO) is incorporating more agile technologies and has hired a new project manager with hybrid project management experience. The team is slow in adopting the new methodology and has not been updating project artifacts in a timely manner. Which action should the project manager take to improve the team's performance? | Multiple Choice | Set up a training session for all project team members | Reach out to the functional managers for support | Speak individually with each project team member about making the needed updates | Send an email asking all project team members to complete updates at the end of the day |  |  | A |  | 1
In a hybrid project, a project team is facing a lot of obstacles and blockers from some stakeholders. As a project manager, what should you do to improve project performance? | Multiple Choice | Empower the team members to remove obstacles and blockers | Address and remove obstacles and blockers for the team | Ask stakeholders to communicate with the project manager and not directly with the team | Add blockers to the issue log and risk management plan |  |  | B |  | 1
At the end of the third iteration in a hybrid project, a business analyst joins the team to learn about the financial and scheduling aspects of project management. What should the project manager do to support the business analyst? | Multiple Choice | Provide the business analyst with access to the financial and scheduling information | Ask the business analyst to focus on their work allocation for the needs of the project | Create reports to inform the business analyst about the schedule and project cost | Assign resources to coach the business analyst |  |  | A |  | 1
A company uses a hybrid approach to project management and has just completed the first sprint. A team member provided Ideas to improve the testing process during the sprint retrospective.What is the next step for the project manager? | Multiple Choice | Document the lessons learned and implement improvements in the next sprint | Facilitate a daily standup with the team to track the implementation of changes | Organize a demonstration of the changes in the enterprise system | Request that all team members think of ideas to improve processes |  |  | A |  | 1
A hybrid project is used to transit from a current system to a new and enhanced system. The plan is to transit the system in stages. However, the operations team is complaining that they are not ready to start supporting the new system. How should the project manager effectively approach this situation? | Multiple Choice | Create lessons learned register to include operations team training for future projects. | Change the project management plan to add a final stage for product handoff to the operations team | Include knowledge transfer sessions between the project and operations teams at every stage | Prepare detailed documentation to be shared with the operations team during project closure |  |  | C |  | 1
A project in the implementation phase and is managed using a hybrid approach. What should the project manager do to ensure full compliance of quality requirements during the execution phase? | Multiple Choice | Plan quality management | Continually survey the quality of the deliverable | Analyze the quality requirements | Set up quality policies and procedures |  |  | B |  | 1
A company that is introducing a new product into the market by the end of the year requires a storage and distribution facility to be built. During the monthly stakeholder meeting, it is discovered that the location for implementation is a government-owned area What should the project manager do first? | Multiple Choice | Update the issue log | Identify an alternative site | Update the risk register | Issue a change request |  |  | C |  | 1
A new project manager is assigned to a project to an agile project and discovers that a contractor for the project does not have any experience with agile. What should the project manager do? | Multiple Choice | Ask the project sponsor to replace the contractor since they do not have agile experience | Consult the project team to understand the extent of the training needs for the contractor | Issue a formal notice to the contractor to obtain an agile certification | Instruct the contractor to receive agile training since the project has already started |  |  | B |  | 1
A new project has been kicked off following a planning session. The project is under the direct oversight of an executive in the organization. After a review meeting, the project manager overhears an executive request a dashboard from one of the team members to show the overall project status What should the project manager do? | Multiple Choice | Ask the team member to develop a dashboard to fulfill the request | Update the communications management plan to include informal requests | Tell the team member to route the request through the project manager | Update the stakeholder engagement assessment matrix |  |  | B |  | 1
An intern is replacing a critical resource midway through a sprint. To help the intern get up to speed, the project manager assigns a senior engineer in the team as the intern's mentor. Two months later, the project goes into critical status, delaying the release milestone by a month. What should the project manager have done to avoid this scenario? | Multiple Choice | Negotiated additional time to complete the project | Convinced the critical resource to remain on the project | Requested an experienced resource as a replacement | Allocated additional time for mentoring |  |  | C |  | 1
You are a project manager managing a multinational project. A project baseline has been approved. During project execution, the project manager discovers that multiple risk elements have appeared. The project manager did not foresee these risks during the planning stage of the project. What should the project manager calculate to address this critical budgetary situation? (Choose two) (Choose two) | Multiple Response | Currency exchange rate | Benefits management control in the project | Contingency control in the project and rebaseline | Mitigation control in the project | Integrated change control in the project |  | CE |  | 1
You are a project manager for a complex project. A service provider on the project has been facing resource availability problems for the last four months. However, the service provider has assured the project manager that the deliverables will be on time.As a project manager, How you address this situation? | Multiple Choice | Perform a qualitative risk analysis | Perform a root cause analysis | Update the issue log | Implement a risk response plan |  |  | C |  | 1
You are a project manager for an agile project. The project manager is working with key stakeholders from different parts of the organization. How should the project manager handle the different stakeholders? | Multiple Choice | This is an agile project, so listen only to the directions of the project manager's supervisor and the functional managers of the organization | Because there are different perspectives perform a stakeholder analysis and act based on the outcome. | All stakeholders are important, so the project manager should follow directions provided by management and key stakeholders | The project manager is working on the client's premises, so follow the directions of all the key stakeholders |  |  | B |  | 1
A vendor informed the project manager that a critical resource will be on a long leave of absence. The project team reviewed the pending vendor deliverables and identified an alternative solution, but the solution will incur an additional cost. The project is currently on schedule and slightly under budget. What should the project manager do next? | Multiple Choice | Request a replacement resource | Perform a cost-benefit analysis | Perform Integrated Change Control | Implement risk responses |  |  | C |  | 1
A stakeholder from the legal department does not attend any of the project meetings during the project planning and is not interested in the product design. As a project manager, how to deal with this situation? | Multiple Choice | Review the product requirements and update the stakeholder register | Engage the project stakeholder and ensure all requirements are captured | Review the stakeholder engagement plan and communication strategy | Review the product requirements and update the stakeholder register |  |  | C |  | 1
During a retrospective meeting, the development team wants to identify what had a positive impact on the velocity and keep doing it. Choose the area that the team should focus on to identify good practices. (Choose the) | Multiple Choice | A4 | A3 | A5 | A1 | A2 |  | C |  | 1
The team is located in different countries around the world. Team members are in multiple time zones and they use different languages for communication. The project manager needs to keep the team organized and avoid misunderstandings and miscommunication that may produce a negative impact to the project. What should the project manager do to reduce negative impacts to the project? | Multiple Choice | Conduct a multigenerational management training session | Modify the communications management plan to account for regional differences | Hold a virtual meeting to discuss the political environment | Conduct cultural awareness seminars |  |  | B |  | 1
You are a project manager for a construction project. Part of the agreed-upon plan was to use a cloud-based system with a server that runs on high-speed internet service since most of the team members work virtually. The company needs to reduce operating costs as much as possible and management insists that the project will now use a system running on a conventional dial-up service. As a project manager, what should you do next? | Multiple Choice | Evaluate the impact of this decision and communicate with management | Replace some of the team members that work virtually to help the company save money | Agree with management and continue working the project management plan | Meet with management about their decision and ask them to get another project manager |  |  | A |  | 1
You are a project manager managing the XYZ project. The project team is geographically distributed and has development issues between the collocated and virtual teams causing productivity to decrease. As a project manager, what should you do to address this issue? | Multiple Choice | Force the team members to work from one location | Develop protocols for resolving conflicts between team members | Obtain special expertise to advise the team members | Set up face-to-face meetings with project team members |  |  | B |  | 1
A project manager was asked to provide an indication of the time remaining on an agile project. What tools can be used to provide this information? | Multiple Choice | A release burndown chart | Analysis of the business requirements document | Story points for the remaining user stories | Pareto chart |  |  | A |  | 1
A project team is having difficulties understanding technical details regarding requirements. The information was not initially provided by the customer, but the information is critical in the current iteration for clarification on how tasks need to be accomplished. How should the project manager approach this situation? | Multiple Choice | Educate the customer and have them participate in daily standup meetings. | Request that the customer reviews and clarifies feature definitions for the current sprint | Schedule weekly meetings and product reviews with the customer to clarify requirements | Send a burndown chart of the current sprint to the customer and seek clarifications |  |  | B |  | 1
During an Iteration demo, a customer noticedan enhancement they would like to make to the product. What should the team do next? | Multiple Choice | Refine and estimate the enhancement so the size is known | Add it to the product backlog to be completed in the future | Start working on the enhancement for the customer immediately | Ask the product owner to prioritize the item with the customer |  |  | D |  | 1
After a project has been approved, a key stakeholder tellsthe project manager that the current project management strategy is not well defined The project manager is also informed that the key stakeholder does not want to hold a working session What should the project manager do first? | Multiple Choice | Ask the project sponsor to exert authority on the key stakeholder in order to maintain the approved timeline | Proceed with a working session for teams that do not belong to that key stakeholder | Share the project documents and invite the key stakeholder to discuss any concerns | Invite the key stakeholder to the project's change control board (CCB) to discuss adjustment of the project strategy |  |  | C |  | 1
A key project stakeholder showed interest in the beginning of a complex agile project but has become less involved as the sprint has progressed due to additional responsibilities. A few sprints later, the key stakeholder rejected a feature deliverable. The team is reworking the rejected deliverable for the next sprint. What should the project manager have done to avoid this situation? | Multiple Choice | Involved the key stakeholders in the decision-making process | Analyzed the changes in stakeholder attributes | Customized stakeholder communications based on the stakeholders' needs | Documented the project vision and objectives |  |  | A |  | 1
Vendor A submitted a bid for US$500,000. There is a 65% probability that the vendor will deliver behind schedule with a cost overrun of US$ 100,000.The vendor will come in ahead of schedule for a savings of US$50,000. What should the project manager determine as the value of the vendor's bid? | Multiple Choice | US$582,500 | US$452,500 | US$547,500 | US$750,000 |  |  | B |  | 1
The project schedule is falling behind and the project manager observes that the project team seems to be spending the majority of their time writing documentation instead of performing project tasks, What should the project manager do to help ensure that the team focuses on project tasks? | Multiple Choice | Save all documentation activities until the end of the project | Assign a team member to handle the documentation activities. | Review and adapt the appropriate project artifacts | Coach the project team to complete the project documentation activities |  |  | C |  | 1
A research and development team is finishing up a two-year initiative. The project manager is focused on the closing activities for the project.Which activity should be considered as a priority? | Multiple Choice | Hold a steering committee meeting to inform them of the project completion | Mark the product backlog completion status and update the communications management plan. | Ensure that knowledge transfer activities are executed as planned | Release the resources and plan for a project completion celebration. |  |  | C |  | 1
The project charter was just approved and the project sponsor has given permission to proceed with the project. The program manager has confirmed that one of the requested key resources is also needed on another project at the same time. This will affect project delivery. What should the project manager do? | Multiple Choice | Pay overtime to key resource to get the work done outside of working hours | Speak with the client to see if the project delivery deadline can be delayed due to resource availability | Have a meeting with project manager of the other project to find a resource optimization solution that works for both projects | Talk to the program manager and about prioritizing this project over other projects so the key resources are available |  |  | C |  | 1
A company wants to increase the commercial value of one of its products in a highly competitive market. In order to do this, the company commissions a project to create a prototype. The team constructs the prototype incrementally. Which action should the project manager take as a priority? | Multiple Choice | Implement a plan-do-check-act (POCA) cycle | Emphasize the use of Kanban methodology. | Deliver business value as soon as possible | Ensure the project sponsor is aware of the go-to market date |  |  | C |  | 1
A company has decided to implement a new archiving system. A data breach occurred during the implementationof the project. What should the project manager do first? | Multiple Choice | Review possible alternative documentation methods with team. | Implement the planned risk response to handle the issue. | Ask the team to fix the system to resolve the issue. | Update the risk register with the risk and proposed impact. |  |  | C |  | 1
A project manager has been using a predictive methodology for more than 9 years and is switching to an agile project. The team members have not previously worked together. After two sprints of work, the team has not achieved any outcome and there is a lot of pressure to get work done. What kind of leadership style should the project manager use at this stage? | Multiple Choice | A democratic style that uses techniques where majority opinion prevails | A passive leadership style that allows the team to self-organize until the norming stage is reached | A directive style that makes decisions for the group to reach early outcomes | A leadership style that coaches people who want help and fosters greater team collaboration |  |  | D |  | 1
A project is in the implementation phase and is managed using a hybrid approach. What should the project manager do to ensure full compliance of quality requirements during the execution phase? | Multiple Choice | Plan quality management | Analyze the quality requirements. | Continually survey the quality of the deliverable | Set up quality policies and procedures |  |  | C |  | 1
The project manager has recently received funding approval for a training program for the entire project team but has not yet defined the most effective training course. One team member submitted a request for specialized training that is required for the project. How should the project manager handle this request? | Multiple Choice | Reject the request as it does not impact the project deliverables. | Validate if the training is within scope and budget. | Approve the request for the specialized training. | Send this change request to the change control board (CCB) for approval. |  |  | B |  | 1
While reviewing prototypes, the quality team found some deviations that do not affect the main functionality but have the potential to be an issue in the future. To avoid major problems in the future, the team recommends corrective actions that will require additional funds. The project is already struggling to stay on budget and has even used some of the contingency reserves.What should the project manager do? | Multiple Choice | Report to the project sponsor that the product is working and the project is struggling with the budget. | Ask the quality team to discard the sample and test again with a new sample | Evaluate and initiate the change request process with the stakeholders | Ask the product designer why the deviation was not considered in the design phase |  |  | C |  | 1
A project manager is leading a project with several stakeholders in other functional areas of the company. One of these stakeholders has just been promoted to lead another functional area, and remains a stakeholder for this project. What should the project manager have the project team update to ensure proper communications to stakeholders? | Multiple Choice | Stakeholder engagement plan | Project management plan | Communications management plan | Stakeholder register |  |  | D |  | 1
During the execution phase of a healthcare IT project, the customer's project manager resigns. The key stakeholders are no longer getting updated information in a timely manner. What should the project manager do next? | Multiple Choice | Update the communications management plan | Inform the key stakeholders directly | Update the project sponsors on the issue | Keep sending the information until a response is received |  |  | A |  | 1
While developing a new product, a key stakeholder expresses concern about insufficient information on product feature requirements. The product team disagrees and mentions that detailed requirements have been provided. What should the project manager do to handle this situation? | Multiple Choice | Conduct new risk and scope analyses, identifying the missing information. | Redirect the stakeholder to discuss this request with the functional manager. | Record the new requirements and ask the product team to develop them. | Organize a discussion with the product team to clarify the missing information. |  |  | D |  | 1
During the final stage of a project, one of the key stakeholders asks the project manager to debrief the executive board about the return on investment (ROI) and any relevant new commercial value identified during project implementation. What should the project manager do next? | Multiple Choice | Review the benefits management plan. | Review the cost-benefit analysis | Review the cost management plan. | Review the financial success factors |  |  | A |  | 1
A project manager is working with a Scrum team that is continually missing deadlines. The steering committee is concerned about the project as it is not clear that it will deliver the expected value. After some analysis, the project manager discovers there is a mismatch of competencies in one of the teams. What should the project manager do? | Multiple Choice | Update the project schedule to reflect the delay | Provide appropriate training to compensate for the mismatch. | Accept the risk of the project missing deadlines due to the mismatch. | Emphasize to the teams the importance of meeting the agreed deadlines |  |  | B |  | 1
During the closing process, the project manager learns that one deliverable is not meeting customer expectations. How should the project manager proceed? | Multiple Choice | Contact the project sponsor and ask for help in negotiating the closing of the project with the customer | Ask the customer to issue a change request with the information to analyze and provide a solution. | Meet with the customer to reach agreement on the scope of the deliverable that will satisfy both parties | Review the deliverable requirements, check the customer approval criteria, and proceed accordingly |  |  | D |  | 1
A project manager is leading a project which shows a trend to exceed the cost baseline. What should the project manager do first to manage the budget? | Multiple Choice | Ask the project sponsor for assistance in getting the budget back on track | Meet with the project team to analyze the actual cost to determine deviations | Issue a change request including the analysis to increase the budget | Inform the stakeholders that the project will be finished over budget |  |  | B |  | 1
A project manager is appointed to simultaneously deploy a new solution to branches located in different countries. Deployment teams in each country will integrate and deploy the solution. The project manager discovers that the deployment teams each encounter similar issues, However, each team addresses the issues separately. What should the project manager do to help ensure more collaboration between the teams? | Multiple Choice | Ask each deployment team to provide a very detailed schedule and action plan | Ask the project sponsor to appoint new managers for the deployment teams | Propose that some of the teams delay deployments in their countries | Organize regular meetings with all of the deployment teams to share issues and solutions |  |  | D |  | 1
During a retrospective review, many project team members say they are not completing tasks during the iterations because of interruptions and requests for help from other teams. As a team facilitator, what should the project manager do to avoid this? | Multiple Choice | Reunite with the project team members affected and tell them not to reduce the team's capacity | Identify the problem's root causes and define the ground rules with all project team members to minimize interferences | Hire a coach to help all project teams to improve their abilities to solve problems on their own. | Recommend to the project team members that they should improve their planning and make their stones smaller |  |  | B |  | 1
A project manager realizes that the team members are new to the hybrid approach and do not value standup meetings. Team members often arrive late or skip the meetings altogether. How should the project manager improve this situation with the project team? | Multiple Choice | Ask the product owner to remove team members who do not comply with standup meeting rules. | Send a daily retrospective report to all team members instead of holding standup meetings. | Include a daily brainstorming session In the standup meetings to resolve pending Issues. | Engage the project team in implementing and Improving key aspects of the standup meetings. |  |  | D |  | 1
A project is going through its iterative design stage. One of the team members has been performing poorly. This is a critical project for the company and execution is about to start. What should the project manager do? | Multiple Choice | Escalate the issue to the human resources manager and request that the team member be replaced | Avoid selecting the team member to the next project that has an iterative design stage. | Request action from the functional manager regarding the team member's poor performance. | Provide feedback and coach the team member during the iterative design stage. |  |  | D |  | 1
A company has transitioned and is now delivering projects using a hybrid approach instead of a predictive approach. The distributed project team's knowledge of agile is varied. The project manager feels this new methodology will impact the timely delivery of the project. What should the project manager do? | Multiple Choice | Ask to execute the project with a predictive approach since there is a budget and schedule risk | Use crashing to reduce the critical path to ensure enough buffer to include the impact of the agile methodology update. | Plan for training on agile tools and techniques used in the defined hybrid methodology for consistent application by all team members. | Use the predictive approach for team members who are not knowledgeable in agile project delivery practices. |  |  | C |  | 1
A project manager is instructed by the project sponsor to draft the project charter. The project sponsor asks the project manager to involve a particular stakeholder in order to provide necessary resources. However, the stakeholder is refusing to get involved because the stakeholder thinks that there is no benefit in using the project deliverable. What should the project manager do to resolve this? | Multiple Choice | Escalate to the project sponsor due to the political nature of the issue | Meet with the stakeholder to discuss the impact of the deliverable. | Consider the stakeholder as a risk and evaluate possible solutions with the project team. | Improve communication with the stakeholder to obtain their assistance in the future |  |  | B |  | 1
A project manager works in a key project that has critical and time-sensitive delivery objectives. One of the project team members missed completing an assigned deliverable on time, despite repeated assurances from the team member that it would be completed on time. As a project manager, what should you do next? | Multiple Choice | Hold a team meeting to discuss team member commitments and communications. | Record the issue, then refocus the team's efforts on delivering the next set of deliverables. | Give the team member a formal warning for the negative impact due to failure to deliver and not meet deadlines. | Meet with the team member and work on a development plan for them to avoid missed deliverables in the future. |  |  | B |  | 1
A project manager has been working with the same groupof stakeholders for 4 years using a predictive approach. The stakeholders have invested in many projects and are familiar with the approach. Recently, the organization has strongly encouraged all project managers to adopt an agile approach. This was announced 2 weeks before the project manager planned to kickoff a large, complex project with the same group of stakeholders. What should the project manager do? | Multiple Choice | Share and discuss the pros and cons of adopting agile with the stakeholders and choose the approach they prefer for the new project | Share the pros and cons of adopting an agile approach for the new project only with the team and ask them to decide which approach to use | Continue to use the predictive approach in the new project since it is the approach the stakeholders are familiar with using | Use the agile approach in the new project and schedule agile training for those stakeholders who are new to this approach |  |  | D |  | 1
A new solution is being deployed in countries A, B, and C. This solution will allow the countries to propose new services to their customers. Country A has asked for a change in the solution in order to comply with its own customer market. What should the project manager in charge of the deployment in country A do? | Multiple Choice | Refuse country A's request as there is no time for the change as deployment has already begun. | Accept the change request from country A and reschedule the deployment project for country A. | Ask country A to submit a change request that will be analyzed along with countries B and C | Take the request into account and ask the sponsor to inform countries Band C about the change |  |  | B |  | 1
A project manager is assigned to a digital transformation project for a bank. The company culture is conservative and resistant to transformation or innovation. What should the project manager do first to support the transformation? | Multiple Choice | Hire an expert in digital transformation and assign that person as the champion for the change. | Provide a digital transformation guide and explain that the change is unavoidable. | Provide proper training sessions to the stakeholders So they understand the purpose of the change | Ask the bank executives to officially announce that the project manager is leading the project. |  |  | C |  | 1
A project manager primarily works on implementation projects. Depending on the deliverable, the project manager is able to estimate the timeline based on previous projects. The project manager now receives a project that is differentfrom the previous implementation projects. What should the project manager do next? | Multiple Choice | Break down the project into smaller tasks and estimate the durations of the activities. | Refer to the previous project they worked on and base the estimate on that. | Use expert judgment to estimate the schedule and then adjust the schedule as the project progresses. | Ask the project management office (PMO) by when the project can be completed and use that date as the project timeline. |  |  | A |  | 1
A project manager acquired information from the market that would reduce the business value being delivered by an ongoing project. Based on that information, the project manager believes the project should be stopped. How should the project manager handle the situation? | Multiple Choice | Have a discussion with the project sponsor and cancel the project. | Continue working on the defined scope and review the risk matrix. | Have a discussion with the sponsor and recommend the project business value be reassessed. | Remove the items no longer applicable from the backlog and present the backlog to the project team. |  |  | C |  | 1
During the development of a product, multiple identified risks have now become issues, which is hindering the team's velocity. What should the project manager do in this situation? | Multiple Choice | Prioritize the user stories with issues and have the team resolve them. | Document the issues and extend the project delivery timeline. | Convene the steering committee and inform them of the impact to the project. | Update the project management plan and risk management plan. |  |  | A |  | 1
A major national company known for quality products has just selected a small subcontracting firm to assist with a project. The project manager from the subcontracting firm is meeting with the project team to ensure that the project is delivered according to the customer's standards. In order to ensure this, what should the project manager define and document? | Multiple Choice | Objectives | Estimates | Requirements | Quality |  |  | C |  | 1
You are a project manager for a hybrid project. There is software in place to access the repository of project artifacts. However, a few stakeholders are reporting that they are unable to find the latest project schedule. As a project manager, what should you do? | Multiple Choice | Advise the project management office (PMO) that there is a resource gap for sharing project artifacts effectively | Make sure all stakeholders have access to the system and know where to find project artifacts. | Escalate the issue to the steering committee and ask them to deal with the stakeholders' lack of training. | Send the project schedule via email to the stakeholders who need that information. |  |  | B |  | 1
A project selection committee is shortlisting projects for the coming year. Which selection criteria should the project manager recommend? | Multiple Choice | Projects with maximum revenue generation | Projects with the least associated risks | Projects that maximize the business value | Projects with the least duration |  |  | C |  | 1
A project team is experiencing conflict between two team members. Team member A feels that team member B is always talking over team member A and does not listen to any advice. Team member B is not willing to listen to feedback. What should the project manager do to resolve the issue? | Multiple Choice | Review the ground rules for collaboration within the team. | Move one of the team members to a different project team. | Modify the communications management plan and resend it to the team. | Report the performance issue to both of the team members' supervisors. |  |  | A |  | 1
A project manager is working on a critical path activity and notices a delay in product delivery due to an anticipated event. What should the project manager do first? | Multiple Choice | Prepare a change request | Follow the risk response plan | Use the contingency fund. | Update the risk register |  |  | B |  | 1
A team member has encountered a technical issue, similar to the one faced in a successfully closed project. However, the team member did not know about the previous project and would like to resolve the issue on their own. What should the project manager do? | Multiple Choice | Improve the risk management strategy and risk monitoring | Share the lessons learned from the previous project with the team member | Reach out to the project manager of the previous project for assistance. | Allow the team member to work through the issue as a training opportunity. |  |  | B |  | 1
A lead project manager for an agile project needs to prioritize requirements, define the scope of the initial product, and deliver the approved scope in a series of multiple versions. What should the project manager do next? | Multiple Choice | Determine the expected benefits of each requirement to maximize the overall business value. | Work with the product owner to evaluate and prioritize the requirements. | Prioritize the requirements based on the hierarchical level of the requesting stakeholders. | Ask the lead developer to run a meeting with the stakeholders to agree on an ordered list |  |  | B |  | 1
A new project team has formed, and the project manager notices that some of the team members do not feel comfortable being part of the project team. As result, members of the team are working individually and not as a team. What should the project manager do to resolve this? | Multiple Choice | Wait until some iterations are completed to intervene | Directly guide the team members on how to perform their tasks. | Allow the team members to remain in their former individual roles. | Facilitate a team-building meeting to help this issue. |  |  | D |  | 1
A project manager is leading a project that has been in execution for year. An experienced team member is performing well, but often disagrees with the project manager and refuses to implement their decisions. Part of the team supports the team member's defiance, while the other team members do not. What should the project manager do? | Multiple Choice | Conduct a performance review and define and document the goals for the team member | Clarify decisions and request that the project team follows the project manager's decisions | Remove existing ground rules and create new ground rules that support the project manager. | Understand what the team member wants and find possible opportunities to address it |  |  | D |  | 1
A new team member joins an agile team. In a previous role, this team member was a subject matter expert {SME). This team member often directs the team on how to solve problems based on previous experience. What should the project manager do first? | Multiple Choice | Let the new team member know that even if they know the answer, it is better to give the team a chance to solve their own problems. | Ask the new team member to size all the stories in the backlog SO that the rest of the team can focus on delivery. | Update the definition of done (DoD) to include a review by the new team member to ensure the best outcome of each deliverable. | Ask the new team member to create a wiki that the rest of the team can reference in the future for all questions. |  |  | A |  | 1
A project manager has heard about the large volume of emails the team receives each day, which prevents them from doing project work. One team member has stated that they would like to be able to access project-related information when needed. To what type of communication is the team member referring? | Multiple Choice | Mass communication | Pull communication | Push communication | Interactive communication |  |  | B |  | 1
A project manager is managing the development of a dental wire bending machine. The machine is compatible with the three most popular dental wires in the market, which covers 90% of the market. The prototype is now under testing for certification. The manufacturer of one of the three wires announced they will be producing a different wire that will be incompatible with the machine. This will result in a 25% loss of market coverage from the initially predicted 90% coverage. What should the project manager do? | Multiple Choice | Investigate the impact of this issue with the team and survey the market for alternative wires with similar characteristics. | Stop the project and Kick-off another project to apply alternative wires for the machine. | Meet with the wire manufacturer to secure enough of the existing stock for the machine. | Meet with the sales and marketing representatives and ask them to convince the wire manufacturer to reconsider. |  |  | A |  | 1
A project manager is managing a hybrid project. After attending an iteration review, a stakeholder tells the project manager that they are very busy and asks why these reviews are held so frequently. How should the project manager respond? | Multiple Choice | Record the issue in the issue log and escalate the conflict to the project sponsor for assistance | Explain to the stakeholder that the stakeholder engagement plan requires their attendance at all reviews | Negotiate a reduced review attendance with the stakeholder and update the stakeholder engagement plan to reflect this reduced attendance | Discuss with the stakeholder the benefits of the hybrid project and how frequent reviews lead to greater value and less rework |  |  | D |  | 1
A project manager has recently taken over a project and notices that a client team member often halts progress due to a lack of understanding of some project elements. The former project manager gave the new project manager a complete list of people to communicate with, and this client team member is not on it. What should the project manager do? | Multiple Choice | Update the communications matrix to ensure that client team member is included. | Speak with the client team member about the continuous delays during project meet | Submit a change request to cover extra hours associated with project, meetings. | Increase the project meeting frequency and duration to allow for the extra work required |  |  | A |  | 1
A project to implement a new online lending platform has started. After the first sprint, the project sponsor requested a change. What should the project manager do next? | Multiple Choice | Escalate the change request to the sponsor | Validate the work completed | Facilitate the update of the product backlog. | Inform the stakeholders of the change |  |  | C |  | 1
The project manager of a high-risk project is concerned about a delay in the schedule that might force the project to move its go-live date. What should the project manager do next? | Multiple Choice | Raise a change request to the change control board (CCB) to ask for funds to onboard new resources to expedite the project | Capture the risk in the risk register and monitor it to prevent it from becoming an issue by taking the proper response action. | Ask the sponsor to start a new project to support the existing project and help it meet the original time line | Ensure that the project meets the committed time lines as this is the core objective and purpose of the project. |  |  | B |  | 1
A project manager and project team developing a new product are discussing which work methods and tools to use to build the deliverable. What should the result of this discussion be? | Multiple Choice | A technology roadmap for creating similar deliverables in the future with the same tools | A detailed mitigation plan on the risks for each work method and the tools used | An agreed-upon work method and tools that should fit the business need and project constraints | A consensus that everything will run as anticipated once the tools and work methods are identified |  |  | C |  | 1
A project manager is in rapid development mode on a Joint application development module The company wants delivery to occur in two weeks. The module needs to be integrated With other modules on a similar timeline, but release management has a three-week backlog. What should the project manager do? | Multiple Choice | Speak to the stakeholders to resolve the bottleneck and see how the entire process can be streamlined | Have the team work toward the tighter deadline so that integration will be easier. | Push the team to deliver more so that the modules are developed and rolled out according to management's request | Speak to the team and slow the current pace to ensure the team is in alignment with the release |  |  | A |  | 1
A project manager created a contingency plan associated with a risk. The risk was realized, but the client insists on using a new workaround Instead. The requested workaround will introduce delays and require an additional budget. What should the project manager do? | Multiple Choice | Proceed with the approved risk response plan. | Mitigate risks associated with the workaround to avoid project delays | Request to use the management reserve to keep the schedule | Discuss the options with the client as part of the change control process |  |  | D |  | 1
A project manager works for a large manufacturing company with diversified domains. The project team often participates in change requests Recently, the change control board (CCB) deferred some requests and the project manager wants to communicate these requests to the stakeholders. What document should the protect manager use to communicate these requests? | Multiple Choice | Risk log | Backlog | Issue log | Change log |  |  | D |  | 1
A business analyst on the project meets the customer in the elevator and says that due to constant changes in requirements the development of the product will take more time than expected What should the project manager do? | Multiple Choice | Submit a change request to the change control board (CCB) in order to reflect the new requirements and longer timeline of the project | Explain that distribution or important news can only be done using traceable communication methods | Refer to the resource management plan to find out if more business analysts may be assigned to process the requirements changes | Point out to the project team and the customer that all information concerning the timeline of the project should be communicated by the project manager. |  |  | A |  | 1
During each phase of an ongoing project, one of the customer's engineering team members constantly disagrees with the project manager. The team member has no project authority but is consulted by top management about the Progress of the project. What should the project manager do first? | Multiple Choice | Review the stakeholder register to determine if the team member is on it. | Issue a change request to clarify the scope | Use soft skills to meet privately with the team member to align expectations. | Escalate the issue to the customer |  |  | A |  | 1
A project sponsor insists that the project scope for a new product launch should include two geographical locations. However, after the project scoping session was done, a project charter was completed and approved with one location only. What should the project manager do? | Multiple Choice | Ask the sponsor to increase the budget and schedule of the project to accommodate the additional scope. | Encourage the sponsor to start another project for the additional location so that the current project is not impacted. | Discuss with the sponsor that the project scope is approved and it is not possible to include two locations as it will affect the budget. | Assess the impact to the scope and submit a change request for approval of the two locations before including them in the scope of the project. |  |  | D |  | 1
A human resource (HR) acquisition process for a large project has recently changed. One major process change includes the approval of the financial manager and the recruitment manager. This change to the process implies longer processing. The project urgently needs new resources. What should the project manager do? | Multiple Choice | Review the project schedule to determine which technique will reduce the impact on project duration. | Adapt the resource management plan and ask for financial approval before sending it to the customer. | Ask the financial manager to delay implementation due to potential project delays and penalties. | Assess the impact of the change and review the project management plan for the next steps. |  |  | D |  | 1
An agile team is in the early phases of the development cycle for a project; however, theyhave already begun to deliver functionality to the customer. The team has identified risks to the project and are working on developing the mitigation strategy. What should the project manager do next? | Multiple Choice | Incorporate and prioritize the risks in the risk register according to impact | Determine if any of the new risks have any financial impact. | Implement the risk mitigation strategy according to the highest impact. | Escalate the risk to the project sponsor and steering committee. |  |  | A |  | 1
A customer's technical lead discussed a new feature with project manager. The project manager believes the new feature will boost performance significantly and adds it as a high-priority item in the sprint backlog. At the end of the sprint, all of the planned stories were not completed because the new feature took more rime. What should the project manager do next? | Multiple Choice | Agree with the project team to modify and delete some of the stories in the current sprint backlog. | Negotiate with the scrum master before adding the new story to the sprint backlog. | Receive an agreement from the product owner and add the new story to the product backlog. | Obtain approval from the project team and add the new story to the product backlog |  |  | C |  | 1
A company recently adopted agile to develop innovation projects. The project manager is experiencing problems with some team members who consider some agile ceremonies to be unnecessary . What should the project manager have done before the beginning of the project? | Multiple Choice | Conducted a survey to determine if the team was willing to adopt agile ceremonies on the current project. | Prepared an inception deck and clearly explained the purpose of agile ceremonies and their benefits to the project. | Discussed with the product owner and requested assistance by requiring the adoption of agile ceremonies. | Discussed with the project sponsor about convincing the team to adopt the agile ceremonies as part of their routine. |  |  | B |  | 1
A project has completed design activities ahead of schedule. Suddenly, the project manager is informed by a vendor that a deliverable may not meet the agreed delivery time frame due to a resource shortage. The internal team asked if they should continue to deliver as per the schedule. What should the project manager do? | Multiple Choice | Inform the project team that some of them will work for the vendor. | Discuss with the team the need for longer hours to minimize the impact. | Discuss with the project team alternative options to deliver as planned. | Inform the project team that they may proceed at a more relaxed pace. |  |  | C |  | 1
Project stakeholders are engaged in a discussion on how to achieve the best user experience in the design of a new application. The agile team is divided on the approach. The conflict is more of a collective disagreement than an outright conflict. What should the project manager do next? | Multiple Choice | Call a team meeting to have a formal discussion of the issue. | Apply appropriate conflict resolution techniques to solve the issue. | Engage in individual conversation with each team member. | Allow the team to work through it on their own unless help is needed. |  |  | B |  | 1
An organization is using a hybrid delivery approach for a business project. The product owner, the person who was also managing the project, was promoted to a more senior role. A new project lead has joined the project. Which artifact should the project lead use to ensure that the project benefits have been identified? | Multiple Choice | Product backlog | Business case | Statement of work (SOW) | Pareto chart |  |  | B |  | 1
A project manager is using an agile approach. During the sprint planning meeting. the product owner flagged a backlog item as high business value and easy to implement. However, the other team members identified a high dependency between this item and another item that is flagged as row business value and high complexity, What should the project manager do to support the backlog prioritization? | Multiple Choice | Support the team to move both items to the next sprint when the team will know more. | Facilitate the discussion until the team reaches an agreement about the two items. | Prioritize the item flagged as a dependency with low business value and high complexity. | Prioritize the item flagged as high business value and low complexity for this sprint. |  |  | B |  | 1
A project manager working on a unique project that is dissimilar to the project nature of the organization. The project manager is tailoring the artifacts for this new project. Who should determine which artifacts should be used in the project? | Multiple Choice | The project stakeholders should meet and determine the project artifacts to be used by the project manager and the project management team. | The project manager and project management team should use the standard project artifacts from the database. | The project sponsor should select the project artifacts that the project manager and project management team should use in the project. | The project manager and the project management team should select the appropriate artifacts for use in the specific project. |  |  | D |  | 1
The Development Team has chosen, together with the Product Owner, Items in the Product Backlog to develop in the Sprint. Who must determine how the Development Team should go about its work? | Multiple Choice | The Development Team | The function managers the Development Team reports to. | The Product Owner. | The ScrumMaster. |  |  | A |  | 1
A project manager Is leading a hybrid project and is collaborating with the client to develop the project contract. Some delays have been experienced due to unforeseen technical difficulties and new dependencies. However, the project manager Is optimistic about recovering the delays In the upcoming sprints. A key stakeholder asked the project manager If the contract deadlines can be met. What should the project manager do first? | Multiple Choice | Ask the stakeholder to remain calm and confirm that they are participating in all team meetings. | Study the contract terms and deadlines to ensure they are not under risk and confirm them with the stakeholder. | Clarify the current work progress. causes for delays. existing risks, and planned corrective actions. | Submit a request for extra time and budget related to the dependencies and technical difficulties. |  |  | C |  | 1
A project manager is assigned to a new project. The project is for a new product that the company wants to launch as soon as possible to test market readiness. The project is part of a large business transformation, and the objective is to open delivery channels for the new product. Which delivery approach should the project manager recommend? | Multiple Choice | An adaptive approach with loosely defined large epics. | An adaptive approach with clearly defined user stories. | A predictive approach with an experienced project team. | A predictive approach with clear acceptance criteria. |  |  | B |  | 1
A project team member identified a procurement ri.sk and sent an email to the project sponsor highlighting the ri.sk. The sponsor forwarded the email to the project manager asking for further details. After speaking with the sponsor, the project manager decided to take preventive action. Which document should the project manager review with their team? | Multiple Choice | Communications management plan | Quality management plan | Procurement management plan | Risk management plan |  |  | D |  | 1
A project manager is assigned to a global project with dispersed team members, Previously, when working with remote teams, the project manager observed that teammembers do not tend to produce quality work. What should the project manager do to ensure the project is completed on time with quality? | Multiple Choice | Arrange regular team meetings for the team to update one another on the progress of their assigned tasks. | Introduce the use of time sheets and ask team members to review and submit them regularly. | Meet with the team together and in one-on-one meetings to set clear, shared targets. | Encourage the team to participate in a peer evaluation activity by the end of the project. |  |  | C |  | 1
A government agency is developing a new connectivity policy. The assigned project manager is a famous economistwith international recognition. The team is eager to work with the project manager, but feels intimidated. The project manager realizes that a junior economist, whose tasks are behind schedule, is especially intimidated by the situation. What should the project manager do first? | Multiple Choice | Consider organizing paired work sessions for the junior and senior economists. | Evaluate the performance or the junior economist in the upcoming months. | Request to replace the junior economist with a more experienced economist. | Reassign some or the junior economist's tasks to other economists. |  |  | A |  | 1
A project manager has received feedback from stakeholders regarding poor communication about project progress. Weekly status reports were provided to the project management office (PMO), and the standard communications management plan was followed. What should the project manager do? | Multiple Choice | Perform a root cause analysis (RCA) of the existing communication approach. | Distribute hard copies of status reports and confirm that messages were read. | Ensure that all of the complaining stakeholders are on the distribution list. | Create a change request for implementing an online collaboration tool. |  |  | A |  | 1
Close to the end of a project. a customer claims that some deliverables have not been met and starts initiating change requests. What should the project manager do next? | Multiple Choice | Revise the project scope baseline. | Escalate the change request to the project sponsor. | Review the approved project charter. | Refer to the requirements traceability matrix. |  |  | D |  | 1
During the execution phase of a project, a new department has been created in the company, The manager of this department has requested to be involved in the regular project communications and reporting cycles. What should the project manager do? | Multiple Choice | Perform a stakeholder analysis and update the communications management plan to reflect the new situation. | Ask the project team members to include the manager in all of their communications regarding this project. | Suggest the manager contact the steering committee and project management office (PMO) to be included. | Inform the manager that only stakeholders identified in the communications management plan should be involved. |  |  | A |  | 1
A client wants to create an innovative software for the travel industry using an agile approach..,A project manager from the company was assigned to work on the details and estimates as requested by the client. What should the project manager do before sending the information to the client? | Multiple Choice | Analyze the tasks. provide estimates, include a prototype demo, and send to the client directly. | Work with the team to understand their views and add the appropriate dependencies and risks. | Put the tasks with estimates in the backlog and clarify that the project will not need any reserves. | Sequence the tasks with estimates and add standard risk reserves to use for software development. |  |  | B |  | 1
During a project meeting, the project manager expressed the importance of delivering reports on time. These individual reports will be consolidated into a single report. One of the team member's reports was not delivered on time and therefore the report could not be integrated with the other reports. This demonstrates a lack of teamwork and impacts project success. What should the project manager do to resolve this issue? | Multiple Choice | Discuss this matter during the project meeting. | Discuss it with the team member in confidence. | Assign the task to someone else on the team. | Include this item in the risk register. |  |  | B |  | 1
The team lead on a project has left the organization and management wants to promote engineer A to this position.The project manager is confident that selecting engineer A will add problems to the. project and believes that engineer B would better fit this role. The project manager discussed all of the arguments with management, but their decision remains unchanged. what should the project manager do? | Multiple Choice | Request management approval that engineer B will be promoted if engineer A fails in this role. | Coach engineer B to be prepared to perform this role if and when engineer A fails. | Promote engineer B instead since the project manager has the authority to make this decision | Help engineer A to become familiar with this new role and ensure engineer B stays motivated. |  |  | D |  | 1
During a project, the project manager finds an opportunity to reduce the project cost by completing a deliverable ahead of schedule with a minimal impact On project resources. However, the client has only been focused On the next milestone. How should the project manager approach this situation? | Multiple Choice | Evaluate whether the client's request will add extra features to the project deliverable. | Focus on the deliverable of the next project milestone as per the client's strict instructions. | Review the change management plan to discuss early benefits realization with the client. | Apply additional resources to realize the early deliverable and ensure the next milestone is achieved. |  |  | D |  | 1
A project manager is working on a multinational project that has more than 100 stakeholders. The project manager is concerned about the appropriate stakeholderparticipation and involvement level required for successful project delivery. what should the project manager do? | Multiple Choice | Perform a stakeholder assumption and constraint analysis. | Communicate with the stakeholders to find a solution. | Evaluate the stakeholder engagement assessment matrix. | Review the issue log with the project stakeholders. |  |  | C |  | 1
A company has started developing a new product. During execution, the project team notices that another competitor has launched a product with very similar functionalities and a cheaper market price, what should have been done differently to avoid this scenario? | Multiple Choice | A minimum viable product (MVP) should have been released to get feedback from the market. | More backlog refinement meetings should have been scheduled | The Kanban method should have been utilized to optimize the work in progress (WIP). | An iterative life cycle approach should have been adopted. |  |  | A |  | 1
During the sprint planning of a project, the team members have a disagreement about the comparative size of the backlog items and if they would t into the next sprint. Considering a hybrid approach, what should the project manager do? | Multiple Choice | Remove the items from the product backlog since the size couldn't be estimated. | Ask an external technical leader to provide input and plan the sprint | Facilitate the discussion so that the team members can reach a consensus. | Make the decision about the backlog items based on what makes more sense. |  |  | C |  | 1
A project manager is leading a large public project that will have a high impact on the town's citizens. How should the project manager define the different requirements? | Multiple Choice | Include only the key requirements and keep the stakeholders informed about scope decisions. | Add only the opinions of the team. because they know the objectives of the project. | Include only the common requirements of each stakeholder group in the project goals. | Analyze the interests and influence of stakeholders and evaluate their requirements. |  |  | D |  | 1
A project manager is leading a project that is in the execution phase. Due to a company reorganization, some key project team members are likely to leave the project.What should the project manager do next? | Multiple Choice | Determine the impact to the project and implement mitigations per the project management plan. | Start looking for replacements as soon as possible to help prevent any schedule slippage. | Discuss this issue with the affected team members and support them during the transition. | Engage with the project sponsor to ensure that this change does not affect the project execution. |  |  | A |  | 1
A project manager is leading a global project with resources spread out in different locations. The stakeholders have different interpretations of the requirements. The project manager is concerned about scope creep. Which action should the project manager take to control the scope? | Multiple Choice | Accept only those changes to requirements that provide additional value to the project. | Accept only those changes that are approved by the change control board (CCB) prior to being implemented. | Reject all changes that will increase the budget or increase the time line of the project. | Ensure that all key stakeholders agree to the project deliverables and there will be no need for changes. |  |  | B |  | 1
The project sponsor reports that a key stakeholder is complaining about performance differences in the metrics reported by the project manager, which gives the impression that the project is out of control. The project manager has been providing the project's status according to the agreed-upon communications management plan. This key stakeholder, however, seldom attends the status report meetings. What should the project manager do first to address this situation? | Multiple Choice | Use the contingency reserves to implement fast tracking and improve the schedule key performance indicators (KPls). | Review the resource breakdown structure (RBS) to request the main stakeholder's manager to replace the stakeholder. | Evaluate the communication needs to discover the gaps and adjust the original plan if needed. | Provide evidence to the project sponsor that the project is on track and the communications have been sent. |  |  | C |  | 1
A project lead is working on an agile project to build the team's vision, including the decision-making process. It was decided that the team will vote on items, and if 90% of the team agrees on a decision, then it will be carried forward. At the very first technical design meeting, the team makes a decision that the project lead strongly disagrees with. How should the project lead proceed? | Multiple Choice | Refuse to let the team proceed with the work based on their decision. | Take the technical team lead aside and try to persuade them to change their vote. | Set up a meeting with the project champion and ask them to intervene. | Note the reasons for the disagreement and let the team proceed. |  |  | D |  | 1
An agile team is working on a 2-week sprint to deliver business value. About 1 week after the sprint starts, the team members do not feel confident about the product increment they are building. They do not want to wait until the end of the sprint and want. to validate the product increment with the product owner now. What should the project manager do to mitigate this risk? | Multiple Choice | Address the issue as part of the retrospective. | Schedule an additional interim demo with the product owner. | Extend the sprint end date in anticipation of feedback from the product owner that will require extra work. | Ask the team to work overtime toward the end of the sprint to meet the original sprint end date. |  |  | B |  | 1
A company is starting a critical project witha strict deadline. During the first planning meeting, the team realizes that the list of requirements has too many items to allow on-time delivery. What should the project manager do first? | Multiple Choice | Update the risk register and present a contingency plan to meet the deadline. | Increase the capacity of the team to finish the project on time. | Ask the team to propose a minimum viable product (MVP) to meet the date. | Suggest to the customer to reduce the backlog to meet the date. |  |  | C |  | 1
A senior project manager has included a junior project manager as part of the project team. During a coaching session, the junior project manager asks the senior project manager how to be efficient and reduce rework. How should the senior project manager respond? | Multiple Choice | Schedule daily meetings with key stakeholders to assess the effectiveness of the project management plan. | Assign project tasks to the team regardless of their skills to accomplish the project schedule. | Use a work breakdown structure (WBS) to create a project schedule based on the project and resource requirements. | Monitor resource allocation to ensure that team members work 8 hours per day. |  |  | C |  | 1