## Exam Data
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
You are managing an e-commerce-enabled website. You have recommended the Agile project management approach to the client and they are happy with any management approach as long as they receive a working product. You and your team have a tough decision to make regarding sprint durations. A sprint duration of two weeks would add a lot of pressure on the team as complex requirements will be tough to build in a single sprint. A sprint duration of six weeks would make the project less Agile but the project might get finished early as the customer won't get to see many prototypes. What sprint size should be selected? | Multiple Choice | A sprint size needs to be determined that maximizes customer value and satisfaction. | Four weeks should be selected as that is the average of two numbers. | Two weeks should be selected since Agile Manifesto mandates frequent delivery of working software. | Six weeks should be selected since the project would get finished early and satisfy the customer. |  |  | A |  | 1
A project manager is leading a project to design and develop a new cutting edge computer system, which is in the second of five phases. The project is running behind schedule and significantly over budget due to a force majeure. The project is being conducted internally to maintain control over the proprietary technology which will provide a competitive advantage. The project has reached a phase gate. What is the purpose of performing the phase gate? | Multiple Choice | Adjust the schedule and cost baselines based on past performance | Obtain customer acceptance of project deliverables | Determine how many resources are required to complete the project according to the project baseline | The project's performance is compared to the business documents to determine if the project should be Continue to the next phase, End the project, or Repeat the phase |  |  | D |  | 1
Two team members have been arguing with each other openly at meetings. Each team member individually spoke with the sponsor directly and made decisions without Informed the project manager. What two actions should the project manager take? Choose two. | Multiple Response | Ask the team members to work it out themselves. | Discuss this situation with other project managers and ask for advice. | Reiterating ground rules at the next meeting and ensure that all team members are clear about these rules. | Discuss the behavior directly with their managers and request them to correct the behavior. | Address the behavioral issues with each team member. |  | CE |  | 1
A scrum team is midway into a sprint when the project sponsor approaches the scrum master and requests that a new, urgent, and potentially complex mandatory compliance-related requirement should be developed immediately in the current sprint. The sponsor stresses that if the requirement is not implemented, the entire project may be canceled. What is the scrum master's best response? | Multiple Choice | Add the requirement to the current sprint backlog and direct the team to start working on it immediately. | Discuss the requirement with the product owner, and let them make a decision, including sprint cancellation. | Submit a change request to update the scope baseline and add the requirement to the requirement traceability matrix. | Add the requirement to the product backlog and request the product owner to review the requirement after the sprint is over. |  |  | B |  | 1
During sprint execution, one of the developers requires clarification about the acceptance criteria for a particular task. What should the project manager do to obtain the Information required by the developer? | Multiple Choice | Work with the product owner to clarify the requirements. | Request directions for the project sponsor. | Request support from the development manager. | Send an email to the customer requesting clarification. |  |  | A |  | 1
During a sprint review, the product owner rejects a deliverable stating that it does not meet the acceptance criteria. The quality assurance team, who verified the deliverable as part of the Control Quality process, argues that there is nothing wrong with the deliverable and that it should be accepted. The product owner disagrees and rejects the deliverable. What is the project manager's best course of action to ensure that this type of misunderstanding does not recur? | Multiple Choice | Fire the team member who causes the issue | Submit a change request to modify the Control Quality process based on the recommendations from the team and product owner | Discuss the problem during the next daily scrum meeting and resolve the misunderstanding between the product owner and team | At the upcoming sprint retrospective meeting, facilitate an exercise to identify the underlying cause of the misunderstanding |  |  | D |  | 1
A large project is affecting the neighborhood in which it is located. The neighbors are not satisfied with the project and their resistance to the project may affect the project deadline. What two actions should the project manager take'? (Choose two) | Multiple Response | Set up a meeting with neighborhood representatives to win their cooperation | Send letters to the neighbors and ask them kindly not to disturb the project | Analyze the situation and find out what is causing the neighborhood's negative attitude | Ask the customer to extend the project deadline to allow time for conflict resolution | Ask the mayor of the city to use their authority to stop neighborhood resistance |  | C |  | 1
How will the selection of a predictive project life cycle shape the way the project is carried out? (Choose three) | Multiple Response | A single final product will be delivered at the end of the project. | Cost and time will be fixed, and the project scope will be allowed to vary. | The requirements will be determined upfront before the project execution begins. | Business value will be delivered to the customer frequently rather than just at the end of the project. | Changes will be constrained to the extent possible. |  | ACE |  | 1
A project manager for a large multiyear project has a project with diversified stakeholders from various geographical areas. Recently the project manager encountered an Issue with stakeholder engagement. Which two tools should the project manager use to determine the underlying reason for why engagement is not having the planned effect? | Multiple Response | Issue log. | Open space meeting. | Ishikawa diagram | Communication management plan. | Five whys. |  | CE |  | 1
After the project charter's approval, the projectmanager needs to work on detailed project requirements,constraints, and assumptions with stakeholders. However,not all of the stakeholders are immediately available for ameeting in the short term. What should the project managerdo in order to gather the information needed fromstakeholders? | Multiple Choice | Conduct a meeting to build the project management plan with the stakeholders who are available. | Email, call, or meet with each stakeholder separately to obtain their input | Escalate to the project sponsor that not al stakeholders are available for a meeting | Meet with the project management team to build the project management plan before consulting stakeholders. |  |  | B |  | 1
A project is being executed. The project's life cycle is defined as predictive; however, a major deliverable will be handed over incrementally to the customer. The assigned resources are experienced and reliable and are willing to make decisions that the project manager used to make after each incremental delivery on other projects. What should the project manager do? | Multiple Choice | Consult the product owner about letting the resources make decisions | Schedule a steering committee meeting and obtain their approval on the request. | Support the decisions of the team and transfer the decision-making responsibility to them. | Inform the team that although this is a hybrid environment, the project manager must still be responsible for making decisions. |  |  | C |  | 1
A project manager works in a matrix organization and is managing an internal software development project that is intended to reduce conflicts in the company's internal tracking system. During development, the project manager is informed that the software has to account for an unexpected change to government accounting requirements. The development team was able to make the change with no additional cost; however, the project manager notices that the testing costs are beginning to exceed the testing budget. What should the project manager do? | Multiple Choice | Conduct a cost-benefit analysis to determine if the funds can be reallocated from the development team. | Ask the project sponsor to allocate funds from the contingency reserve to fund the additional testing. | Submit a change request to the cost baseline through the governance process to fund the additional testing. | Update the basis of estimates and the cost management plan to track the additional funding required for testing. |  |  | C |  | 1
A project manager is leading a project with strict time constraints. In team meetings, one of the team members is always silent. The project manager determines that this team member is not knowledgeable about the technology solution. The project manager is concerned that this problem will impact productivity. What should the project manager do? | Multiple Choice | Assign an experienced team member to work with this member on a daily basis in order to become knowledgeable about the technology. | Let this team member understand the urgency and encourage them to spend extra time to become knowledgeable about the technology. | Let the team lead the meeting discussions so that every member has a chance to prepare and speak up. | Arrange formal training for this member to gain sufficient knowledge to reduce the impact on team performance. |  |  | D |  | 1
In a fixed time and budget project the customer wants the development of a core component to be based on agile practices, as the final scope of the requirement has not yet been fully developed. The project manager is participating in contract development with the sales team and wants to ensure that development costs do not impact the profitability of the project. Which two controls should the project manager incorporate into the contract to specifically address the development of the core component? (Choose two) | Multiple Response | Provide alternatives to scope change at specific project phases within the contract. | Limit the number of iterations for development in the contract. | Tier the contract for fixed and agile components | Establish a governance committee to review the contract delivery | Require that only internal resources be utilized for this project |  | BE |  | 1