## Exam Data
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
The city has decided to build a new tram station The project will include various approaches The construction and infrastructure work will be accomplished using a predictive life cycle while software will be developed using an iterative life cycle Some neighbors are resisting the project have been asking the mayor to stop the project, and are threatening legal action. What two actions should the project manager take? | Multiple | Have a meeting with the mayor and explain the importance of the new train station to the city. | Publish information on the city's website about the benefits that the new tram station will bring | Register this situation as a risk and develop a mitigation plan | Conduct regular meetings with the neighbors to get their buy-in for the project | Discuss with the construction team alternatives on moving the new train station to another location. |  | AC |  | 1
Your team members told you they are overloaded with many tasks. They are saying they have many tasks assigned to them besides the main tasks in the project. You promised them that you would clear the overloaded tasks. You are a Project manager in: | Single | Weak Matrix Organization | Projectized Organization | Strong Matrix Organization | Balanced Matrix Organization |  |  | C |  | 1
You are a project manager working in a multinational company. You have Just been assigned to initiate a project in a new country where your company has no presence. To develop an appropriate Implementation strategy, what should beconsidered first? | Single | Evaluate the environmental and regulatory factors and identify highlevel risks and assumptions | Assign project resources from the new country to mitigate the risk. | Ask the sponsor to work on another project. | Identify and monitor the risks because your company doesn't have lessons learned for this country. |  |  | A |  | 1
In a hybrid project, the customer has issued a contract that specifies the deliverables for each quarter. The customer wants to show their stakeholders a tangible outcome in the first quarter and wants to move the second milestone to the first quarter. The project manager explains to the customer that it is not feasible unless the requirements for the second milestone are changed. Which two actions should the project manager take? Choose two | Multiple | Go back to the development team and discuss which second milestone requirements can be performed in the first quarter. | Convince the customer to leave the second milestone in place and not change it. | Tell the customer that moving the milestone has a very high impact on the cost of the project. | Escalate the issue to upper management to resolve the problem and suggest a plan. | Ask the customer for their priorities regarding the requirements for the second milestone. |  | BE |  | 1
A project manager is assigned to a multiyear project. During project execution, the customer delegates a new representative who contacts the project manager directly with a concern about their participation in status meetings. The representative wants to contact team members directly. What should the project manager do next? | Single | Send the new representative the approved project management and communications management plans. | Meet with the project sponsor to discuss how to incorporate the new representative in the project. | Meet with the new representative to determine their understanding of the project and address their concerns. | Reach out to the customer directly for assistance in incorporating the new representative into the project management plan. |  |  | C |  | 1
In a frequently changing project, the project manager discovers a customer requirement change during a daily meeting. What should the project manager do? | Single | Escalate to management for approval since the change was not included in the original requirements. | Validate the requirement change with the product owner and development team before redefining the scope. | Give the change to the scrum master to investigate how much additional effort the change will require. | Tell the customer that the requirement change will be put into the next project phase if management approves. |  |  | B |  | 1
A project manager is scheduled to meet with a client for their weekly risk management meeting. The project manager observed that one of the tasks which had external dependencies is delayed by one week. The project manager knows this will have an impact but does not know the exact details. What two things should the project manager do? (Choose two) | Multiple | Wait for the client to raise a concern and collect more information. | Discuss the issue with the external supplier's authority. | Review the lessons learned from similar past projects. | Gather additional information and estimate the impact | Update the risk log and bring this up in the meeting with the client. |  | DE |  | 1