## Exam Data
Question | Question Type | Option A | Option B | Option C | Option D | Option E | Option F | Right Answer | Feedback | Points | Category | Labels
Mark has recently been assigned as the project manager for a new shopping mall construction project. Lucy suspects that there are materials In the building that may be a serious health hazard. What should Lucy do? | Multiple Choice | Implement the risk response plan. | Hire a hazardous materials expert to investigate. | Assess the risk and update the risk register. | Perform integrated change control |  |  | B |  | 1
In the middle of the construction of a new water treatment plant, the government established more stringent water quality requirements for treatment plants. What should the project manager do next? | Multiple Choice | Ask the project sponsor to update the project charter | Submit a change request to update the quality management plan | Update the quality management plan due to the legal requirement | Update the scope baseline to reflect the changes |  |  | B |  | 1
During a software project, a project manager notices that the coding quality for one developer is statistically lower than another developer assigned the same task. Which tool should the project manager use to trace the problem's source back to Its actionable root cause? | Multiple Choice | Scatter diagram. | Histogram | Ishikawa diagram. | Control chart. |  |  | C |  | 1
A project team is working on a risk response strategy by evaluating every risk and coming up with suitable response strategies. However, one particular risk with a negative impact cannot be avoided or mitigated. Furthermore, there is no way to transfer risk by outsourcing or buying insurance. What is the best the team can do about the risk? | Multiple Choice | Revisit the Risk Response Strategy | Treat it as a secondary risk and update it in the Risk Register | Accept the risk | Share the risk by allocating ownership to a third party |  |  | C |  | 1
A company has recurring quality issues with one of its sole source suppliers. A new project will incur significant penalties from the customer if deliverables are late What should the project manager do? | Multiple Choice | Review incoming inspection reports and quality logs | Identify high- level risks prior to developing contingency plans | Negotiate with other vendors with better quality-control methods. | Escalate the issue to top management |  |  | B |  | 1
Before initiating any such project, the value of the project to the organization must be determined. Which of the following is the most critical factor to be considered in such a scenario? | Multiple Choice | Net Present Value CNPV) of the projects. | Alignment with the strategic goals. | Investment requirement | Internal Rate of Return (IRR) of the projects |  |  | B |  | 1
You are creating your activity fist, but only for the next two portions of the project. The rest of the work you are leaving at the work package level. What approach are you using? | Multiple Choice | Brainstorming | Bottom up | Predictive life cycle | Progressive elaboration |  |  | D |  | 1
If the project was terminated early, why would the project manager insist that the team perform the Close Project or Phase process? | Multiple Choice | To document lessons learned so mistakes won't be repeated in future projects. | To make sure everyone knows that the reason for project termination was his fault or the fault of the team. | To document the reasons why the project was terminated early, and how to transfer the finished and unfinished deliverables to others. | The project manager should insist this is a waste of the team members' time since no one wants the project or its output any longer. |  |  | C |  | 1
A company's PMO has been trying to implement an adaptive approach and a project manager has been asked to use adaptive tools in their next project. This is not the first time the request has been made, and the previous project failed when adaptive tools were implemented. What should the project manager do? | Multiple Choice | Bring third-party company to develop and implement a hybrid framework for this specific project. | Conduct individual interviews with key stakeholders in order to understand all concerns then prepare a communication management plan. | Recommend to the PMO that it's not the right time to start implementing adaptive tools in projects. | Prepare a change request and seek approval from the steering committee regarding the new project framework |  |  | A |  | 1
Which of the following techniques used in adaptive lifecycles helps in minimizing scope creep? | Multiple Choice | User stories | Iterations | Time-boxing | Product owner |  |  | C |  | 1
In an agile project, the project manager finds that the team members are involved in several Different projects due to budget constraints. As a project manager, what should you do? | Multiple Choice | Brainstorm with the team members on how they can deliver on multiple projects within the given budget | Provide an incentive plan so the team members will work more unaccounted hours on multiple projects | Instruct the team members to spread evenly across projects so mistakes will not occur within the current budget. | Request the project sponsor prioritize and if necessary, allocate additional budget so the team can work on a single project |  |  | D |  | 1
A project manager is part of an organization that is assessing the use of agile delivery approaches. A new project management office (PMO) manager who had a bad experience with a Serum approach recommended that the project board replace Serum with a predictive approach. What should the project manager do? | Multiple Choice | Review the communications management plan to identify new stakeholders. | Define a risk management plan for the new approach, as needed. | Review the benefits realization plan to include the cost of the change. | Define a project management plan for the new approach, as needed |  |  | C |  | 1
A project team has finished its first iteration out of six. The iteration's delivery performance (velocity) was 50%. During the iteration retrospective, the team realizes that the complexity of the work was underestimated. What should the project manager do? | Multiple Choice | Ask the technical manager to help the team with the issue. | Meet with the team to review internal actions to resolve the situation. | Ask to replace some team members with more experienced ones. | Update the issue log and escalate it to the project sponsor. |  |  | B |  | 1
While a project manager is trying to build the first baseline for a project, a change request is being sent from one of the functional managers. What should the project manager do? | Multiple Choice | Apply for a formal change control board (CCB) approval. | Analyze the impact of the change request on the project. | Discuss this with the functional manager and related parties. | Reject the functional manager's change request immediately. |  |  | B |  | 1
A major public-transportation construction project is aimed at significantly reducing emissions. The project has been severely delayed due to non-compliance with environmental codes and bylaws. What should the project manager have done to prevent this? | Multiple Choice | Mapped environmental compliance requirements, identified risks to achieving them, and prepared mitigations. | Approached the regulator for a partial waiver in light of the environmental importance of the project. | Appointed a senior environmental compliance officer to report directly to the project manager. | Incorporated sufficient schedule reserves based on similar delays in past projects. |  |  | A |  | 1
A project team is conducting sprint planning. Based on the estimated effort, only 95% of the items included in the sprint may be delivered. The product owner asks the project manager for advice on how to prioritize the backlog items. What should be used to prioritize the backlog items? | Multiple Choice | Estimation accuracy | Business value | Risk to delivery | Technical complexity |  |  | B |  | 1
Project acceptance criteria include on-site training for the new users of a system. Due to unforeseen circumstances, all team members have to work remotely for an indefinite period of time. What should the project manager do? | Multiple Choice | Reschedule on-site training to online sessions. | Cancel al of the on-site training sessions. | Create a risk and assign remediation actions. | Document the project issue and provide options |  |  | D |  | 1
Travel restrictions are suddenly imposed during a project's execution. The team members reside in different geographic locations. What should the project manager do next to address this issue? | Multiple Choice | Obtain and implement the sponsor's recommendations for a solution. | Halt al processes until procurement and implementation of solutions are completed. | Place a hold on activities until the team can resume the work on-site. | Ask the team members to proceed independently while examining needs and alternatives. |  |  | D |  | 1
During the Implementation phase, the project manager identifies a new project activity that will not affect the project end date. What should the project manager do next? | Multiple Choice | Ask the sponsor to approve the new activity. | Create a change request. | Update the schedule baseline and Begin working on the new task immediately | Update the change log and update the schedule baseline |  |  | B |  | 1
A project team member identifies a simple change that will improve product quality without impacting the project budget. What should the project manager do? | Multiple Choice | Have team members include it in their assignments as quickly as possible. | Meet with the team member to assess the impact, and follow the change control process | Ask the sponsor for their advice regarding the suggested change. | After reviewing the change, include it in the quality management plan. |  |  | B |  | 1
A new government regulation requires financial resources to be added to a project Due to this regulation, A new key stakeholder request to add another project activity What should the project manager do? | Multiple Choice | Use funding allocated to other activities to execute the key stakeholder's request. | Document the request from the key stakeholder and perform the change request procedure | Execute the new activity because it was requested by the key stakeholder. | Update the schedule to include the new activity because it was requested by the key stakeholder. |  |  | B |  | 1
Which of the following responsibilities is NOT one of the Scrum Master's | Multiple Choice | Assigning tasks to team members | Facilitating meetings | Reminding the team of the process | Removing impediments |  |  | A |  | 1
Which of the following main events are defined by the Scrum Framework? | Multiple Choice | Sprint Planning Meeting, Sprint Retrospective Meeting Sprint Review Meeting, and Daily XP Meeting. | Sprint Planning Meeting, Sprint Retrospective Meeting Sprint Review Meeting, and Daily Scrum Meeting. | Sprint Planning Meeting, Sprint Retrospective Meeting Sprint Review Meeting, and Daily Kanban Meeting. | Sprint Planning Meeting, Sprint Retrospective Meeting Sprint Review Meeting, and Mid-Sprint Status Review Meeting. |  |  | B |  | 1
An agile team is tasked with the development of a robot. The project manager wants to ensure that before the actual robot is built, the team receives early feedback on requirements and adapts the design accordingly. Which of the following should the project manager use to achieve that goal? | Multiple Choice | Business case | Checklists | Design review | Prototyping |  |  | D |  | 1
At the end of an iteration, the product owner rejects the work items developed and provides feedback. What should an agile team do to avoid this situation in the future? | Multiple Choice | Ensure the product owner attends daily standups to understand the current status. | Ensure the product owner is part of daily agile team activities and provides feedback. | Document the product owners' feedback in the retrospective session. | Schedule frequent backlog refinement sessions with the product owner to clarify acceptance criteria |  |  | C |  | 1
There is a conflict between two members on how they complete a task. The conflict is not yet escalated to the project manager and there is no impact to the project. What should the project manager do? | Multiple Choice | Ask the functional managers to get involved and facilitate a resolution. | Reassign both resources to different projects. | Allow the project team members to find a resolution to their conflict. | Help facilitate a satisfactory conflict resolution |  |  | C |  | 1
One of your project team members doesn't finish his tasks on time. As a project manager, what should you do next? | Multiple Choice | Meeting with the project team members and evaluate the impact on the project. | Conduct One-on-One Meeting with the team member | Schedule training sessions for the team member to optimize his performance. | Release a team member |  |  | B |  | 1
As a project manager, you are leading a software development project as a result of observation and conversation, you notice some of the team members need to improve their skills. What should you do FIRST? | Multiple Choice | Update Cost Baseline | Acquire new members | Review the Resource Management Plan | Schedule training sessions for the team member to optimize his performance. |  |  | C |  | 1
Situational Awareness is a key interpersonal skill for all effective project managers and means knowing what is going on around you and being able to quickly switch your focus. What another skill is often used in conjunction with Situational Awareness where you the project manager, have to be persuasive in expressing your point and position In order for your project team and stakeholders to react quickly to changing project priorities? | Multiple Choice | Negotiation | Leadership | Conflict Management | Influencing |  |  | D |  | 1
Your project is very complex and due to a scope change, you need a few additional experts, which you did not think of earlier. You request that your company provide you with some experts for consultancy work. Although your company has provided you with those experts, they are located in a different geographical location. In this situation, how will you get their Input? | Multiple Choice | Recruit new members with same skills | Create a virtual team | Ask management to bring them to you | None of the above |  |  | B |  | 1
During project execution, a project manager learns that a team member's functional manager believes they shouldn't execute a certain task. What document should the project manager review to resolve this? | Multiple Choice | Organizational chart | Resource management plan | RACI (responsible, accountable, consult, and inform) chart | Work breakdown structure (WBS) |  |  | C |  | 1
Two team members on your project often disagree. You need a conflict resolution method that provides a long-term resolution. You decide to use which one of the following approaches? | Multiple Choice | Compromise | Smoothing | Problem solving | Withdrawal |  |  | C |  | 1
While you are in one of the first meetings for your new project that you have been assigned to early, two team members were discussing new ideas that each one thinks is correct and their opinion is the best for the project. You didn’t interact or cut the discussion, as you know thisis a normal discussion in this phase, which is? | Multiple Choice | Storming | Supporting | Performing | Norming |  |  | A |  | 1
A project manager wants to recruit another team member to replace an architect who resigned. What document should capture this change? | Multiple Choice | Ground rules | Project management plan. | Responsibility assignments matrix (RAM) | Organizational process Assets. |  |  | C |  | 1
A conflict appeared between two members of your team, and the conflicts began to affect the entire project team.The team's morale has become low. As a project manager, what should you do? | Multiple Choice | Ask the team members to solve the conflict by themselves | Escalate the problem to the HR department. | Interfering for solving the problem immediately | Do nothing |  |  | C |  | 1
You are a project manager for StecoCompany. Two team members come to you with a dispute regarding who will perform and report the status of a particular task. To resolve the conflict, which document will you refer to? | Multiple Choice | Functional manager | Responsible, accountable, consult, and inform (RACI) matrix. | Project sponsor. | Stakeholder register |  |  | B |  | 1
Your project expense has increased in the last quarter due to the required office space for personnel and some of their travel. What can you do from a resource management planning perspective to address this? | Multiple Choice | Plan to incorporate a virtual team environment, if not done already | Bring all project team members to work from one location | Reduce the travel and office equipment cost | Use video conferencing and web based meetings |  |  | A |  | 1
Two of your team members have come to you due to a difference of opinion between them. What is the best way to resolve this situation? | Multiple Choice | When one of them backs out due to frustration | When one of them is very flexible to accept the other person's opinion in front of you | By providing your opinion of who is right | By understanding the needs of both and guiding them towards successful resolution and their full satisfaction |  |  | D |  | 1
You are planning for project resources and have created a table showing individual roles for various tasks in the project. What sort of representation is this called, from a resource planning perspective? | Multiple Choice | An OBS | A RACI chart | A project organization chart | A text based format of an organization chart |  |  | B |  | 1
A customer has been consistently late with approvals on design documentation. George, the project manager, has raised the subject in the past, but the practice of delayed approval has not changed. George has been documenting the delays. Which conflict resolution technique is he following? | Multiple Choice | Collaborating | Smoothing | Withdrawal | Compromising |  |  | C |  | 1
The project team members are in conflict are not collaborative and differ in opinion on the architecture. Which of the following phases of Team Development are they in now? | Multiple Choice | Forming | Norming | Performing | Storming |  |  | D |  | 1
Your project team members have Just started to work together and are now adjusting their work habits and behaviors to support each other. Which stage of the Tuckman ladder has your team Just entered and Once the current stage ends, what is the next stage? | Multiple Choice | The Current stage is Forming and the next stage is Storming | The Current stage is Forming and the next stage is Norming | The Current stage is Norming and the next stage is Performing | The Current stage is Performing and the next stage is Adjourning. |  |  | C |  | 1
You are a project manager of a company, and your project is currently in the execution phase. One of your project teams leave the site early at 3:00 pm Friday and mistreats his colleagues. You would like to establish clear expectations regarding the acceptable behavior of the team member. To avoid such situations, you should create: | Multiple Choice | Team-building activities | Management skills | The team charter | Interpersonal skills |  |  | C |  | 1
A project manager notices that there is limited participation and contribution from a new team member . What should the project manager do? | Multiple Choice | Discuss the situation with the project sponsor. | Review the roles and responsibilities of each team member. | Write a complaint to the human resources department. | Discipline the new team member. |  |  | D |  | 1
A project to develop a new retail banking product is in progress. The project has fallen behind schedule because team members are tacking motivation. What should the project manager do to motivate the project team? | Multiple Choice | Offer recognition and rewards. | Apply creative problem solving. | Delegates the responsibilities. | Use coaching and monitoring skills. |  |  | A |  | 1
During regular team meetings, the project manager notices that there are clear signs of conflict and Issues related to unclear task assignments and ownership. What should the project manager do to address this? | Multiple Choice | Change the structure of the regular project meetings to improve communication. | Investigate possible ways to improve team collaboration and morale. | Meet individually with team members to understand the conflicts and issues. | Define and obtain agreement on a responsible accountable, consult, and inform RACI Matrix. |  |  | D |  | 1
The project manager for a virtual team is struggling to track progress and productivity because the team is spread out over several time zones. What should the project manager do to enhance communication? | Multiple Choice | Establish an information-sharing portal. | Create and update the issue log. | Update the lessons learned register. | Set up a Kanban board . |  |  | A |  | 1
One month into a 12-month project., a vendor informs the project manager that required project equipment will be delayed. After further investigation, the project manager learns that this vendor has a reputation for underperforming. What should the project manager have done to prevent this? | Multiple Choice | Reviewed the lessons learned documents from other projects | Included a contingency buffer in the schedule baseline | Check the updated risk register and issue log | Added a backup vendor to the vendor list |  |  | A |  | 1
A stakeholder who was incorrectly classifiedas a supporter is now reluctant and the project manager becomes worried. What should the project manager do more carefully in future projects? | Multiple Choice | Conduct a meeting with senior management | Create the stakeholders engagement assessment matrix | Identify stakeholders. | Develop interpersonal skills to manage stakeholder expectations |  |  | B |  | 1
Kevin has assigned as a project manager in a multinational company to implement new software that will impact several departments. To guarantee alignment of stakeholder expectations with the final product, what should Kevin develop? | Multiple Choice | Stakeholder engagement plan. | Business case | Resource breakdown structure (RBS) | Stakeholder engagement assessment matrix. |  |  | A |  | 1
One of the factors in making a project successful is stakeholder engagement level. Which of the following is the characteristic of a supportive stakeholder on a project? | Multiple Choice | Aware of potential impacts and supportive to change | Unaware of potential impacts | Actively engaged in project success | Aware of potential impacts but resistant to change |  |  | A |  | 1
A project is on its fourth iteration out of six. During iteration planning, a team member informs the project manager that their computer is not working. What should the project manager do next? | Multiple Choice | Update the issue log and escalate the problem to the product owner. | Facilitate a priority resolution of the issue with the IT department. | Suggest that the team member contact the IT department. | Ask the other team members to step in and do the work. |  |  | B |  | 1
During the early phase of a project, the requirements documentation was not approved. It was identified that the leader of a user party was not included in any of the requirements collection communications. Which of the documents was likely missed or outdated? | Multiple Choice | Stakeholder Register | Project Charter | Risk Register | Business Documentation |  |  | A |  | 1
A key stakeholder in your construction project has recently resigned from his duties due to personal reasons. What should you do next as part of stakeholder management? | Multiple Choice | Initiate an investigation into his resignation | Remove all changes suggested by the stakeholder | Update Stakeholder Register | Contact the sponsor |  |  | C |  | 1
You are the project manager on an industrial design project. During project execution some of your stakeholders raised concerns regarding poor project communications management. You are shocked to hear this since you have left no stone unturned when preparing the project management plans, especially the Communications Management Plan. You believe that the stakeholders are being unreasonable. In this situation, who is now responsible for managing these stakeholders' expectations? | Multiple Choice | Project Manager | Project Team | Project Sponsor | Project Stakeholders |  |  | A |  | 1
A project is six months into its nine-month projected duration, and the project manager is reporting that the project is at least three months behind schedule because certain key stakeholders were resistant to any changes that might occur as outcomes of the project. What might have been done differently during project planning to have avoided this situation? | Multiple Choice | Establishment of a more robust communications management plan | Better execution of the Manage Stakeholder Engagement process | Creation of a comprehensive stakeholder register | Development of a stakeholder engagement assessment matrix |  |  | D |  | 1
A recently appointed project manager is in constant conflict with a senior manager. Since this is not ideal for the team, the project manager wants to resolve this. What should the project manager do? | Multiple Choice | Request scheduled face-to-face meetings with the senior manager. | Enlist the help of a neutral mediator. | Seek guidance from the other project managers. | Escalate the issue to the project sponsor. |  |  | A |  | 1
A project manager focuses on systems and structure to accomplish project goals. As a result, the project manager has a strained relationship with the project team. Although the current project is trending to meet project objectives, excessive turnover of the project team threatens the project. For self-improvement, what type of skills should the project manager spend time developing? | Multiple Choice | Management skills | Communication skills | Leadership skills | Operational and problem-solving skills |  |  | C |  | 1
An agile team has been working overtime for the last few iterations. The project manager has decided that from now on the team should maintain a 40-hour workweek. What is the most likely reason behind the project manager's decision? | Multiple Choice | To deliver working software frequently | To promote sustainable development | To minimize the amount of work in progress | To maximize the amount of work not done |  |  | B |  | 1
As a scrum master, you are facilitating a retrospective for a sprint that failed to meet all of its objectives. Members of the development team and the product owner are arguing over who is responsible for the failure. After performing a root cause analysis, you uncover the source of the conflict. Of the following, what did you most likely discover? | Multiple Choice | You, as the scrum master, failed to assign user stories to the development team. | The development team decided how many user stories were to be completed during the sprint. | The Gantt chart did not include enough story points. | The product owner determined how many user stories were to be completed during the sprint. |  |  | D |  | 1
As part of the Estimate Activity Durations process, the project manager facilitates a sprint planning meeting with the product owner and Scrum team. The project manager breaks down the user stories Into low-level tasks, estimates the time required in hours, and determines the sprint backlog based on the team's capacity. Despite meticulous planning, the sprint falls. What might the project manager have done differently? | Multiple Choice | Used story points instead of hours while estimating the size of the user stories and tasks | Asked the team to prioritize the product backlog before determining the sprint backlog | Assigned the identified low-level tasks to specific individuals in the project schedule | Empowered the team to determine how many user stories they can complete during the sprint |  |  | D |  | 1
You are always struggling with resource supply for your project as they are shared across various projects. Who should you escalate this issue to? | Multiple Choice | The organization's PMO | The Procurement manager | The sponsor | The HR department |  |  | A |  | 1
Your organization's PMO is periodically asking for project artifacts from all projects and checking whether corporate standards of project management are being adhered to or not. They are also supportive in providing templates and guidelines related to project management when asked. Which type of PMO are we referring to here? | Multiple Choice | Controlling PMO | Directing PMO | Governing PMO | Supporting PMO |  |  | A |  | 1
Your project team is making significant progress. You want to prepare Work Performance information and distribute it to the stakeholders so that they are aware of project progress. Which of the following can be included as Work Performance information? | Multiple Choice | Number of Defects | Status of Deliverables | Number of Team Members | Actual Costs |  |  | B |  | 1
You have been appointed a project manager within an information systems organization. You are not aware of the organization's policies and procedures. If you want to know more about the organization's general issues management procedures, which of the following should you review? | Multiple Choice | Enterprise environmental factors ( EEF) | Issue Log | Organizational Process Assets ( OPA) | Project Management Plan |  |  | C |  | 1
A project manager has Just taken over a project to develop a product using a hybrid life cycle. With this project, the hardware has fixed requirements while the software requirements are still evolving. How should the project manager apply the hybrid life cycle for this project? | Multiple Choice | Develop the hardware with a predictive life cycle and use an adaptive life cycle for the software | Both the hardware and software should have their scope defined iteratively | Develop the software with a predictive life cycle and use an adaptive life cycle for the hardware | Both the hardware and software should have their scope defined during initial project planning |  |  | A |  | 1
Which of the following business documents Justify why the project is authorized? | Multiple Choice | Business case | Project charter. | Project management plan. | Scope statement of work. |  |  | A |  | 1
You are a project manager managing a large software project. Your project team sent confidential information to the subcontractor by mistake. What could have prevented this situation? | Multiple Choice | Reviewing the Scope management Plan | Reviewing the Communication management Plan | Review stakeholder register | Reviewing the stakeholder engagement Plan |  |  | B |  | 1
Which of the following interpersonal and team skills helps to reduce misunderstandings and improves communication and knowledge sharing? | Multiple Choice | Active listening | Leadership | Political awareness | Lessons learned register |  |  | A |  | 1
Which of the following activities is the most important to perform to help manage a project meeting? | Multiple Choice | Ensure that every attendee has a chance to speak | limit the meeting to a specific length of time | Follow up on action items | Create and follow an agenda |  |  | D |  | 1
You recently took over a large project from another project manager who had to leave for a personal emergency. You want to understand what kind of information should be provided to different stakeholders, and what methods should be used to provide this information. You will find this information in the: | Multiple Choice | Project Communications | Stakeholder engagement plan | Enterprise environnemental factor | Communications Management Plan |  |  | D |  | 1
John is the project manager for a research and development project. The last few meetings were a disaster since more time was spent in arguments, less on decisions and, the meeting takes a long time. What should have done to prevent this situation? | Multiple Choice | Set a meeting agenda before the meeting | Use Listening techniques | Set a virtual conversation | Invite only team members boss |  |  | A |  | 1
You Just completed the first phase of a multi-phase project. You have calculated earned value measurements and found that the current CPI is 0.79 and the current SPI is 1.08. Your next phase plan should focus first on which element of the project: | Multiple Choice | Scope | Quality | Cost | Schedule |  |  | C |  | 1
You are running a software development project and currently, the project stakeholders are in the process of accepting deliverables. While doing this task they want to compare nonfunctional requirements such as level of service, performance, and supportability for the deliverables to see if the deliverables meet the requirements. These non-functional requirements are usually documented in the: | Multiple Choice | Requirements Documentation | Work Breakdown Structure | Issue Log | Requirements Management Plan |  |  | A |  | 1
A project manager is currently in the process of determining, documenting, and managing stakeholder needs and requirements. Due to the sensitive nature of the project, there is a concern that some stakeholders will not provide candid feedback unless confidentially is maintained. What is the project manager's best course of action? | Multiple Choice | Conduct interviews to elicit information from stakeholders by talking to them directly | Use brainstorming to generate and collect multiple ideas related to project requirements | Hold a focus group to learn about stakeholder expectations and attitudes about the project | Use multicriteria decision analysis to provide a systematic analytical approach for establishing criteria |  |  | A |  | 1
During a presentation to management, you want to display the project schedule with only the key deliverables displayed. What is the correct tool for this purpose? | Multiple Choice | Critical chain diagram | Control chart | Milestone chart | Critical path method |  |  | C |  | 1
You are managing a complex construction project and you request a five-year schedule for this project. Although multiple brainstorming sessions with your project team, you struggle to provide detail for the project management plan. This causes a delay in obtaining the project management plan approvals. As a project manager, what should you have done to avoid this situation? | Multiple Choice | Used decomposition techniques. | Used the rolling wave planning technique for activity planning. | Used subject matter expert to develop the detailed schedule. | Created a high level Gantt chart to represent the milestone only. |  |  | B |  | 1
You have been assigned to lead an agile project. You want to ensure that project information is shared within and across the organization, so that any misalignments, dependencies, or other issues related to the frequently changing requirements are surfaced as quickly as possible. How could this goal be best achieved? | Multiple Choice | By promoting aggressive transparency | By inviting stakeholders to daily standups | By distributing the project report weekly | By sharing comprehensive documentation |  |  | A |  | 1
While performing project work, a team member notices that there is a potential new risk, which could impact the project's critical path. What should the team member do immediately? | Multiple Choice | Document the risk in the risk register | Generate a risk report using qualitative analysis of the identified risk to alert the team of the schedule impacts | Draft an emergency fallback plan since the critical path is in jeopardy | Recommend the project be placed on hold for a day to avoid the risk |  |  | A |  | 1
You are a project manager in a construction project. During the implementation phase, you observe conflicts between project stakeholders, resulting in deliverable and output approval delays. Which area should you focus? | Multiple Choice | Revisiting the stakeholder engagement plan, focusing on specific overlooked stakeholders. | Increasing the frequency of project update meetings to keep stakeholders informed. | Revisiting the project management plan to ensure deliverables are on time. | Reviewing the business documents and identifying gaps within scope. |  |  | A |  | 1
A project manager is working on a large IT project. During a review for one of the deliverables, a stakeholder raised a concern about the final product. What should the project manager do first? | Multiple Choice | Set up a meeting with the sponsor to discuss the details of the deliverable. | Set up a meeting with the product owner to discuss the stakeholder's concern. | Discuss this with the team and review the project requirements documentation. | Discuss this with the team and put the stakeholder's concern in the issue log. |  |  | B |  | 1
A company has always utilized a predictive approach to project management, but now the project management office wants to incorporate some agile best practices to generate earlier revenue realization. The project manager is about to begin planning for the new project and is concerned that the project team is not equipped to work in a hybrid environment. What is the project manager's best course of action? | Multiple Choice | Empower the team to self-organize and study agile best practices | Request the training from the project management office (PMO) | Add the risk of the team's inadequate agile skills to the risk register | Check the lessons learned repository for agile best practices |  |  | B |  | 1
During a project that affects the entire organization, some groups of stakeholders appear to have low product expectations. As a result, they are not performing as expected. This may put project objectives at risk . What should the project manager do? | Multiple Choice | Speak with the problematic stakeholders to increase their performance. | Submit a change request. | Follow the stakeholder engagement plan. | Ask the project sponsor to intervene and motivate the underperforming stakeholders. |  |  | C |  | 1
During the execution of a project, the project manager discovers that one branch team's tasks are being ineffectively influenced by one team member. What should a project manager use to ensure good working relationships among team members? | Multiple Choice | Team-building activities. | Interpersonal skills. | Ground rules. | Recognition and rewards. |  |  | A |  | 1
You are a scrum master leading an agile project team that has been consistently meeting the goals set for each iteration. However, you feel that one team member is less productive than the others. What is the most appropriate feedback approach for you to take in this situation? | Multiple Choice | From the next iteration onward, assign the team member the easiest user stories | Call out the team member's low productivity at the upcoming iteration retrospective | Direct the underperforming team member to work extra hours to bridge the gap | Allow the project team members to address the issue if they deem necessary |  |  | D |  | 1
You have identified a risk that may cause safety concerns for the workers completing the task. You've decided to hire a third party to complete this work because the risk is too great to accept internally. Which risk response is this? | Multiple Choice | Avoidance | Transference | Mitigation | Acceptance |  |  | B |  | 1
The project near to complete and a previously unidentified risk is discovered. Which funds will the project manager use to cover this risk? | Multiple Choice | Project Funding baseline | Management reserves | Cost baseline | Contingency reserves |  |  | B |  | 1
There are a variety of stakeholders on your project representing several different functional areas. While collecting requirements from all of them, you want to define the cross-functional requirements and reconcile stakeholder differences. Which requirement collection techniques is best used to achieve this goal? | Multiple Choice | Interviews | Focus Groups | Facilitation | Brainstorming |  |  | C |  | 1
Your team member wants to make technical changes to an activity, which will add more time to that activity. What should you do? | Multiple Choice | Check if the activity is on critical path | Report to senior management | Ignore change in activities | Allow team members to change the activity |  |  | A |  | 1
You are a project manager who is in charge of an important project for your company. A contractor submits a high level project schedule for a three-year project, including a detailed design-phase schedule. What does this describe? | Multiple Choice | Rolling wave planning. | Expert judgement. | Schedule management plan | Decomposition |  |  | A |  | 1
Jack is the project manager of a project that is halfway through its execution. The project sponsor wants to add a new feature that wasn't defined during the initial requirement gathering phase. 15,000 USO will be required to add this feature. Based on the following data, (the estimated direct cost for a project is 200,000 USO , the estimated of rework is 15,000 USO , and management reserve is 20,000 USO ), what should Jack do? | Multiple Choice | The Project manager should Use 15,000 USD for rework. | The Project manager should Use 15,000 USD of management reserves. | Seek approval from management to increase the project budget by 15,000 USD | Issue a change request to increase the cost budget by 15,000 USD |  |  | D |  | 1
A project with a hard timeline is starting its first iteration out of six. The project team is lacking the necessary skills to execute. What should the project manager do? | Multiple Choice | Add a subject matter expert (SME) to the project team. | Allow the team to proceed as they attempt to meet the timeline. | Fill the skill gap personally to execute the project. | Invite stakeholders to discuss a mitigation plan to finish on time. |  |  | C |  | 1
A software development project completed the initiation phase. The technical design was approved by the project steering committee. Later, it was discovered that the design will impact the company's production system. A new technical design must be found and this could delay the project by 3 months. What should the project manager do first? | Multiple Choice | Continue with the approved design so that the project is not delayed. | Ask the steering committee to approve a new technical design. | Log the technical design delay as a risk in the project risk log. | Set up a steering committee session to review the project delay. |  |  | C |  | 1
A project team is planning the next sprint review. The project lead receives an email from a senior manager asking for a project status using a template that is more detailed than the one used for monthly reports sent to the project management office (PMO). The team uses an electronic product backlog and a kanban board to track the progress. What should the project manager do next? | Multiple Choice | Organize a review of the kanban board with the manager. | Contact the senior manager and discuss their needs. | Modify the PMO template to include the information. | Give the senior manager access to the product backlog. |  |  | B |  | 1
A project team has been working together for about 2 years. One of the team members has consistently shown high performance and stood out among their peers during the execution of the project. How should the project manager recognize high performance? | Multiple Choice | Choose a reward for the team member that aligns with their personal goals. | Thank the team member privately to avoid conflict among the team members. | Acknowledge the high-performing team member in the next team meeting. | Ask the sponsor to approve a bonus for the high-performing team member. |  |  | A |  | 1
During a monthly review meeting, a high-performing team member raised a concern about the quality feedback mechanism. The team member expressed that they are not able to deliver high-quality output. What should the project manager do first? | Multiple Choice | Request feedback from stakeholders about the quality delivery. | Assign the work based on the skill sets of team members. | Assign the work in consultation with the functional manager. | Discuss this with the team and review the quality process. |  |  | D |  | 1
A large project requires new equipment to support the project execution. The procurement manager communicated to the project manager that the delivery of the newly purchased equipment will be delayed. The project manager is concerned that this will directly effect the project schedule. What should the project manager do next? | Multiple Choice | Source second-hand equipment in order to prepare for any delivery delays. | Validate the information and update the risk management plan. | Update the sponsor of the potential issue and ask for any suggestions. | Update the risk register and discuss it with the project stakeholders. |  |  | D |  | 1
A company is going through structural changes. A couple of people will leave the company as their positions were made redundant. The team members are unhappy as they do not understand why the changes are being made when the project is on track. What should the project manager do? | Multiple Choice | Advise the team to continue their work as planned because the schedule cannot be changed. | Organize a team meeting to discuss the changes and their importance for the company. | Advise the team that the changes were decided by the CEO and must be implemented. | Inform the project sponsor about the team's unhappiness and ask for overtime pay. |  |  | B |  | 1
During the execution of a project, an experienced team member informs the project manager that they cannot take part in all of the scheduled project activities due to a conflicting operational schedule. What should the project manager do? | Multiple Choice | Discuss the situation with the team member's functional manager to see if the schedule can be adjusted. | Replace the team member with another available resource on the team. | Check with the project management office (PMO) on the available resources to complete the activities. | Encourage the team member to prioritize scheduled project activities. |  |  | A |  | 1
At the end of a project, the project manager was asked to provide a performance rating of the project team members. What should the project manager mainly make reference to? | Multiple Choice | Agreed-upon key performance indicators (KPls) | Feedback from the project sponsor | Competencies of team members | Input from project stakeholders |  |  | A |  | 1
A steering committee member is complaining about the weekly report. They stated that the report is too long and has unnecessary details. As a result, they are unable to obtain the main message and take action. What should the project manager do to avoid similar complaints? | Multiple Choice | Send a shorter daily report to this steering committee member. | Verify the information needed for steering committee members. | Demonstrate the weekly reports in a presentation for the steering committee member. | Present the status at a weekly meeting with the steering committee. |  |  | B |  | 1
In a daily standup meeting, a developer indicates that a backlog item will not be delivered because they need to take an unexpected leave for the next couple of days. The backlog item is a prerequisite for a feature expected by users in the next sprint review. What should the project lead do? | Multiple Choice | Ask the development manager to provide a replacement for a couple of days. | Work with the product owner to change the priorities in the sprint backlog. | Ask the developer to postpone the leave until the backlog item is delivered. | Work with the product owner to inform the users that the feature is delayed. |  |  | A |  | 1
A project manager is managing the transition to operations. The project sponsor wants to ensure that good support is provided to the end users. What should the project manager do? | Multiple Choice | Ensure that knowledge is transferred to the operations team. | Ensure that comprehensive documentation is handed over. | Ensure that the user guide is detailed and has clear instructions. | Ask the project team to provide operational support for 1 year. |  |  | A |  | 1
Which of the following documents links product requirements from their origin to the deliverables that satisfy them and provides a structure for managing changes to the product scope? | Multiple Choice | Requirements documentation | Requirements tractability matrix | Project charter | Risk register |  |  | B |  | 1
The end-user rejects some type of deliverables, although many of the requirements are met. After conducting a root cause analysts, the project manager learns that a specific quality control process was not performed due to a lack of resources. What should the project manager have done to avoid this? | Multiple Choice | Ensured that quality was managed | Requested more resources for quality control activity | Held quality control process meetings. | Created quality checklists. |  |  | A |  | 1
Internal restructuring by the customer has resulted in the replacement of some key stakeholders. What should the project manager do first? | Multiple Choice | Review and execute the communication management plan. | Review and update the stakeholder engagement plan. | Hold another kick-off meeting with the new stakeholders to re-establish the project baseline. | Distribute a summary of the project's current status to the new stakeholders. |  |  | B |  | 1
In your project, a supplier delivers equipment that falls to meet customer requirements. after the investigation, you determined that the supplier misunderstood the requirements and make incorrect assumptions without clarifying them with the customer. As a project manager, what type of communication methods should you have used to avoid this? | Multiple Choice | Pull communication | Push communication | Interactive communication | Manual communication |  |  | C |  | 1
A project manager prepared a project benefits management plan. Which of the following should be included in this document? | Multiple Choice | Target benefits, strategic alignment, time frame for realizing benefits | Target benefits, benefits owner, lessons learned | Project requirements, target benefits, issue log, metrics | Strategic alignment, benefits owner, risk register |  |  | A |  | 1
During the execution stage, the project manager discovered that one team member is not able to complete their work on time and is running later than expected. This delay may potentially impact a project milestone. What should the project manager do first? | Multiple Choice | Discuss with the team and assess the reasons that led to the delay. | Request the team member's manager to find a solution. | Discuss with senior management and seek their guidance. | Assign more resources form other teams on the late work. |  |  | A |  | 1
A distributed project team has communication issues because of their collaboration tools. The team feels that efficiency could be improved by changing the collaboration platform. What should the project manager do? | Multiple Choice | Escalate the issue to the sponsor and ask them to decide. | Discuss this with the project team and select the appropriate tools. | Implement the communication tools used by other project teams. | Inform the project team to continue using the current tools. |  |  | B |  | 1
A highly critical project is in jeopardy due to missing professional resources. What should the newly assigned project manager do first? | Multiple Choice | Determine the possibility for team members to split up the required tasks. | Find available professionals within the organization to fill the gaps. | Allocate funding for seeking external professionals to fill the gaps. | Request additional budget for team training for the missing expertise. |  |  | B |  | 1
A project manager starts to receive emails from different stakeholders requesting information about the project status. What should the project manager do to avoid this in the future? | Multiple Choice | Designate a team member to respond to the emails from these stakeholders. | Include the stakeholders' emails in all of the project status communications. | Include the project stakeholders' needs while planning the project communications strategy. | Schedule weekly project status meetings with all stakeholders including the customer and internal resources |  |  | B |  | 1
A team member has very strong technical skills and is interested in a leadership role. A leadership position opens up outside of the team in the organization. The project manager has observed that the team member has a major gap in communicating in a professional manner. What should the project manager do? | Multiple Choice | Recommend the team member for effective communication training and support their career development interests. | Suggest the team member focus on positions with technical aspects and possible technical career opportunities | Ask the team member to refrain from pursuing new opportunities as they are not a suitable fit for a leadership position. | Encourage the team member to stay in their current role as they are important to the project |  |  | A |  | 1
A highly skilled team resource received a job offer and is leaving the project soon. What should the project manager do to maintain project performance while a new team member is being onboarded? | Multiple Choice | Motivate the new team member to perform. | Share project documents with the new team member | Log a risk in the risk register and work with the new team member to mitigate it | Offer to cross-train and mentoring to the new team member |  |  | D |  | 1
A project manager and project team are developing a strategic approach to engage the internal and external stakeholders. Which approach should be followed? | Multiple Choice | Classify all high-risk stakeholders and request that the project sponsor communicate directly with them. | Schedule status meetings with all stakeholders to allow their participation in all project discussions and reports. | Analyze both internal and external stakeholders and develop a customized engagement strategy for each stakeholder. | Involve only the internal stakeholders, as the external stakeholders should not have access to confidential information. |  |  | C |  | 1
During the execution phase of a project, a new project manager is assigned to replace the previous project manager. As the project manager starts managing the project, they discover that team performance is significantly decreasing, which is impacting the project's key performance indicators (KPlS). This team has delivered good performance on similar projects in the past. What should the project manager do next to improve this situation? | Multiple Choice | Call for a team meeting to identify the root cause for the declining performance. | Estimate the baseline impacts and submit a change request. | Implement compression techniques to bring the project back on track. | Review the resource management plan and organizational assets. |  |  | A |  | 1
After the second iteration of a component development project, the project team conducts a retrospective it shows that in the initial phase the project has failed to comply with product functionality. The planning for this product has a predominantly predictive approach. Which technique will help the project manager to accelerate the deliverable? | Multiple Choice | Scrum of Scrums | Impact mapping | Collective code ownership | Rolling wave planning |  |  | D |  | 1
A team is holding the first demonstration of the software built to date on a medium-sized project The product owner has uncovered a number of issues they would like to be addressed before providing approval How should the project manager approach this problem? | Multiple Choice | Plan to address the issues through backlog grooming and incorporate them into the next sprint | Refer the product owner to the signed business requirement document and explain that the current plan cannot facilitate these changes | Tell the product owner the issues will be addressed in the second version of the software | Refer the product owner to the change management plan, then escalate to the steering committee |  |  | A |  | 1
The project sponsor requested technical specifications for a project-related component. The project sponsor does not have the authorization to see the specifications but insists on seeing them. What should the project manager do first in this situation? | Multiple Choice | Update the issue log to make the project team aware and to develop a strategy | Meet with the project sponsor as soon as possible to discuss the matter further | Create a stakeholder engagement plan to help the team formulate a response | Provide the specifications to the project sponsor with some information removed |  |  | B |  | 1
During the third iteration, the team encounters a major delay that has not had significant improvements over the last few weeks What should the project manager do? | Multiple Choice | Request additional team members to help with improvements | Incorporate a predictive approach for this element. | Incorporate a predictive approach for this element. | Retrospect frequently and suggest improvements. |  |  | D |  | 1
Due to a company merger and acquisition process, the main stakeholder of a critical project has been changed. This new stakeholder complains that they were unaware of a delay on the project of which the rest of the stakeholders were aware. All the communications about the project are shared via email at the start of every week. How should the project manager address this situation? | Multiple Choice | Suggest that the new stakeholder review the project status before the next board meeting | Share the communications management plan with the new stakeholder | Send evidence to the new stakeholder that the project's status was sent according to the schedule | Discuss project requirements with the new stakeholder, and update the communications management plan. |  |  | D |  | 1
In a functional organization, a product analyst is assigned to a short-duration application development effort. The analyst expresses concerns about the task and asks the project manager to provide the support of a peer with expertise in this domain. What should the project manager do? | Multiple Choice | Make sure the analyst has regular pairing meetings with the other team member throughout task execution | Enroll the analyst in a capacity-building program and keep this analyst assigned to the task | Ask the analyst to use skills to develop the tool, then move development to another team member | Recognize the analyst's concerns and reassign the task to another team member |  |  | A |  | 1
During the daily meetings with the team the project manager notices that a new team member is not making the expected progress on an assigned taskWhat should the project manager do? | Multiple Choice | Ask an experienced team member to identify a replacement | Ask an experienced team member to coach the new team member | Ask the new team member to follow the team ground rules. | Ask the new team member to reassess their own capabilities |  |  | B |  | 1
An executive sponsor of a predictive project asked a project manager experienced in agile to assess if a project could be executed using an agile approach. What factor should the project manager consider when determining if the project is suitable for an agile approach? | Multiple Choice | The project is an information technology project and has minimal impact to the organization | The project scope is well defined and the requirements are prioritized | The project team has a co-located space and is capable of working together | The project scope can be decomposed into smaller parts, the first representing a minimum viable product (MVP). |  |  | C |  | 1
A project manager accepts a delivery at the project site but the items are of a poor quality. The project manager gets the local vendor to fix the items but more deliveries from this vendor are expected What should the project manager do going forward? | Multiple Choice | Review the contract requirements and ask for the applicable evidence for quality assurance | Allocate extra time to inspect deliveries for quality assurance upon arrival at the site | Call the vendor and have them verbally guarantee the quality of the next site delivery | Have the vendor issue the quality documentation prior to the next delivery. |  |  | A |  | 1
The project manager of a large construction project discovers that the blueprints received from the client appear incomplete. What should the project manager do first? | Multiple Choice | Reschedule the project execution date. | Consult with the client to determine if project execution should be continued. | Continue project execution using the current blueprints from the client. | Escalate this issue to the project sponsor |  |  | B |  | 1
An agile project is starting its seventh out of eight iterations In a planning meeting, the team realizes that an unidentified risk became an issue and the contingency reserve has to be used. What should the project manager do? | Multiple Choice | Ask the team to include the contingency plan in the iteration backlog | Ask the sponsor for money to implement the contingency plan. | Ask the sponsor to approve inclusion of an additional iteration to the project | Help the team review the project approach to initiate the corrective actions |  |  | D |  | 1
A project manager is managing a project which is approaching the end of the execution phase. A high-level stakeholder informs the project manager that a very important requirement was not included in the scope of the project, and that without that requirement the project will deliver no value. What is the first thing the project manager should do? | Multiple Choice | Inform the project sponsor about the situation and request assistance | Include the requirement into the project and schedule it as soon as possible | Evaluate the impact that the inclusion of this new requirement will have on project performance | Inform the stakeholder that it is impossible to add new requirements to an approved project |  |  | C |  | 1
During the execution of a maintenance project the contractor submits an offer for additional work. The project manager realizes that the activities billed are included in the initial scope of work. What should the project manager do next In this situation? | Multiple Choice | Submit a change request to approve the offer | Review the project scope and negotiate with the contractor | Review the project costs and communicate this to the project sponsor | Refuse the offer as it is included in the initial project scope |  |  | B |  | 1
A project manager is leading a team that is geographically dispersed. The team needs to collaborate and finalize the monthly reports. Occasionally, meetings occur during the weekends due to the time differences. Team members have expressed that they do not want to work on the weekends. What should the project manager do? | Multiple Choice | Avoid reporting during the months that team members would need to work on the weekend. | Remind the team members of their governance responsibilities documented in the team charter. | Take over the activity and deliver the reports whenever work is required on a weekend. | Communicate to the project stakeholders that the reports will be delayed certain months of the year. |  |  | B |  | 1
The change control board (CCB) rejects a change request submitted by a subject matter expert (SME) The SME refuses to accept this rejection and does not want to continue the project without the change What should the project manager have done to avoid this situation? | Multiple Choice | Submitted the change request directly to the CCB | Assessed the change's overall impact to the project before submission | Ensured that the change request was aligned with the project scope | Requested that the sponsor approved the change request first |  |  | B |  | 1
A project manager notices a conflict in the team on both technical and interpersonal levels during the execution phase of a project. What should the project manager do? | Multiple Choice | Hold a team meeting to understand and address the conflict. | Schedule a monthly meeting to handle all project conflicts. | Hire an external consultant to lead an organizational intervention | Address the conflicts during the lessons learned session. |  |  | A |  | 1
In the middle of a software development project, the lead design programmer accepted an offer from a competitor. The project manager needs to find a replacement to meet an upcoming milestone. What should the project manager do? | Multiple Choice | Assign the tasks to another team member. | Update the resource calendar. | Consult the risk response plan. | Issue a request to the change control board (CCB). |  |  | B |  | 1
The project velocity has recently slipped, and a decision was made to skip testing to increase the momentum and bong the project back on track. What will the project manager need to focus on as a result of this decision? | Multiple Choice | Increased burn rate | Increased cost | Decreased efficiency | Increased technical debt |  |  | D |  | 1
During the last sprint review, the product owner stated that the product does not deliver any value. The project manager believes that the product meets all the provided specifications. The team is confused by the product owner's statement. What should the project manager do when using a hybrid approach? | Multiple Choice | Review the project's benefits management plan with the product owner | Escalate the matter to the executive board so they can decide on next steps | Prioritize the project backlog and ask the development team to �x the issues | Ask the product owner to terminate the project as it is no longer aligned to the expected benefits |  |  | A |  | 1
During daily team standup meetings, team members constantly ask about which tasks they should focus on first. How should the project manager ensure. the team is fully productive? | Multiple Choice | Ensure team members are working according to the project plan. | Encourage project team members to prioritize the product backlog. | Review the project backlog during the team's standup meeting. | Work with the product owner to ensure the project backlog is prioritized. |  |  | D |  | 1
A company is conducting a digital transformation project that has a hard deadline. The marketing team wants to combine this implementation with a new product, and the newly assigned project manager is not aware of all the dependencies. Using a hybrid approach, what should the project manager do to ensure the dependencies are taken into consideration? | Multiple Choice | Combine all of the small projects into one big project so the team can collaborate better as one big team. | Implement a project newsletter so the different team members can be informed about the progress of each project. | Make sure that each individual project schedule is aligned with the common deadlines. | Facilitate communication promoting a Scrum of Scrums so the different teams are aware of the dependencies and progress. |  |  | D |  | 1
A team has individual daily start times for each team member. Sometimes the overlap between team member working hours is short. During those times, the interactions and work as a team are reduced and ineffective. What should the project manager do? | Multiple Choice | Allocate the overlap time for each team member and ask them to adhere to the schedule. | Ask the team to define a team charter and agree on core working hours. | Ask the team to start at the same time to obtain the maximum number of team working hours. | Inform the team members who are joining late to join early and work together. |  |  | B |  | 1
Several components of an expensive manufacturing project have been returned by the customer. The customer is complaining that the quality of the components is poor and is concerned that, as a result, their products will be returned clue to quality issues. The project manager is certain that quality has been maintained. How should the project manager communicate with the customer to help assure them that the project has produced quality products? | Multiple Choice | Show the customer sample results from the current batch. | Show the customer the quality control measurements. | Show the customer the tolerance and control limits. | Show the customer a sample history of quality. |  |  | B |  | 1
A project manager is newly appointed to lead a project team that will be working remotely. The project manager decided to use a set of tools that worked well for previous projects. However, a few team members are not happy with this plan. What should the project manager have. clone to avoid this? | Multiple Choice | Asked the project sponsor for approval to purchase the newest collaboration tool on the market. | Allowed the project team members to use the tools that will work best for them for this project. | Delegated the responsibility of selecting the collaboration tools to the project's technical lead. | Met with the project team to determine their collaboration needs and identified tools that will work best. |  |  | D |  | 1
When a project is in its final stage, the project manager will request from the team to prepare a delivery acceptance document. What is the importance of this document to the project manager? | Multiple Choice | Needed to close the work breakdown structure (WBS). | Needed to share it with the stakeholders. | Needed to release the team at the end of the project. | Needed to close out the project or a phase. |  |  | D |  | 1
A development team is struggling to find design documentation for the upcoming sprint. Prior to leaving for vacation, the product owner communicated that the documentation had been uploaded to the project file repository. What should the project manager do to address this issue? | Multiple Choice | Investigate new software tools used to manage project artifacts. | Audit the effectiveness of the management of project artifacts. | Improve email communication protocols to manage project artifacts. | Assign a team member to manage project artifacts. |  |  | B |  | 1
In an agile team, some of the team members are coming forward to ask for more autonomy on the project. What should the project manager do in this situation? | Multiple Choice | Discourage this request, as it is for the management team. | Discourage them as conflicts may be created. | Encourage the team lead to make decisions. | Encourage the team members to make decisions |  |  | D |  | 1
A project manager has been assigned to deliver a challenging project on time and within budget. The project manager needs to empower the team members by removing organizational impediments and facilitating collaboration. What should the project manager do to lead the project? | Multiple Choice | Use a servant-leader approach. | Act as the project owner. | Perform the project sponsor activities. | Assume the functional manager role. |  |  | A |  | 1
During an iteration review session, some product features are at risk of being canceled due to high operational costs when the product is launched into a production environment. What type of analysis should the project lead have conducted to avoid this situation? | Multiple Choice | Capacity analysis | Risk analysis | Benefits analysis | Gap analysis |  |  | B |  | 1
If an Agile team planned to complete 30 story points In an Iteration but worked at only 83% of the rate planned.What is the project's SPI? | Multiple Choice | 25 story points | 36 story points | SPI cannot be determined from the given information. | 0.83 |  |  | D |  | 1
The project manager and project team have worked together for many years. There is a deep sense of community and collaboration. Everyone knows their stuff and gets better with every project. Which leadership style of the project manager is most effective In deepening those connections? | Multiple Choice | Charismatic leadership | Servant leadership | Transformational leadership | Communications leadership |  |  | B |  | 1
A project team consisting of various professionals of different nationalities is struggling to achieve their project deliverables. What should the project manager do? | Multiple Choice | Ask the functional department manager to replace the team members. | Provide the team with support to solve their own problems. | Inform the project sponsor and train the entire team. | Ask the human resources (HR) department to conduct performance training. |  |  | B |  | 1
An experienced team member has joined a project during the execution phase. What should the project manager do to ensure the new team member engages with the team quickly? | Multiple Choice | Allow the new team member to meet with the team and start their assigned tasks independently. | Set up a meeting with the new team member to go through all of the project documents and assigned tasks. | Ask a team member to set up a meeting to communicate the project's detailed scope and task assignments to the new member | Send an email to the new team member with the status of the project and assigned tasks. |  |  | A |  | 1
A project is ready to deliver the first batch of the product when a quality control check rejects the product as unfit for delivery. The root cause analysis (RCA) shows that a component added as part of the latest change request was not tested throughout the development cycle. What should the project manager do next? | Multiple Choice | Review the change control process to ensure quality management artifacts are updated as part of the change. | Review the communications management plan to ensure change requests are communicated to the affected team members. | Review the quality management process with the project management office (PMO) to ensure compliance with best practices. | Review the quality management process and perform a process audit as part of ongoing quality assurance. |  |  | A |  | 1
An enthusiastic, newly hired vice-president has been assigned as the product owner for a digital transformation project. The project manager advises the product owner that. some of the functional requirements are not aligned with the chief information technology officer's (CTO) strategy. The product owner tells the project manager that the CTO is not part of the project and should not be engaged at. this moment. What should the project manager do? | Multiple Choice | Continue building the backlog since they are functional requirements. | Review the organizational process assets (OPAs) for historical information from similar projects. | Influence the product owner to review the engagement needed from other stakeholders. | Advise the CTO about the possible impacts caused by the project. |  |  | C |  | 1
A business transformation project has a four-phase delivery plan. The project team has successfully delivered one phase of the project. To further enhance team performance and empower team members, which two actions should the project manager take? (Choose two) | Multiple Choice | Allow team members to make limited decisions. | Support team members to make decisions in their areas of strength. | Organize and assign team members to tasks where they have strengths. | Vet all of the decisions before execution. | Encourage team members to cross-check decisions with the project manager.Support team members to make decisions in their 1. |  | C |  | 1
The deliverables of a project have been completed. However, the stakeholders did not approve the deliverables, because they did not cover the needs of the business. Which actions should the project manager have taken to avoidthis situation? | Multiple Choice | Provided and explained the sprint backlog at the beginning of the project to the stakeholders and project team. | Ensured that the stakeholders participated in the daily meetings to confirm that the project was developing correctly. | Requested that the team change the frequency of the deliverables in the development phase to obtain earlier feedback. | Defined the project management plan and ensured it met the project objectives and business needs. |  |  | D |  | 1
You are a project manager on a software project. You work with a global virtual team. The team is facing difficulty in communicating with each other and often misses important messages. This difficulty leads to missed deadlines. What should you do to enhance project team effectiveness? | Multiple Choice | Identify the root cause of communication issues. | Initiate daily communication of project progress. | Implement team colocation to improve communication. | Schedule a communication control board meeting |  |  | C |  | 1
A company is using a predictive approach for the development of a particular component as defined in the scope management plan. Due to regularly changing regulatory requirements, the development team has requested to utilize agile approaches. What should the project manager do about the development team's request"? | Multiple Choice | Escalate the request for additional financial resources | Analyze the requirements that will need to be addressed under the requested method | Ask the project sponsor to obtain approval for implementation of the new approach | Forward the request to the project management office (PMO) to amend the organizational process assets |  |  | B |  | 1